## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | DALMORE TG & RAMJHORA TG WATER SUPPLY SCHEME | SM/00043 | New | Repairing and rewinding of 20HP submersible pumping machinery at P/H No.-II under Dolmore TG & Ramjhora TG water supply scheme under AMSD PHE DTE. |  |  | ORD/000773/2020-2021 | 61/AMSD | 23/04/2020 | 03/05/2020 | SUNLIT | 0.21 | 0 | 0 | 0
2 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | DALMORE TG & RAMJHORA TG WATER SUPPLY SCHEME | SM/00043 | New | Withdrawing ,overhauling and installation of 20HP submersible pumping machinery at P/H No.-II under Dolmore TG & Ramjhora TG water supply scheme under AMSD PHE DTE. |  |  | ORD/000772/2020-2021 | 60/AMSD | 23/04/2020 | 03/05/2020 | SUNLIT | 0.21 | 0 | 0 | 0
3 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | DALMORE TG & RAMJHORA TG WATER SUPPLY SCHEME | SM/00043 | New | Supply, delivery and installation of 30 KVA servo motor operated Copper wound line voltage corrector at DALMORE T.G W/S Scheme TW NO- II under NMD-II, P.H.E. Dte.Alipurduar. |  |  | ORD/000038/2020-2021 | 1111/NMD-II | 08/10/2020 | 08/11/2020 | CHAKRABORTY MINING & ENGINEERING | 3.94 | 0 | 0 | 0
4 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | DALMORE TG & RAMJHORA TG WATER SUPPLY SCHEME | SM/00043 | New | Supply, delivery and installation of 30 KVA servo motor operated Copper wound line voltage corrector at DALMORE T.G W/S Scheme TW NO- I under NMD-II, P.H.E. Dte.Alipurduar. |  |  | ORD/000040/2020-2021 | 1112/NMD-II | 08/10/2020 | 08/11/2020 | B.B CONCERNED | 3.93 | 0 | 0 | 0
5 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | DALMORE TG & RAMJHORA TG WATER SUPPLY SCHEME | SM/00043 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at different PWSS under Birpara - Madarihat block in the dist. of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000521/2021-2022 | 1069/NMD-II | 10/09/2021 | 30/09/2021 | CHOWDHURY AND BASU ENTERPRISE | 4.72 | 0 | 0 | 0
6 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | DALMORE TG & RAMJHORA TG WATER SUPPLY SCHEME | SM/00043 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under DALMORE TG & RAMJHORA TG W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000409/2021-2022 | 565/NMD-II | 06/07/2021 | 06/07/2022 | MALAY KUMAR SAHA | 4.88 | 0 | 0 | 0
7 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | DALMORE TG & RAMJHORA TG WATER SUPPLY SCHEME | SM/00043 | New | Operation and Guarding of Pumping machinery at Pump House No. IV , Under DALMORE TG & RAMJHORA TG W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000410/2021-2022 | 566/NMD-II | 06/07/2021 | 06/07/2022 | MALAY KUMAR SAHA | 4.88 | 0 | 0 | 0
8 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | DALMORE TG & RAMJHORA TG WATER SUPPLY SCHEME | SM/00043 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under DALMORE TG & RAMJHORA TG W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000415/2021-2022 | 571/NMD-II | 06/07/2021 | 06/07/2022 | MALAY KUMAR SAHA | 4.88 | 0 | 0 | 0
Total | [13 empty] | 27.67 | 0 | 0