## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata | Alipurduar Division | FALAKATA WATER SUPPLY SCHEME | SM/00138 | New | Construction of boundary wall (Eastern, Western and Southern side) at Bhutnirghat Water Supply Scheme. |  |  | ORD/000006/2020-2021 | 02/ALD | 31/07/2020 | 30/08/2020 | GOUTAM KUMAR DAS | 4.81 | 0 | 0 | 0
2 | ALIPURDUAR | Falakata | Northern Mechanical Division II | FALAKATA WATER SUPPLY SCHEME | SM/00138 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under FALAKATA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000564/2021-2022 | 651/NMD-II | 06/07/2021 | 06/07/2022 | S.D CONCERN WORKSHOP | 4.88 | 0 | 0 | 0
3 | ALIPURDUAR | Falakata | Northern Mechanical Division II | FALAKATA WATER SUPPLY SCHEME | SM/00138 | New | -"Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at Bhutnirghat ,Choto salkumar, Dalimpur etc under Falakata block in the dist. of Alipurduar under NMD-II P.H E Dte¿ |  |  | ORD/000614/2021-2022 | 1114/NMD-II | 20/09/2021 | 20/10/2021 | M/S PARITOSH BHOWMICK & CO. | 2.15 | 0 | 0 | 0
4 | ALIPURDUAR | Falakata | Northern Mechanical Division II | FALAKATA WATER SUPPLY SCHEME | SM/00138 | New | Supply, delivery and installation of standby automatically controlled hydrualic diaphragm type Chlorinator for accurate dosing of Chlorine solution at P/H No. I & II of Jateswar , Falakata W/S scheme under Falakata Block in the district of Alipurduar under NMD-II ,P.H.E Dte. |  |  | ORD/000590/2021-2022 | 1037/NMD-II | 02/09/2021 | 22/09/2021 | KASHI NATH DEY | 3.48 | 0 | 0 | 0
5 | ALIPURDUAR | Falakata | Northern Mechanical Division II | FALAKATA WATER SUPPLY SCHEME | SM/00138 | New | Operation and Guarding of Pumping machinery at Pump House No. I OF ZONE-I , Under FALAKATA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000717/2021-2022 | 1224/NMD-II | 28/10/2021 | 28/07/2022 | RMD TRADING | 2.22 | 0 | 0 | 0
6 | ALIPURDUAR | Falakata | Northern Mechanical Division II | FALAKATA WATER SUPPLY SCHEME | SM/00138 | New | Operation and Guarding of Pumping machinery at Pump House No. II OF ZONE-III , Under FALAKATA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000673/2021-2022 | 1219/NMD-II | 28/10/2021 | 28/07/2022 | CHOWDHURY AND BASU ENTERPRISE | 2.22 | 0 | 0 | 0
Total | [13 empty] | 19.77 | 0 | 0