## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | UTTAR MADARIHAT WATER SUPPLY SCHEME | SM/00139 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under UTTAR MADARIHAT W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000413/2021-2022 | 569/NMD-II | 06/07/2021 | 06/07/2022 | SUBODH KUMAR BANIK | 4.88 | 0 | 0 | 0
2 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | UTTAR MADARIHAT WATER SUPPLY SCHEME | SM/00139 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under UTTAR MADARIHAT W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000665/2021-2022 | 673/NMD-II | 06/07/2021 | 06/07/2022 | SUBODH KUMAR BANIK | 4.88 | 0 | 0 | 0
3 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | UTTAR MADARIHAT WATER SUPPLY SCHEME | SM/00139 | New | Supply, delivery and installation of standby automatically controlled hydrualic diaphragm type Chlorinator for accurate dosing of Chlorine solution at P/H No.I &II of Hasimara ,and uttar Madarihat PWSS in the district of Alipurduar under NMD-II ,P.H.E Dte. |  |  | ORD/000574/2021-2022 | 1036/NMD-II | 02/09/2021 | 22/09/2021 | AHALYA ENGINEERING WORKS | 3.51 | 0 | 0 | 0
Total | [13 empty] | 13.28 | 0 | 0