## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | SAMUKTALA WATER SUPPLY SCHEME | SM/00146 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at Shamultala,Loknathpur etc under Alipurduar-I& II Block in the dist. of Alipurduar¿ |  |  | ORD/000703/2021-2022 | 1314/NMD-II | 03/12/2021 | 18/12/2021 | M/S KUNDU CONSTRUCTION | 2.29 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | SAMUKTALA WATER SUPPLY SCHEME | SM/00146 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under SAMUKTALA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000318/2021-2022 | 627/NMD-II | 06/07/2021 | 06/07/2022 | CHOWDHURY AND BASU ENTERPRISE | 4.88 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | SAMUKTALA WATER SUPPLY SCHEME | SM/00146 | New | Additional Work related to yard lighting arrangement at P/H No.I under Samuktala W/S/Scheme under NMD-II ,P.H.E Dte |  |  | ORD/000827/2020-2021 | 875/AMSD | 04/02/2021 | 14/02/2021 | RMD TRADING | 0.22 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | SAMUKTALA WATER SUPPLY SCHEME | SM/00146 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under SAMUKTALA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000319/2021-2022 | 628/NMD-II | 06/07/2021 | 06/07/2022 | CHOWDHURY AND BASU ENTERPRISE | 4.88 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | SAMUKTALA WATER SUPPLY SCHEME | SM/00146 | New | Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at Samuktala,Dholajhora T.G, Purba Chepani etc under Alipurduar block in the dist. of Alipurduar under NMD-II P.H E Dte |  |  | ORD/000615/2021-2022 | 1111/NMD-II | 20/09/2021 | 20/10/2021 | COMBINE ENTERPRISES | 3.01 | 0 | 0 | 0
6 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | SAMUKTALA WATER SUPPLY SCHEME | SM/00146 | New | Supply,delivery & installation of automatically controlled Hydraulic diaphragm type chlorinator dosing pump at pump house no. I , of Samuktala water supply scheme under Northern Mechanical Division-II ,P.H.E Dte. |  |  | ORD/000607/2020-2021 | 818/AMSD | 15/01/2021 | 25/01/2021 | ALPHA ENTERPRISE | 0.82 | 0 | 0 | 0
7 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | SAMUKTALA WATER SUPPLY SCHEME | SM/00146 | New | Supply, delivery and installation of standby automatically controlled hydrualic diaphragm type Chlorinator for accurate dosing of Chlorine solution at differernt PWSS under Alipurduar-II Block in the district of Alipurduar under NMD-II ,P.H.E Dte. |  |  | ORD/000598/2021-2022 | 1043/NMD-II | 03/09/2021 | 23/09/2021 | WEST BENGAL ENGINEERING CO. | 3.5 | 0 | 0 | 0
8 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | SAMUKTALA WATER SUPPLY SCHEME | SM/00146 | New | Operation and Guarding of Pumping machinery at Pump House No. III , Under SAMUKTALA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000306/2021-2022 | 615/NMD-II | 06/07/2021 | 06/07/2022 | MUSTAFI CONCERN | 4.88 | 0 | 0 | 0
Total | [13 empty] | 24.49 | 0 | 0