## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | BAROBISA AREA WATER SUPPLY SCHEME | SM/00147 | New | Supply, delivery and installation of 25 KVA servo motor operated Copper wound line voltage corrector at BAROVISA W/S Scheme,T/W NO- IV under NMD-II, P.H.E. Dte.Alipurduar. |  |  | ORD/000047/2020-2021 | 1140/NMD-II | 15/10/2020 | 15/11/2020 | PRAGATI CONSTRUCTION COMPANY | 3.12 | 0 | 0 | 0
2 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | BAROBISA AREA WATER SUPPLY SCHEME | SM/00147 | New | Operation and Guarding of Pumping machinery at Pump House No. III , Under BAROVISA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000411/2021-2022 | 567/NMD-II | 06/07/2021 | 06/07/2022 | MALAY KUMAR SAHA | 4.88 | 0 | 0 | 0
3 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | BAROBISA AREA WATER SUPPLY SCHEME | SM/00147 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under BAROVISA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000389/2021-2022 | 556/NMD-II | 06/07/2021 | 06/07/2022 | BONANZA ENTERPRISE | 4.88 | 0 | 0 | 0
4 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | BAROBISA AREA WATER SUPPLY SCHEME | SM/00147 | New | Supply and Delivery of Calcium Hypochlorite[Ca(Ocl)2] granules at different PWSS under Kumargram Block in the District of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000531/2020-2021 | 1316/NMD-II | 29/12/2020 | 18/01/2021 | SUMON ELECTRICAL | 1.79 | 0 | 0 | 0
5 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | BAROBISA AREA WATER SUPPLY SCHEME | SM/00147 | New | Supply, delivery and installation of 25 KVA servo motor operated Copper wound line voltage corrector at BAROVISA W/S Scheme,T/W NO- II under NMD-II, P.H.E. Dte.Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000046/2020-2021 | 1139/NMD-II | 15/10/2020 | 15/11/2020 | B.B CONCERNED | 3.12 | 0 | 0 | 0
Total | [13 empty] | 17.8 | 0 | 0