## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | PATLAKHAWA WATER SUPPLY SCHEME | SM/00151 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under PATLAKHAWA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000536/2021-2022 | 643/NMD-II | 06/07/2021 | 06/07/2022 | M/S BHOWMIK & CO. | 4.88 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | PATLAKHAWA WATER SUPPLY SCHEME | SM/00151 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under PATLAKHAWA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000320/2021-2022 | 629/NMD-II | 06/07/2021 | 06/07/2022 | M/S BHOWMIK & CO. | 4.88 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | PATLAKHAWA WATER SUPPLY SCHEME | SM/00151 | New | Supply and Delivery of Calcium Hypochlorite[Ca(Ocl)2] granules at Different PWSS under Alipurduar-I & II Block in the Dist of Alipurduar under Northern Mechanical Division-II,PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000395/2021-2022 | 863/NMD-II | 28/07/2021 | 27/08/2021 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 3.58 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | PATLAKHAWA WATER SUPPLY SCHEME | SM/00151 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under PATLAKHAWA W/S Scheme, in the dist. Of Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000259/2022-2023 | 1027/NMD-II | 13/07/2022 | 13/07/2023 | M/S BHOWMIK & CO. | 4.89 | 0 | 0 | 100
Total | [13 empty] | 18.23 | 0 | 0