## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata | Northern Mechanical Division II | BHUTNIRGHAT WATER SUPPLY SCHEME | SM/00157 | New | Withdrawing 15 HP capacity submersible pump set and lowering same capacity stand by set at tube well no-I under BHUTNIRGHAT W/S Scheme, in the district of Alipurduar, AMSD,PHE DTE. |  |  | ORD/000612/2020-2021 | 42/AMSD | 20/04/2020 | 30/04/2020 | MAA ENTERPRISES | 0.11 | 0 | 0 | 0
2 | ALIPURDUAR | Falakata | Northern Mechanical Division II | BHUTNIRGHAT WATER SUPPLY SCHEME | SM/00157 | New | Withdrawing 15 HP capacity submercible pumpset and lowering same set after repairing at tube well no-II under BHUTNIRGHAT W/S Scheme, in the district of Alipurduar,AMSD,PHE Dte. |  |  | ORD/000770/2020-2021 | 25/AMSD | 15/04/2020 | 25/04/2020 | PRAGATI CONSTRUCTION COMPANY | 0.28 | 0 | 0 | 0
3 | ALIPURDUAR | Falakata | Northern Mechanical Division II | BHUTNIRGHAT WATER SUPPLY SCHEME | SM/00157 | New | Operation and Guarding of Pumping machinery at Pump House No. I under BHUTNIRGHAT W/S Scheme. In the dist. Of ALIPURDUAR |  |  | ORD/000485/2021-2022 | 584/NMD-II | 06/07/2021 | 06/07/2022 | M/S RATAN KUMAR DASGUPTA & CO. | 4.88 | 0 | 0 | 0
4 | ALIPURDUAR | Falakata | Northern Mechanical Division II | BHUTNIRGHAT WATER SUPPLY SCHEME | SM/00157 | New | Operation and Guarding of Pumping machinery at Pump House No. II under BHUTNIRGHAT W/S Scheme. In the dist. Of ALIPURDUAR |  |  | ORD/000486/2021-2022 | 585/NMD-II | 06/07/2021 | 06/07/2022 | M/S RATAN KUMAR DASGUPTA & CO. | 4.88 | 0 | 0 | 0
5 | ALIPURDUAR | Falakata | Northern Mechanical Division II | BHUTNIRGHAT WATER SUPPLY SCHEME | SM/00157 | New | -"Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at Bhutnirghat ,Choto salkumar, Dalimpur etc under Falakata block in the dist. of Alipurduar under NMD-II P.H E Dte¿ |  |  | ORD/000614/2021-2022 | 1114/NMD-II | 20/09/2021 | 20/10/2021 | M/S PARITOSH BHOWMICK & CO. | 2.15 | 0 | 0 | 0
6 | ALIPURDUAR | Falakata | Northern Mechanical Division II | BHUTNIRGHAT WATER SUPPLY SCHEME | SM/00157 | New | Supply, delivery and installation of standby automatically controlled hydraulic diaphragm type Chlorinator for accurate dosing of Chlorine solution at P/H No.II of Chhoto Salkumar , Jogijhora Barabak, BhutnirghatW/S Scheme and P/H No.I of Jogendrapur W/S Scheme of Falakata Block etc in the district of Alipurduar under NMD-II P.H.E Dte. |  |  | ORD/000595/2021-2022 | 1041/NMD-II | 03/09/2021 | 23/09/2021 | SARKAR ELECTRIC | 3.39 | 0 | 0 | 0
Total | [13 empty] | 15.69 | 0 | 0