## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata | Alipurduar Division | JAGIJHORA BARABAK MOUZA WATER SUPPLY SCHEME | SM/00848 | New | Construction of Pump House ,Boundary Wall and Tube well Boring by ODEX-165 Method of drilling including Rising Main for JAGIJHORA BARABAK PWSS under Alipurduar Division PHE DTE | Birpara A.E |  | ORD/000402/2021-2022 | 2393/ALD | 31/01/2022 | 01/05/2022 | SUBHAS CHANDRA ROY | 21.13 | 0 | 0 | 0
2 | ALIPURDUAR | Falakata | Northern Mechanical Division II | JAGIJHORA BARABAK MOUZA WATER SUPPLY SCHEME | SM/00848 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under JAGIJHORA BARABAK W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000369/2021-2022 | 732/NMD-II | 08/07/2021 | 08/07/2022 | UTTAM PAUL | 2.97 | 0 | 0 | 0
3 | ALIPURDUAR | Falakata | Northern Mechanical Division II | JAGIJHORA BARABAK MOUZA WATER SUPPLY SCHEME | SM/00848 | New | -"Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at Bhutnirghat ,Choto salkumar, Dalimpur etc under Falakata block in the dist. of Alipurduar under NMD-II P.H E Dte¿ |  |  | ORD/000614/2021-2022 | 1114/NMD-II | 20/09/2021 | 20/10/2021 | M/S PARITOSH BHOWMICK & CO. | 2.15 | 0 | 0 | 0
4 | ALIPURDUAR | Falakata | Northern Mechanical Division II | JAGIJHORA BARABAK MOUZA WATER SUPPLY SCHEME | SM/00848 | New | Operation and Guarding of Pumping machinery at pump house No. I under Jagijhora Barabak W/S Scheme ,in the dist. of Alipurduar. |  |  | ORD/000568/2021-2022 | 768/NMD-II | 08/07/2021 | 08/07/2022 | M/S BHOWMIK & CO. | 2.97 | 0 | 0 | 0
Total | [13 empty] | 29.21 | 0 | 0