## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | LANKAPARA WATER SUPPLY SCHEME | SM/00892 | New | Quotation for New service connection , Lankapara T/W No. III. Application No. 4002574435 |  |  | VCH/001109/2020-2021 |  | 06/10/2020 | 06/10/2020 | WBSEDCL | 1.76 | 0 | 0 | 0
2 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | LANKAPARA WATER SUPPLY SCHEME | SM/00892 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at different PWSS under Birpara - Madarihat block in the dist. of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000521/2021-2022 | 1069/NMD-II | 10/09/2021 | 30/09/2021 | CHOWDHURY AND BASU ENTERPRISE | 4.72 | 0 | 0 | 0
3 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | LANKAPARA WATER SUPPLY SCHEME | SM/00892 | New | Operation and Guarding of Pumping machinery at Pump House No. I (NEAR HEAD WORKS SITE) , Under LANKAPARA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000677/2021-2022 | 1215/NMD-II | 28/10/2021 | 28/07/2022 | CHOWDHURY AND BASU ENTERPRISE | 2.22 | 0 | 0 | 0
4 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | LANKAPARA WATER SUPPLY SCHEME | SM/00892 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under LANKAPARA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000376/2021-2022 | 737/NMD-II | 08/07/2021 | 08/07/2022 | RIPON DAS | 2.97 | 0 | 0 | 0
5 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | LANKAPARA WATER SUPPLY SCHEME | SM/00892 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under LANKAPARA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000364/2021-2022 | 729/NMD-II | 08/07/2021 | 08/07/2022 | RIPON DAS | 2.97 | 0 | 0 | 0
6 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | LANKAPARA WATER SUPPLY SCHEME | SM/00892 | New | Supply, delivery and installation of standby automatically controlled hydrualic diaphragm type Chlorinator for accurate dosing of Chlorine solution at P/H No.I of Lankapara T G ,Makrapar T.G Gargenda TG W/S scheme and P/H No.II of Uttar Kamakhyaguri in the district of Alipurduar under NMD-II ,P.H.E Dte. |  |  | ORD/000578/2021-2022 | 1026/NMD-II | 27/08/2021 | 16/09/2021 | DIAMOND ELECTRICAL WORKS | 3.5 | 0 | 0 | 0
Total | [13 empty] | 18.14 | 0 | 0