## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | UTTAR SISUBARI WATER SUPPLY SCHEME | SM/00895 | New | Withdrawing & installation of 15 HP Submersible pump machinery and repairing the same with allied electrical works under UTTARSISHUBARI WATER SUPPLY SCHEME,P/H No-II under Northern Mechanical Division-II Phe. Dte. In the dist. Of Alipurduar. |  |  | ORD/000947/2019-2020 | 865/AMSD | 17/02/2020 | 27/02/2020 | BLUE PINE | 0.59 | 0 | 0 | 0
2 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | UTTAR SISUBARI WATER SUPPLY SCHEME | SM/00895 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at different PWSS under Birpara - Madarihat block in the dist. of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000521/2021-2022 | 1069/NMD-II | 10/09/2021 | 30/09/2021 | CHOWDHURY AND BASU ENTERPRISE | 4.72 | 0 | 0 | 0
3 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | UTTAR SISUBARI WATER SUPPLY SCHEME | SM/00895 | New | Supply, delivery and installation of standby automatically controlled hydrualic diaphragm type Chlorinator for accurate dosing of Chlorine solution at P/H No.I of Shishubari ,BaraHauda , Madhu T.G W/S schemeand P/H No.II of Birpara Madarihat Block in the district of Alipurduar. |  |  | ORD/000546/2021-2022 | 1018/NMD-II | 27/08/2021 | 16/09/2021 | TAPAN BISWAS | 3.5 | 0 | 0 | 0
4 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | UTTAR SISUBARI WATER SUPPLY SCHEME | SM/00895 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under UTTAR SISUBARI W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000367/2021-2022 | 730/NMD-II | 08/07/2021 | 08/07/2022 | RIPON DAS | 2.97 | 0 | 0 | 0
5 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | UTTAR SISUBARI WATER SUPPLY SCHEME | SM/00895 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under UTTAR SISUBARI W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000656/2021-2022 | 773/NMD-II | 08/07/2021 | 08/07/2022 | M/S B ENTERPRISE | 2.97 | 0 | 0 | 0
Total | [13 empty] | 14.75 | 0 | 0