## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kumargram | Alipurduar Division | UTTAR KAMAKSHYAGURI (NM) WATER SUPPLY SCHEME | SM/01022 | New | Restoration of laying distribution system by replacing of damaged AC pipeline with UPVC pipeline and Providing House Connection of Uttar Kamakhyaguri Water Supply Scheme under Alipurduar Division, PHE Dte. (Part-B) | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000226/2021-2022 | 1574/ALD | 22/11/2021 | 21/01/2022 | M/S PALIT ENTERPRISE | 48.63 | 0 | 0 | 78
2 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | UTTAR KAMAKSHYAGURI (NM) WATER SUPPLY SCHEME | SM/01022 | New | Supply, delivery and installation of 25 KVA servo motor operated Copper wound line voltage corrector at UTTAR KAMAKHYAGURI W/S Scheme TW NO- IV under NMD-II, P.H.E. Dte.Alipurduar. |  |  | ORD/000044/2020-2021 | 1114/NMD-II | 08/10/2020 | 07/11/2020 | QUAZI NOZRUL ISLAM | 3.11 | 0 | 0 | 0
3 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | UTTAR KAMAKSHYAGURI (NM) WATER SUPPLY SCHEME | SM/01022 | New | Supply and Delivery of Calcium Hypochlorite[Ca(Ocl)2] granules at different PWSS under Kumargram Block in the District of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000533/2020-2021 | 1317/NMD-II | 29/12/2020 | 18/01/2021 | SARKAR ELECTRIC | 1.79 | 0 | 0 | 0
4 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | UTTAR KAMAKSHYAGURI (NM) WATER SUPPLY SCHEME | SM/01022 | New | Continuation for Operation & guarding of the pumping machinery at Pump House No. I under UTTAR KAMAKHYAGURI W/S Scheme, in the dist. Of Alipurduar P.H.E.,Dte. |  |  | ORD/000027/2021-2022 | 70/AMSD | 28/04/2021 | 27/07/2021 | M/S SAJAHAN CHOWDHURY | 0.72 | 0 | 0 | 0
5 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | UTTAR KAMAKSHYAGURI (NM) WATER SUPPLY SCHEME | SM/01022 | New | Supply, delivery and installation of standby automatically controlled hydrualic diaphragm type Chlorinator for accurate dosing of Chlorine solution at P/H No.I of Lankapara T G ,Makrapar T.G Gargenda TG W/S scheme and P/H No.II of Uttar Kamakhyaguri in the district of Alipurduar under NMD-II ,P.H.E Dte. |  |  | ORD/000578/2021-2022 | 1026/NMD-II | 27/08/2021 | 16/09/2021 | DIAMOND ELECTRICAL WORKS | 3.5 | 0 | 0 | 0
6 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | UTTAR KAMAKSHYAGURI (NM) WATER SUPPLY SCHEME | SM/01022 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at different PWSS under Kumargram block in the dist. of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000520/2021-2022 | 1076/NMD-II | 10/09/2021 | 30/09/2021 | M/S P.P ELECTRICALS | 3.58 | 0 | 0 | 0
7 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | UTTAR KAMAKSHYAGURI (NM) WATER SUPPLY SCHEME | SM/01022 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under UTTAR KAMAKHYAGURI W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000327/2021-2022 | 694/NMD-II | 07/07/2021 | 07/07/2022 | GEETA CONSTRUCTION | 2.97 | 0 | 0 | 0
8 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | UTTAR KAMAKSHYAGURI (NM) WATER SUPPLY SCHEME | SM/01022 | New | Operation and Guarding of Pumping machinery at Pump House No. III , Under UTTAR KAMAKHYAGURI W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000343/2021-2022 | 710/NMD-II | 08/07/2021 | 08/07/2022 | THE BANERJEE CONCERN | 2.97 | 0 | 0 | 0
9 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | UTTAR KAMAKSHYAGURI (NM) WATER SUPPLY SCHEME | SM/01022 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under UTTAR KAMAKHYAGURI W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000401/2021-2022 | 745/NMD-II | 08/07/2021 | 08/07/2022 | M/S SAJAHAN CHOWDHURY | 2.97 | 0 | 0 | 0
10 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | UTTAR KAMAKSHYAGURI (NM) WATER SUPPLY SCHEME | SM/01022 | New | Operation and Guarding of Pumping machinery at Pump House No. IV , Under UTTAR KAMAKHYAGURI W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000404/2021-2022 | 748/NMD-II | 08/07/2021 | 08/07/2022 | MALAY KUMAR SAHA | 2.97 | 0 | 0 | 0
Total | [13 empty] | 73.21 | 0 | 0