## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Makrapara W/S Scheme | SM/02173 | New | Operation and Guarding of Pumping machinery at Pump House No. I (AUG), Under MAKRAPARA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000349/2021-2022 | 716/NMD-II | 08/07/2021 | 08/07/2022 | DEY ENTERPRISE (MALDA) | 2.97 | 0 | 0 | 0
2 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Makrapara W/S Scheme | SM/02173 | New | Operation and Guarding of Pumping machinery at Pump House No. II under MAKRAPARA W/S Scheme. In the dist. Of ALIPURDUAR |  |  | ORD/000494/2021-2022 | 756/NMD-II | 08/07/2021 | 08/07/2022 | WEST BENGAL ENGINEERING CO. | 2.97 | 0 | 0 | 0
3 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Makrapara W/S Scheme | SM/02173 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under MAKRAPARA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000353/2021-2022 | 720/NMD-II | 08/07/2021 | 08/07/2022 | UTTAM PAUL | 2.97 | 0 | 0 | 0
4 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Makrapara W/S Scheme | SM/02173 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at different PWSS under Birpara - Madarihat block in the dist. of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000521/2021-2022 | 1069/NMD-II | 10/09/2021 | 30/09/2021 | CHOWDHURY AND BASU ENTERPRISE | 4.72 | 0 | 0 | 0
5 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Makrapara W/S Scheme | SM/02173 | New | Supply, delivery and installation of standby automatically controlled hydrualic diaphragm type Chlorinator for accurate dosing of Chlorine solution at P/H No.I of Lankapara T G ,Makrapar T.G Gargenda TG W/S scheme and P/H No.II of Uttar Kamakhyaguri in the district of Alipurduar under NMD-II ,P.H.E Dte. |  |  | ORD/000578/2021-2022 | 1026/NMD-II | 27/08/2021 | 16/09/2021 | DIAMOND ELECTRICAL WORKS | 3.5 | 0 | 0 | 0
Total | [13 empty] | 17.13 | 0 | 0