## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Alipurduar Division | Totopara Water Supply Scheme | SM/03080 | New | test |  |  | ORD/000002/2020-2021 | 22/a | 08/07/2020 | 23/07/2020 | GOUTAM KUMAR DAS | 14.23 | 0 | 0 | 0
2 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Totopara Water Supply Scheme | SM/03080 | New | Supply, delivery of Standby Submersible pumping Machinery for Emergency Breakdown at Pump House No-III Under TOTOPARA Water Supply Scheme under NMD-II,PHE Dte, Dist-Alipurduar. |  |  | ORD/000695/2020-2021 | 693/AMSD | 03/12/2020 | 10/12/2020 | PRAGATI CONSTRUCTION COMPANY | 0.55 | 0 | 0 | 0
3 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Totopara Water Supply Scheme | SM/03080 | New | Operation & guarding of the pumping machinery at Pump House No. III under TOTOPARA W/S Scheme, in the dist. Of Alipurduar P.H.E.,Dte. |  |  | ORD/000694/2020-2021 | 620/AMSD | 03/11/2020 | 26/02/2021 | HARAGOURI ENTERPRISE | 0.93 | 0 | 0 | 0
4 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Totopara Water Supply Scheme | SM/03080 | New | Continuation for Operation & guarding of the pumping machinery at Pump House No. III under TOTOPARA W/S Scheme, in the dist. Of Alipurduar P.H.E.,Dte. |  |  | ORD/000750/2020-2021 | 924/AMSD | 24/02/2021 | 24/06/2021 | HARAGOURI ENTERPRISE | 0.96 | 0 | 0 | 0
5 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Totopara Water Supply Scheme | SM/03080 | New | Continuation for Operation & guarding of the pumping machinery at Pump House No. III under TOTOPARA W/S Scheme, in the dist. Of Alipurduar P.H.E.,Dte. |  |  | ORD/000584/2021-2022 | 206/AMSD | 25/06/2021 | 25/07/2021 | HARAGOURI ENTERPRISE | 0.24 | 0 | 0 | 0
6 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Totopara Water Supply Scheme | SM/03080 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under TOTOPARA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000346/2021-2022 | 713/NMD-II | 08/07/2021 | 08/07/2022 | DEY ENTERPRISE (BALLY) | 2.97 | 0 | 0 | 0
7 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Totopara Water Supply Scheme | SM/03080 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under TOTOPARA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000330/2021-2022 | 697/NMD-II | 08/07/2021 | 08/07/2022 | INDRANI ENTERPRISE | 2.97 | 0 | 0 | 0
8 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Totopara Water Supply Scheme | SM/03080 | New | Operation and Guarding of Pumping machinery at Pump House No. III , Under TOTOPARA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000326/2021-2022 | 693/NMD-II | 07/07/2021 | 07/07/2022 | HARAGOURI ENTERPRISE | 2.97 | 0 | 0 | 0
9 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Totopara Water Supply Scheme | SM/03080 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at different PWSS under Birpara - Madarihat block in the dist. of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000521/2021-2022 | 1069/NMD-II | 10/09/2021 | 30/09/2021 | CHOWDHURY AND BASU ENTERPRISE | 4.72 | 0 | 0 | 0
Total | [13 empty] | 30.54 | 0 | 0