## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | Alipurduar Municipal Water Supply Scheme | SM/03561 | New | Withdrawing & installation of 20HP Submersible pump machinery under Alipurduar municipality Zone -III WATER SUPPLY SCHEME, under AMSD in the dist. Of Alipurduar |  |  | ORD/000759/2020-2021 | 582/AMSD | 07/10/2020 | 17/10/2020 | M/S SAJAHAN CHOWDHURY | 0.11 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | Alipurduar Municipal Water Supply Scheme | SM/03561 | New | Installation of Automatically Controlled Chlorinator (supply departmental) for accurate dosing of chlorine solution at Alipurduar Municipality under AMSD PHE. Dte. |  |  | ORD/000779/2020-2021 | 909/AMSD | 18/02/2021 | 28/02/2021 | M/S ANJALI ENTERPRISE | 0.11 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | Alipurduar Municipal Water Supply Scheme | SM/03561 | New | Operation and Guarding of Pumping machinery at Pump House No. I, Zone - I, Under Alipurduar Municipality W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000412/2021-2022 | 568/NMD-II | 06/07/2021 | 06/07/2022 | SUBODH KUMAR BANIK | 4.88 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | Alipurduar Municipal Water Supply Scheme | SM/03561 | New | Operation and Guarding of Pumping machinery at Pump House No. I (AUG.), Under Alipurduar Municipality W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000300/2021-2022 | 607/NMD-II | 06/07/2021 | 06/07/2022 | DAWA DUKPA | 4.88 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | Alipurduar Municipal Water Supply Scheme | SM/03561 | New | Operation and Guarding of Pumping machinery at Pump House No. II, Zone - I, Under Alipurduar Municipality W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000381/2021-2022 | 548/NMD-II | 06/07/2021 | 06/07/2022 | B.B CONCERNED | 4.88 | 0 | 0 | 0
Total | [13 empty] | 14.87 | 0 | 0