## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | Ground Water Based Water Supply Scheme for Banchukamari & Adj. Mouzas | SM/03708 | New | Supply, delivery & installation of automatically controlled Hydraulic diaphragm type chlorinator dosing pump at pump house no. II , of Banchukumari water supply scheme under Northern Mechanical Division-II ,P.H.E DTE. |  |  | ORD/000608/2020-2021 | 819/AMSD | 15/01/2021 | 25/01/2021 | ALPHA ENTERPRISE | 0.82 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | Ground Water Based Water Supply Scheme for Banchukamari & Adj. Mouzas | SM/03708 | New | Supply, delivery and installation of 25 KVA servo motor operated Copper wound line voltage corrector at BAROVISA W/S Scheme,T/W NO- II under NMD-II, P.H.E. Dte.Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000046/2020-2021 | 1139/NMD-II | 15/10/2020 | 14/11/2020 | B.B CONCERNED | 3.12 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | Ground Water Based Water Supply Scheme for Banchukamari & Adj. Mouzas | SM/03708 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under BANCHUKAMARI W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000328/2021-2022 | 695/NMD-II | 08/07/2021 | 08/07/2022 | M/S SAJAHAN CHOWDHURY | 2.97 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | Ground Water Based Water Supply Scheme for Banchukamari & Adj. Mouzas | SM/03708 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under BANCHUKAMARI W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000342/2021-2022 | 709/NMD-II | 08/07/2021 | 08/07/2022 | THE BANERJEE CONCERN | 2.97 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | Ground Water Based Water Supply Scheme for Banchukamari & Adj. Mouzas | SM/03708 | New | Supply and Delivery of Calcium Hypochlorite[Ca(Ocl)2] granules at Different PWSS under Alipurduar-I & II Block in the Dist of Alipurduar under Northern Mechanical Division-II,PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000395/2021-2022 | 863/NMD-II | 28/07/2021 | 27/08/2021 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 3.58 | 0 | 0 | 0
6 | ALIPURDUAR | Alipurduar - I | Northern Mechanical | Ground Water Based Water Supply Scheme for Banchukamari & Adj. Mouzas | SM/03708 | New | Certified that, the marked schemes vide Sl. No. 1-4, 9-11, 14, 16, 22, 29-31, 33, 36, 38, 44, 45, 50, 53, 55, 56, 65, 71, 73, 80-86, 89-92, 94, 103, 107, 108, 110-112, 134, 135, 141-143, 152, 154, 156, 158, 159, 161-163, 167, 168, 174-187, 202-210, 214, 222-229, 243, 266, 267, 277, 278, 287, 294, 300, 305, 317-320, 331, 332, 335-337, 340-342, 348, 349, 352, 353 comes under the jurisdiction of Northern Mechanical Division-II, PHE Dte. and which accured to Rs 55,50,591.00/- (Rupees fifty five lakh fifty thousand five hundred ninety one only) out of total balance amount Rs 6,13,62,046.94/- (Rupees six crore thirteen lakh sixty two thousand forty six and ninety four paise only) to be transferred at the Deposit Account of Northern Mechanical Division-II, PHE Dte. (Operator ID - 71 under Alipurduar Treasury) from the Deposit Account of Northern Mechanical Division, PHE Dte. (Operator ID - 69 under Siliguri Treasury-I) through inter treasury transfer module of IFMS. |  |  | VCH/000387/2019-2020 | 94/W/19-20 | 12/06/2019 |  | NORTHERN MECHANICAL DIVISION II, P.H.E. DTE. | 55.51 | 0 | 0 | 0
Total | [13 empty] | 68.96 | 0 | 0