## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | Ground Water Based Water Supply Scheme for Banchukamari & Adj. Mouzas | SM/03708 | New | Supply, delivery and installation of 25 KVA servo motor operated Copper wound line voltage corrector at BAROVISA W/S Scheme,T/W NO- II under NMD-II, P.H.E. Dte.Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000046/2020-2021 | 1139/NMD-II | 15/10/2020 | 15/11/2020 | B.B CONCERNED | 3.12 | 0.05 | 1.63 | 0
2 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | Ground Water Based Water Supply Scheme for Banchukamari & Adj. Mouzas | SM/03708 | New | Supply, delivery & installation of automatically controlled Hydraulic diaphragm type chlorinator dosing pump at pump house no. II , of Banchukumari water supply scheme under Northern Mechanical Division-II ,P.H.E DTE. |  |  | ORD/000608/2020-2021 | 819/AMSD | 15/01/2021 | 25/01/2021 | ALPHA ENTERPRISE | 0.82 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | Ground Water Based Water Supply Scheme for Banchukamari & Adj. Mouzas | SM/03708 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under BANCHUKAMARI W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000328/2021-2022 | 695/NMD-II | 08/07/2021 | 08/07/2022 | M/S SAJAHAN CHOWDHURY | 2.97 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | Ground Water Based Water Supply Scheme for Banchukamari & Adj. Mouzas | SM/03708 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under BANCHUKAMARI W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000342/2021-2022 | 709/NMD-II | 08/07/2021 | 08/07/2022 | THE BANERJEE CONCERN | 2.97 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | Ground Water Based Water Supply Scheme for Banchukamari & Adj. Mouzas | SM/03708 | New | Supply and Delivery of Calcium Hypochlorite[Ca(Ocl)2] granules at Different PWSS under Alipurduar-I & II Block in the Dist of Alipurduar under Northern Mechanical Division-II,PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000395/2021-2022 | 863/NMD-II | 28/07/2021 | 27/08/2021 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 3.58 | 0 | 0 | 0
Total | [13 empty] | 13.45 | 0.05 | 0.38