## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Water Supply Scheme for Purba Chenpani & adj. mouzas | SM/03828 | New | Supply and Delivery of Calcium Hypochlorite[Ca(Ocl)2] granules at Different PWSS under Alipurduar-I & II Block in the Dist of Alipurduar under Northern Mechanical Division-II,PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000395/2021-2022 | 863/NMD-II | 28/07/2021 | 27/08/2021 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 3.58 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Water Supply Scheme for Purba Chenpani & adj. mouzas | SM/03828 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at Shamultala,Loknathpur etc under Alipurduar-I& II Block in the dist. of Alipurduar¿ |  |  | ORD/000703/2021-2022 | 1314/NMD-II | 03/12/2021 | 18/12/2021 | M/S KUNDU CONSTRUCTION | 2.29 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Water Supply Scheme for Purba Chenpani & adj. mouzas | SM/03828 | New | Operation and Guarding of Pumping machinery at Pump House No. I under PURBA CHENPANI W/S Scheme. In the dist. Of ALIPURDUAR. |  |  | ORD/000495/2021-2022 | 757/NMD-II | 08/07/2021 | 08/07/2022 | RMD TRADING | 2.97 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Water Supply Scheme for Purba Chenpani & adj. mouzas | SM/03828 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under PURBA CHENPANI W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000324/2021-2022 | 691/NMD-II | 07/07/2021 | 07/07/2022 | BONANZA ENTERPRISE | 2.97 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Water Supply Scheme for Purba Chenpani & adj. mouzas | SM/03828 | New | Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at Samuktala,Dholajhora T.G, Purba Chepani etc under Alipurduar block in the dist. of Alipurduar under NMD-II P.H E Dte |  |  | ORD/000615/2021-2022 | 1111/NMD-II | 20/09/2021 | 20/10/2021 | COMBINE ENTERPRISES | 3.01 | 0 | 0 | 0
6 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Water Supply Scheme for Purba Chenpani & adj. mouzas | SM/03828 | New | Birpara, Ramjhora P/H no. II, Consumer No. 423046758,Consumer No. 4002711461 |  |  | VCH/002624/2021-2022 | 48/21-22 | 13/07/2021 | 13/07/2021 | EXECUTIVE ENGINEER NORTHERN MECHANICAL DIVISION-II | 0.1 | 0 | 0 | 0
7 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Water Supply Scheme for Purba Chenpani & adj. mouzas | SM/03828 | New | Quotation for new service connection WBSEDCL at PURBA CHENPANI T/W no. III, PHE Dte. |  |  | VCH/001010/2021-2022 | 92/21-22 | 20/09/2021 | 20/09/2021 | WBSEDCL | 0.8 | 0 | 0 | 0
Total | [13 empty] | 15.71 | 0 | 0