## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | Water Supply Scheme for Tapashikhata & adj. mouzas | SM/03829 | New | Supply, delivery and installation of 25 KVA servo motor operated Copper wound line voltage corrector at BAROVISA W/S Scheme,T/W NO- II under NMD-II, P.H.E. Dte.Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000046/2020-2021 | 1139/NMD-II | 15/10/2020 | 15/11/2020 | B.B CONCERNED | 3.12 | 0.08 | 2.62 | 0
2 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | Water Supply Scheme for Tapashikhata & adj. mouzas | SM/03829 | New | Renovation of Yard lighting Arrangement and Electrification of the pump house I under Tapashikhata W/S Scheme under AMSD P.H E Dte |  |  | ORD/000688/2021-2022 | .400/AMSD | 30/09/2021 | 15/10/2021 | B.B CONCERNED | 0.45 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | Water Supply Scheme for Tapashikhata & adj. mouzas | SM/03829 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under TAPSHIKHATA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000368/2021-2022 | 731/NMD-II | 08/07/2021 | 08/07/2022 | UTTAM PAUL | 2.97 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | Water Supply Scheme for Tapashikhata & adj. mouzas | SM/03829 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under TAPSHIKHATA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000340/2021-2022 | 707/NMD-II | 08/07/2021 | 08/07/2022 | B.B CONCERNED | 2.97 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | Water Supply Scheme for Tapashikhata & adj. mouzas | SM/03829 | New | Supply, delivery and installation of standby automatically controlled hydrualic diaphragm type Chlorinator for accurate dosing of Chlorine solution at differernt PWSS under Alipurduar-I Block in the district of Alipurduar under NMD-II ,P.H.E Dte. |  |  | ORD/000597/2021-2022 | 1042/NMD-II | 03/09/2021 | 23/09/2021 | MUSTAFI CONCERN | 3.5 | 0 | 0 | 0
6 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | Water Supply Scheme for Tapashikhata & adj. mouzas | SM/03829 | New | Supply and Delivery of Calcium Hypochlorite[Ca(Ocl)2] granules at Different PWSS under Alipurduar-I & II Block in the Dist of Alipurduar under Northern Mechanical Division-II,PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000395/2021-2022 | 863/NMD-II | 28/07/2021 | 27/08/2021 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 3.58 | 0 | 0 | 0
7 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | Water Supply Scheme for Tapashikhata & adj. mouzas | SM/03829 | New | Providing extension of distribution line, AT TAPSHIKATHA G.P from the commissioned TAPSHIKATHA PWSS (UID-APD-022) UNDER ALIPURDUAR DIVISION PHE DTE. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000308/2020-2021 | 1481/ALD | 27/01/2021 | 28/03/2021 | KAMALESH ROY | 12.16 | 0 | 0 | 76
Total | [13 empty] | 28.74 | 0.08 | 0.28