## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Ground Water Based Water Supply Scheme for Paschim Khair Bari & adjoining mouzas | SM/03908 | New | Supply,delivery of Electro Mechanical components at Paschim Khayerbari Water Supply Scheme IN THE Dist OF Alipurduar under NMD-II,PHE.Dte. |  |  | ORD/000566/2020-2021 | 1418/NMD-II | 27/01/2021 | 26/02/2021 | S.D CONCERN WORKSHOP | 10.38 | 18.78 | 180.92 | 0
2 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Ground Water Based Water Supply Scheme for Paschim Khair Bari & adjoining mouzas | SM/03908 | New | Supply, delivery of Electro Mechanical components at Paschim Khayerbari Water Supply Scheme,T/W NO-II IN THE Dist OF Alipurduar under NMD-II,PHE.Dte. |  |  | ORD/000588/2020-2021 | 1514/NMD-II | 12/02/2021 | 14/03/2021 | GEETA CONSTRUCTION | 6.44 | 12.87 | 199.91 | 0
3 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Ground Water Based Water Supply Scheme for Paschim Khair Bari & adjoining mouzas | SM/03908 | New | Withdrawing & installation of 10 HP Submersible pump machinery and repairing the same under PASCHIM KAIR BARI, WATER SUPPLY SCHEME,P/H No-III under Northern Mechanical Division-II Phe. Dte. In the dist. Of Alipurduar. |  |  | ORD/000791/2020-2021 | 804/AMSD | 11/01/2021 | 21/01/2021 | PRAGATI CONSTRUCTION COMPANY | 0.33 | 0 | 0 | 0
4 | ALIPURDUAR | Madarihat | Alipurduar Division | Ground Water Based Water Supply Scheme for Paschim Khair Bari & adjoining mouzas | SM/03908 | New | SUPPLY OF DIFFERENT STATIONARY MATERIALS AT OFFICE OF THE EXECUTIVE ENGINEER, ALIPURDUAR DIVISION, PHED |  |  | VCH/000779/2021-2022 | 259/21-22 | 07/10/2021 | 07/10/2021 | JAYGURU ENTERPRISE | 0.54 | 0 | 0 | 0
5 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Ground Water Based Water Supply Scheme for Paschim Khair Bari & adjoining mouzas | SM/03908 | New | Operation and Guarding of Pumping machinery at Pump House No. III under PASCHIM KHAIR BARI W/S Scheme. In the dist. Of ALIPURDUAR |  |  | ORD/000509/2021-2022 | 763/NMD-II | 08/07/2021 | 08/07/2022 | HARA PROSAD DAS | 2.97 | 0 | 0 | 0
6 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Ground Water Based Water Supply Scheme for Paschim Khair Bari & adjoining mouzas | SM/03908 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under PASCHIM KHAIR BARI W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000530/2021-2022 | 765/NMD-II | 08/07/2021 | 08/07/2022 | RIPON DAS | 2.97 | 0 | 0 | 0
7 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Ground Water Based Water Supply Scheme for Paschim Khair Bari & adjoining mouzas | SM/03908 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under PASCHIM KHAIR BARI W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000667/2021-2022 | 775/NMD-II | 08/07/2021 | 08/07/2022 | RAJEEV RANJAN OJHA | 2.97 | 0 | 0 | 0
8 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Ground Water Based Water Supply Scheme for Paschim Khair Bari & adjoining mouzas | SM/03908 | New | Supply, delivery of Electro mechanical components at Paschim khairbari Water Supply Scheme and adjoining mouzas in the dist of ALIPURDUAR under NMD-II PHE Dte. Alipurduar. |  |  | ORD/000874/2021-2022 | 349/NMD-II | 15/03/2022 | 14/04/2022 | CINZANO | 11.89 | 11.89 | 100 | 0
9 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Ground Water Based Water Supply Scheme for Paschim Khair Bari & adjoining mouzas | SM/03908 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at different PWSS under Birpara - Madarihat block in the dist. of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000521/2021-2022 | 1069/NMD-II | 10/09/2021 | 30/09/2021 | CHOWDHURY AND BASU ENTERPRISE | 4.72 | 0 | 0 | 0
10 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Ground Water Based Water Supply Scheme for Paschim Khair Bari & adjoining mouzas | SM/03908 | New | Supply & delivery of standby automatically controlled hydrualic diaphragm type Chlorinator for accurate dosing of Chlorine solution at Dekhlapara T.G P/H No.-I , Birpara p/H No.I, Paschim Khairbari P/H No.II ,Gargenda P/h No.II, Dhumchipara P/HNo.I in the district of Alipurduar under NMD-II ,P.H.E Dte. |  |  | ORD/000522/2021-2022 | 1070/NMD-II | 10/09/2021 | 30/09/2021 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 3.76 | 0 | 0 | 0
Total | [13 empty] | 46.97 | 43.54 | 92.71