## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Ground water based water supply scheme for Bakla and adjoining mouzas | SM/04006 | New | Supply and Delivery of Calcium Hypochlorite[Ca(Ocl)2] granules at Different PWSS under Alipurduar-I & II Block in the Dist of Alipurduar under Northern Mechanical Division-II,PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000395/2021-2022 | 863/NMD-II | 28/07/2021 | 27/08/2021 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 3.58 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Ground water based water supply scheme for Bakla and adjoining mouzas | SM/04006 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at Shamultala,Loknathpur etc under Alipurduar-I& II Block in the dist. of Alipurduar¿ |  |  | ORD/000703/2021-2022 | 1314/NMD-II | 03/12/2021 | 18/12/2021 | M/S KUNDU CONSTRUCTION | 2.29 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Ground water based water supply scheme for Bakla and adjoining mouzas | SM/04006 | New | Supply, delivery and installation of standby automatically controlled hydrualic diaphragm type Chlorinator for accurate dosing of Chlorine solution at differernt PWSS under Alipurduar-I Block in the district of Alipurduar under NMD-II ,P.H.E Dte. |  |  | ORD/000597/2021-2022 | 1042/NMD-II | 03/09/2021 | 23/09/2021 | MUSTAFI CONCERN | 3.5 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Ground water based water supply scheme for Bakla and adjoining mouzas | SM/04006 | New | Withdrawing & installation of 7.5 HP Submersible pump machinery and repairing the same under Bakla P/H No.I WATER SUPPLY SCHEME,under A.M.S.D PHE. Dte. In the dist. Of Alipurduar. |  |  | ORD/000840/2021-2022 | 335/AMSD | 31/08/2021 | 10/09/2021 | THE BANERJEE CONCERN | 0.26 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Ground water based water supply scheme for Bakla and adjoining mouzas | SM/04006 | New | Supply, delivery and installation of standby automatically controlled hydrualic diaphragm type Chlorinator for accurate dosing of Chlorine solution at P/H No.I&II under Satkura and Salmara P/H No.I PWSS in the district of Coochbehar under NMD-II ,P.H.E Dte. |  |  | ORD/000569/2021-2022 | 1014/NMD-II | 27/08/2021 | 16/09/2021 | SUNLIT | 2.6 | 0 | 0 | 0
6 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Ground water based water supply scheme for Bakla and adjoining mouzas | SM/04006 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under BAKLA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000398/2021-2022 | 742/NMD-II | 08/07/2021 | 08/07/2022 | TALUKDAR ENTERPRISE | 2.97 | 0 | 0 | 0
7 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Ground water based water supply scheme for Bakla and adjoining mouzas | SM/04006 | New | Operation and Guarding of Pumping machinery at Pump House No. I under BAKLA W/S Scheme. In the dist. Of ALIPURDUAR |  |  | ORD/000496/2021-2022 | 758/NMD-II | 08/07/2021 | 08/07/2022 | SUNLIT | 2.97 | 0 | 0 | 0
8 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Ground water based water supply scheme for Bakla and adjoining mouzas | SM/04006 | New | Supply, delivery of Electro Mechanical components at BAKLA Water Supply Scheme IN THE Dist OF Alipurduar under NMD-II,PHE.Dte. |  |  | ORD/000585/2020-2021 | 1507/NMD-II | 11/02/2021 | 13/03/2021 | TALUKDAR ENTERPRISE | 7.25 | 14.51 | 200 | 0
9 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Ground water based water supply scheme for Bakla and adjoining mouzas | SM/04006 | New | Quotation for new service connection at Bakla W/s scheme T/W no. III, Application no. 4003022080 |  |  | VCH/001534/2022-2023 | BP-102/22-23 | 19/12/2022 | 19/12/2022 | WBSEDCL | 1.37 | 0 | 0 | 0
Total | [13 empty] | 26.78 | 14.51 | 54.18