## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata | Alipurduar Division | Ground water based water supply scheme for Jogendrapur and adjoining mouzas | SM/04039 | New | Providing Functional Household Tap connection (FHTC) in connection with Jaldhara Jal Sapno for Jogendrapur PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000301/2020-2021 | 1381/ALD | 19/01/2021 | 05/03/2021 | ASSOCIATE CONSTRUCTION COMPANY | 15.78 | 0 | 0 | 67
2 | ALIPURDUAR | Falakata | Northern Mechanical Division II | Ground water based water supply scheme for Jogendrapur and adjoining mouzas | SM/04039 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under JOGENDRAPUR W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000337/2021-2022 | 704/NMD-II | 08/07/2021 | 08/07/2022 | SANJIB SAHA | 2.97 | 0 | 0 | 0
3 | ALIPURDUAR | Falakata | Northern Mechanical Division II | Ground water based water supply scheme for Jogendrapur and adjoining mouzas | SM/04039 | New | -"Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at Bhutnirghat ,Choto salkumar, Dalimpur etc under Falakata block in the dist. of Alipurduar under NMD-II P.H E Dte¿ |  |  | ORD/000614/2021-2022 | 1114/NMD-II | 20/09/2021 | 20/10/2021 | M/S PARITOSH BHOWMICK & CO. | 2.15 | 0 | 0 | 0
4 | ALIPURDUAR | Falakata | Northern Mechanical Division II | Ground water based water supply scheme for Jogendrapur and adjoining mouzas | SM/04039 | New | Supply, delivery and installation of standby automatically controlled hydraulic diaphragm type Chlorinator for accurate dosing of Chlorine solution at P/H No.II of Chhoto Salkumar , Jogijhora Barabak, BhutnirghatW/S Scheme and P/H No.I of Jogendrapur W/S Scheme of Falakata Block etc in the district of Alipurduar under NMD-II P.H.E Dte. |  |  | ORD/000595/2021-2022 | 1041/NMD-II | 03/09/2021 | 23/09/2021 | SARKAR ELECTRIC | 3.39 | 0 | 0 | 0
Total | [13 empty] | 24.28 | 0 | 0