## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata | Alipurduar Division | Ground water based water supply scheme for Jogendrapur and adjoining mouzas | SM/04039 | New | Providing Functional Household Tap connection (FHTC) in connection with Jaldhara Jal Sapno for Jogendrapur PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000301/2020-2021 | 1381/ALD | 19/01/2021 | 05/03/2021 | ASSOCIATE CONSTRUCTION COMPANY | 15.78 | 0 | 0 | 67
2 | ALIPURDUAR | Falakata | Northern Mechanical Division II | Ground water based water supply scheme for Jogendrapur and adjoining mouzas | SM/04039 | New | -"Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at Bhutnirghat ,Choto salkumar, Dalimpur etc under Falakata block in the dist. of Alipurduar under NMD-II P.H E Dte¿ |  |  | ORD/000614/2021-2022 | 1114/NMD-II | 20/09/2021 | 20/10/2021 | M/S PARITOSH BHOWMICK & CO. | 2.15 | 0 | 0 | 0
3 | ALIPURDUAR | Falakata | Northern Mechanical Division II | Ground water based water supply scheme for Jogendrapur and adjoining mouzas | SM/04039 | New | Supply, delivery and installation of standby automatically controlled hydraulic diaphragm type Chlorinator for accurate dosing of Chlorine solution at P/H No.II of Chhoto Salkumar , Jogijhora Barabak, BhutnirghatW/S Scheme and P/H No.I of Jogendrapur W/S Scheme of Falakata Block etc in the district of Alipurduar under NMD-II P.H.E Dte. |  |  | ORD/000595/2021-2022 | 1041/NMD-II | 03/09/2021 | 23/09/2021 | SARKAR ELECTRIC | 3.39 | 0 | 0 | 0
4 | ALIPURDUAR | Falakata | Northern Mechanical Division II | Ground water based water supply scheme for Jogendrapur and adjoining mouzas | SM/04039 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under JOGENDRAPUR W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000337/2021-2022 | 704/NMD-II | 08/07/2021 | 08/07/2022 | SANJIB SAHA | 2.97 | 0 | 0 | 0
5 | ALIPURDUAR | Falakata | Northern Mechanical | Ground water based water supply scheme for Jogendrapur and adjoining mouzas | SM/04039 | New | Consolidated Supply and Yard lighting arrangement Bills |  |  | VCH/001048/2018-2019 | 1223/W/18-19 | 17/03/2019 |  | DIAMOND ELECTRICAL WORKS | 3.3 | 0 | 0 | 0
6 | ALIPURDUAR | Falakata | Northern Mechanical | Ground water based water supply scheme for Jogendrapur and adjoining mouzas | SM/04039 | New | Consolidated Supply, delivery and installation Bills |  |  | VCH/001288/2018-2019 | 1306/W/18-19 | 25/03/2019 |  | SUMON ELECTRICAL | 4.05 | 0 | 0 | 0
7 | ALIPURDUAR | Falakata | Jalpaiguri Division | Ground water based water supply scheme for Jogendrapur and adjoining mouzas | SM/04039 | New | SWSM -- Ground water based water supply scheme for Jogendrapur and adjoining mouzas(SM/04039) |  |  | VCH/001028/2018-2019 | 1023 | 01/02/2019 |  | EXECUTIVE ENGINEER ALIPURDUAR DIVISION P.H.E. DTE | 4.15 | 0 | 0 | 0
8 | ALIPURDUAR | Falakata | Northern Mechanical | Ground water based water supply scheme for Jogendrapur and adjoining mouzas | SM/04039 | New | Certified that, the marked schemes vide Sl. No. 1-4, 9-11, 14, 16, 22, 29-31, 33, 36, 38, 44, 45, 50, 53, 55, 56, 65, 71, 73, 80-86, 89-92, 94, 103, 107, 108, 110-112, 134, 135, 141-143, 152, 154, 156, 158, 159, 161-163, 167, 168, 174-187, 202-210, 214, 222-229, 243, 266, 267, 277, 278, 287, 294, 300, 305, 317-320, 331, 332, 335-337, 340-342, 348, 349, 352, 353 comes under the jurisdiction of Northern Mechanical Division-II, PHE Dte. and which accured to Rs 55,50,591.00/- (Rupees fifty five lakh fifty thousand five hundred ninety one only) out of total balance amount Rs 6,13,62,046.94/- (Rupees six crore thirteen lakh sixty two thousand forty six and ninety four paise only) to be transferred at the Deposit Account of Northern Mechanical Division-II, PHE Dte. (Operator ID - 71 under Alipurduar Treasury) from the Deposit Account of Northern Mechanical Division, PHE Dte. (Operator ID - 69 under Siliguri Treasury-I) through inter treasury transfer module of IFMS. |  |  | VCH/000387/2019-2020 | 94/W/19-20 | 12/06/2019 |  | NORTHERN MECHANICAL DIVISION II, P.H.E. DTE. | 55.51 | 0 | 0 | 0
Total | [13 empty] | 91.29 | 0 | 0