## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Water Supply Scheme for Chandijhar & adj. mouzas. | SM/04129 | New | Withdrawing & installation of 7.5 HP Submersible pump machinery and repairing the same under CHANDIJHAR WATER SUPPLY SCHEME, P/H No-I under AMSD in the dist. Of Alipurduar. |  |  | ORD/000761/2020-2021 | 584/AMSD | 08/10/2020 | 18/10/2020 | M/S SAJAHAN CHOWDHURY | 0.27 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Water Supply Scheme for Chandijhar & adj. mouzas. | SM/04129 | New | Supply and Delivery of Calcium Hypochlorite[Ca(Ocl)2] granules at Different PWSS under Alipurduar-I & II Block in the Dist of Alipurduar under Northern Mechanical Division-II,PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000395/2021-2022 | 863/NMD-II | 28/07/2021 | 27/08/2021 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 3.58 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Water Supply Scheme for Chandijhar & adj. mouzas. | SM/04129 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under CHANDIJHAR W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000322/2021-2022 | 689/NMD-II | 07/07/2021 | 07/07/2022 | BONANZA ENTERPRISE | 2.97 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Water Supply Scheme for Chandijhar & adj. mouzas. | SM/04129 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under CHANDIJHAR W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000402/2021-2022 | 746/NMD-II | 08/07/2021 | 08/07/2022 | M/S SAJAHAN CHOWDHURY | 2.97 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | Water Supply Scheme for Chandijhar & adj. mouzas. | SM/04129 | New | Laying of DI/MS/HDPE pipe line and providing Functional Household Tap connection (FHTC) in connection with Jaldhara/Jal Sapna for the Birpara Boro Houda WSS under Alipurduar Division, PHE Dte.(Phase-II) |  |  | VCH/000944/2020-2021 | 571/20-21 | 26/03/2021 | 26/03/2021 | PRAMESH LAMA | 10 | 0 | 0 | 0
6 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | Water Supply Scheme for Chandijhar & adj. mouzas. | SM/04129 | New | PROFESSIONAL BILL FOR GST & TDS RETURN |  |  | VCH/000780/2021-2022 | 261/21-22 | 07/10/2021 | 07/10/2021 | E TAX SERVICE | 0.53 | 0 | 0 | 0
Total | [13 empty] | 20.31 | 0 | 0