## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme for Jashodanga mouza. | SM/04157 | New | Continuation for Operation & guarding of the pumping machinery at Pump House No. I under JASHODANGA W/S Scheme, in the dist. Of Alipurduar P.H.E.,Dte. |  |  | ORD/000028/2021-2022 | 71/AMSD | 28/04/2021 | 28/07/2021 | ANUP BASU | 0.72 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | Ground Water Based Piped Water Supply Scheme for Jashodanga mouza. | SM/04157 | New | PROFESSIONAL BILL FOR GST & TDS RETURN |  |  | VCH/000780/2021-2022 | 261/21-22 | 07/10/2021 | 07/10/2021 | E TAX SERVICE | 0.53 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme for Jashodanga mouza. | SM/04157 | New | Operation and Guarding of Pumping machinery at Pump House No. I, Under JASHODANGA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000639/2021-2022 | 769/NMD-II | 08/07/2021 | 08/07/2022 | ANUP BASU | 2.97 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme for Jashodanga mouza. | SM/04157 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under JASHODANGA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000380/2021-2022 | 740/NMD-II | 08/07/2021 | 08/07/2022 | PRAGATI CONSTRUCTION COMPANY | 2.97 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme for Jashodanga mouza. | SM/04157 | New | 'Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granuels at different PWSS under Mekhliganj block under CMSD, PHE Dte. in the dist. Cooch Behar. |  |  | VCH/002593/2021-2022 | 222/21-22 | 24/02/2022 | 24/02/2022 | B.B CONCERNED | 0.94 | 0 | 0 | 0
6 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme for Jashodanga mouza. | SM/04157 | New | Supply, delivery of Standby Submersible pumping Machinery forJasodanga W/S/S,TW-I under NMD-II,PHE Dte, Dist-Alipurduar. |  |  | ORD/000830/2020-2021 | .815/AMSD | 14/01/2021 | 24/01/2021 | THE BANERJEE CONCERN | 0.51 | 0 | 0 | 0
7 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme for Jashodanga mouza. | SM/04157 | New | Supply and Delivery of Calcium Hypochlorite[Ca(Ocl)2] granules at Different PWSS under Alipurduar-I & II Block in the Dist of Alipurduar under Northern Mechanical Division-II,PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000395/2021-2022 | 863/NMD-II | 28/07/2021 | 27/08/2021 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 3.58 | 0 | 0 | 0
Total | [13 empty] | 12.21 | 0 | 0