## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme for Jashodanga mouza. | SM/04157 | New | Supply, delivery of Standby Submersible pumping Machinery forJasodanga W/S/S,TW-I under NMD-II,PHE Dte, Dist-Alipurduar. |  |  | ORD/000830/2020-2021 | .815/AMSD | 14/01/2021 | 24/01/2021 | THE BANERJEE CONCERN | 0.51 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme for Jashodanga mouza. | SM/04157 | New | Continuation for Operation & guarding of the pumping machinery at Pump House No. I under JASHODANGA W/S Scheme, in the dist. Of Alipurduar P.H.E.,Dte. |  |  | ORD/000028/2021-2022 | 71/AMSD | 28/04/2021 | 27/07/2021 | ANUP BASU | 0.72 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme for Jashodanga mouza. | SM/04157 | New | Operation and Guarding of Pumping machinery at Pump House No. I, Under JASHODANGA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000639/2021-2022 | 769/NMD-II | 08/07/2021 | 08/07/2022 | ANUP BASU | 2.97 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme for Jashodanga mouza. | SM/04157 | New | Supply and Delivery of Calcium Hypochlorite[Ca(Ocl)2] granules at Different PWSS under Alipurduar-I & II Block in the Dist of Alipurduar under Northern Mechanical Division-II,PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000395/2021-2022 | 863/NMD-II | 28/07/2021 | 27/08/2021 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 3.58 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme for Jashodanga mouza. | SM/04157 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under JASHODANGA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000380/2021-2022 | 740/NMD-II | 08/07/2021 | 08/07/2022 | PRAGATI CONSTRUCTION COMPANY | 2.97 | 0 | 0 | 0
6 | ALIPURDUAR | Alipurduar - II | Jalpaiguri Division | Ground Water Based Piped Water Supply Scheme for Jashodanga mouza. | SM/04157 | New | SWSM -- Ground Water Based Piped Water Supply Scheme for Jashodanga mouza.(SM/04157) |  |  | VCH/001030/2018-2019 | 1023 | 01/02/2019 |  | EXECUTIVE ENGINEER ALIPURDUAR DIVISION P.H.E. DTE | 1 | 0 | 0 | 0
7 | ALIPURDUAR | Alipurduar - II | Northern Mechanical | Ground Water Based Piped Water Supply Scheme for Jashodanga mouza. | SM/04157 | New | Certified that, the marked schemes vide Sl. No. 1-4, 9-11, 14, 16, 22, 29-31, 33, 36, 38, 44, 45, 50, 53, 55, 56, 65, 71, 73, 80-86, 89-92, 94, 103, 107, 108, 110-112, 134, 135, 141-143, 152, 154, 156, 158, 159, 161-163, 167, 168, 174-187, 202-210, 214, 222-229, 243, 266, 267, 277, 278, 287, 294, 300, 305, 317-320, 331, 332, 335-337, 340-342, 348, 349, 352, 353 comes under the jurisdiction of Northern Mechanical Division-II, PHE Dte. and which accured to Rs 55,50,591.00/- (Rupees fifty five lakh fifty thousand five hundred ninety one only) out of total balance amount Rs 6,13,62,046.94/- (Rupees six crore thirteen lakh sixty two thousand forty six and ninety four paise only) to be transferred at the Deposit Account of Northern Mechanical Division-II, PHE Dte. (Operator ID - 71 under Alipurduar Treasury) from the Deposit Account of Northern Mechanical Division, PHE Dte. (Operator ID - 69 under Siliguri Treasury-I) through inter treasury transfer module of IFMS. |  |  | VCH/000387/2019-2020 | 94/W/19-20 | 12/06/2019 |  | NORTHERN MECHANICAL DIVISION II, P.H.E. DTE. | 55.51 | 0 | 0 | 0
8 | ALIPURDUAR | Alipurduar - II | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme for Jashodanga mouza. | SM/04157 | New | 'Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granuels at different PWSS under Mekhliganj block under CMSD, PHE Dte. in the dist. Cooch Behar. |  |  | VCH/002593/2021-2022 | 222/21-22 | 24/02/2022 |  | B.B CONCERNED | 0.94 | 0 | 0 | 0
9 | ALIPURDUAR | Alipurduar - II | Alipurduar Division | Ground Water Based Piped Water Supply Scheme for Jashodanga mouza. | SM/04157 | New | PROFESSIONAL BILL FOR GST & TDS RETURN |  |  | VCH/000780/2021-2022 | 261/21-22 | 07/10/2021 |  | E TAX SERVICE | 0.53 | 0 | 0 | 0
Total | [13 empty] | 68.71 | 0 | 0