## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme for Munshipara & adj. mouza. | SM/04216 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under MUNSHIPARA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000400/2021-2022 | 744/NMD-II | 08/07/2021 | 08/07/2022 | M/S SAJAHAN CHOWDHURY | 2.97 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | Ground Water Based Piped Water Supply Scheme for Munshipara & adj. mouza. | SM/04216 | New | Construction of approach road & car parking area with paver block & chequered tiles at Jainty WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division | Alipurduar Sub Division,RWS Alipurduar - I Block | ORD/000331/2021-2022 | 2107/ALD | 05/01/2022 | 04/02/2022 | DAS ENTERPRISE | 5.02 | 0 | 0 | 77
3 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme for Munshipara & adj. mouza. | SM/04216 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at Shamultala,Loknathpur etc under Alipurduar-I& II Block in the dist. of Alipurduar¿ |  |  | ORD/000703/2021-2022 | 1314/NMD-II | 03/12/2021 | 18/12/2021 | M/S KUNDU CONSTRUCTION | 2.29 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme for Munshipara & adj. mouza. | SM/04216 | New | Supply and Delivery of Calcium Hypochlorite[Ca(Ocl)2] granules at Different PWSS under Alipurduar-I & II Block in the Dist of Alipurduar under Northern Mechanical Division-II,PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000395/2021-2022 | 863/NMD-II | 28/07/2021 | 27/08/2021 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 3.58 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme for Munshipara & adj. mouza. | SM/04216 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under MUNSHIPARA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000355/2021-2022 | 722/NMD-II | 08/07/2021 | 08/07/2022 | B.B CONCERNED | 2.97 | 0 | 0 | 0
6 | ALIPURDUAR | Alipurduar - I | Northern Mechanical | Ground Water Based Piped Water Supply Scheme for Munshipara & adj. mouza. | SM/04216 | New | Bill for Advertisement |  |  | VCH/001259/2018-2019 | 1305/W/18-19 | 25/03/2019 |  | UTTARBANGA SAMBAD | 0.72 | 0 | 0 | 0
7 | ALIPURDUAR | Alipurduar - I | Jalpaiguri Division | Ground Water Based Piped Water Supply Scheme for Munshipara & adj. mouza. | SM/04216 | New | SWSM -- Ground Water Based Piped Water Supply Scheme for Munshipara & adj. mouza.(SM/04216) |  |  | VCH/001033/2018-2019 | 1023 | 01/02/2019 |  | EXECUTIVE ENGINEER ALIPURDUAR DIVISION P.H.E. DTE | 6.12 | 0 | 0 | 0
8 | ALIPURDUAR | Alipurduar - I | Northern Mechanical | Ground Water Based Piped Water Supply Scheme for Munshipara & adj. mouza. | SM/04216 | New | Certified that, the marked schemes vide Sl. No. 1-4, 9-11, 14, 16, 22, 29-31, 33, 36, 38, 44, 45, 50, 53, 55, 56, 65, 71, 73, 80-86, 89-92, 94, 103, 107, 108, 110-112, 134, 135, 141-143, 152, 154, 156, 158, 159, 161-163, 167, 168, 174-187, 202-210, 214, 222-229, 243, 266, 267, 277, 278, 287, 294, 300, 305, 317-320, 331, 332, 335-337, 340-342, 348, 349, 352, 353 comes under the jurisdiction of Northern Mechanical Division-II, PHE Dte. and which accured to Rs 55,50,591.00/- (Rupees fifty five lakh fifty thousand five hundred ninety one only) out of total balance amount Rs 6,13,62,046.94/- (Rupees six crore thirteen lakh sixty two thousand forty six and ninety four paise only) to be transferred at the Deposit Account of Northern Mechanical Division-II, PHE Dte. (Operator ID - 71 under Alipurduar Treasury) from the Deposit Account of Northern Mechanical Division, PHE Dte. (Operator ID - 69 under Siliguri Treasury-I) through inter treasury transfer module of IFMS. |  |  | VCH/000387/2019-2020 | 94/W/19-20 | 12/06/2019 |  | NORTHERN MECHANICAL DIVISION II, P.H.E. DTE. | 55.51 | 0 | 0 | 0
Total | [13 empty] | 79.17 | 0 | 0