## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme for Loknathpur & adj. mouzas. | SM/04487 | New | Electric QWuotation bill for the new service connection at TW No. III under LOKNATHPUR PWSS in the dist. of Alipurduar. |  |  | VCH/001892/2020-2021 |  | 18/03/2021 | 18/03/2021 | WBSEDCL | 1.35 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme for Loknathpur & adj. mouzas. | SM/04487 | New | Electric Quotation for new service connection at TW NO. IV under Loknathpur PWSS in the dist. of ALipurduar. |  |  | VCH/001893/2020-2021 |  | 18/03/2021 | 18/03/2021 | WBSEDCL | 1.35 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme for Loknathpur & adj. mouzas. | SM/04487 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under LOKNATHPUR W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000332/2021-2022 | 699/NMD-II | 08/07/2021 | 08/07/2022 | SAIKAT SINHA | 2.97 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme for Loknathpur & adj. mouzas. | SM/04487 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under LOKNATHPUR W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000347/2021-2022 | 714/NMD-II | 08/07/2021 | 08/07/2022 | SAIKAT SINHA | 2.97 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | Ground Water Based Piped Water Supply Scheme for Loknathpur & adj. mouzas. | SM/04487 | New | Retrofitting of pipeline etc. for the 'Jal Sapna' programme (FHTC for every house hold) under Loknathpur PWSS under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division | RWS Alipurduar - II Block | ORD/000368/2021-2022 | 2296/ALD | 24/01/2022 | 25/03/2022 | GOUTAM KUMAR DAS | 45.8 | 0 | 0 | 94
6 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme for Loknathpur & adj. mouzas. | SM/04487 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at Shamultala,Loknathpur etc under Alipurduar-I& II Block in the dist. of Alipurduar¿ |  |  | ORD/000703/2021-2022 | 1314/NMD-II | 03/12/2021 | 18/12/2021 | M/S KUNDU CONSTRUCTION | 2.29 | 0 | 0 | 0
7 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Ground Water Based Piped Water Supply Scheme for Loknathpur & adj. mouzas. | SM/04487 | New | Supply and Delivery of Calcium Hypochlorite[Ca(Ocl)2] granules at Different PWSS under Alipurduar-I & II Block in the Dist of Alipurduar under Northern Mechanical Division-II,PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000395/2021-2022 | 863/NMD-II | 28/07/2021 | 27/08/2021 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 3.58 | 0 | 0 | 0
8 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | Ground Water Based Piped Water Supply Scheme for Loknathpur & adj. mouzas. | SM/04487 | New | Construction of roof truss, field development and other allied works at Headwork site of Old Jaigaon WSS under Alipurduar Division, PHE Dte. | Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Kalchini Block | ORD/000393/2021-2022 | 2307/ALD | 25/01/2022 | 24/02/2022 | DILIP MAHATO | 4.17 | 0 | 0 | 75
Total | [13 empty] | 64.48 | 0 | 0