## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Jalpaiguri Division | Water Supply Scheme for Mujnai Tea Garden Mouza. | SM/04770 | New | MUJNAI T.G |  |  | VCH/001038/2018-2019 | 1023 | 01/02/2019 |  | EXECUTIVE ENGINEER ALIPURDUAR DIVISION P.H.E. DTE | 0.02 | 0 | 0 | 0
2 | ALIPURDUAR | Madarihat | Northern Mechanical | Water Supply Scheme for Mujnai Tea Garden Mouza. | SM/04770 | New | Certified that, the marked schemes vide Sl. No. 1-4, 9-11, 14, 16, 22, 29-31, 33, 36, 38, 44, 45, 50, 53, 55, 56, 65, 71, 73, 80-86, 89-92, 94, 103, 107, 108, 110-112, 134, 135, 141-143, 152, 154, 156, 158, 159, 161-163, 167, 168, 174-187, 202-210, 214, 222-229, 243, 266, 267, 277, 278, 287, 294, 300, 305, 317-320, 331, 332, 335-337, 340-342, 348, 349, 352, 353 comes under the jurisdiction of Northern Mechanical Division-II, PHE Dte. and which accured to Rs 55,50,591.00/- (Rupees fifty five lakh fifty thousand five hundred ninety one only) out of total balance amount Rs 6,13,62,046.94/- (Rupees six crore thirteen lakh sixty two thousand forty six and ninety four paise only) to be transferred at the Deposit Account of Northern Mechanical Division-II, PHE Dte. (Operator ID - 71 under Alipurduar Treasury) from the Deposit Account of Northern Mechanical Division, PHE Dte. (Operator ID - 69 under Siliguri Treasury-I) through inter treasury transfer module of IFMS. |  |  | VCH/000387/2019-2020 | 94/W/19-20 | 12/06/2019 |  | NORTHERN MECHANICAL DIVISION II, P.H.E. DTE. | 55.51 | 0 | 0 | 0
3 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Water Supply Scheme for Mujnai Tea Garden Mouza. | SM/04770 | New | Supply, delivery of Electro Mechanical components at MUJNAI TEA GARDEN Water Supply Scheme IN THE Dist OF ALIPURDUAR under NMD-II,PHE.Dte. |  |  | ORD/000570/2020-2021 | 1443/NMD-II | 29/01/2021 | 28/02/2021 | S.P ENTERPRISE (SLG) | 8.99 | 8.99 | 100 | 0
4 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Water Supply Scheme for Mujnai Tea Garden Mouza. | SM/04770 | New | Continuation for Operation & guarding of the pumping machinery at Pump House No. II under MUJNAI TG W/S Scheme, in the dist. Of Alipurduar P.H.E.,Dte. |  |  | ORD/000008/2021-2022 | 66/AMSD | 27/04/2021 | 26/07/2021 | M/S MATRI CONSTRUCTION | 0.72 | 0 | 0 | 0
5 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Water Supply Scheme for Mujnai Tea Garden Mouza. | SM/04770 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under MUJNAI TG W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000360/2021-2022 | 727/NMD-II | 08/07/2021 | 08/07/2022 | M/S P.P ELECTRICALS | 2.97 | 0 | 0 | 0
6 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Water Supply Scheme for Mujnai Tea Garden Mouza. | SM/04770 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under MUJNAI TG W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000341/2021-2022 | 708/NMD-II | 08/07/2021 | 08/07/2022 | M/S MATRI CONSTRUCTION | 2.97 | 0 | 0 | 0
7 | ALIPURDUAR | Madarihat | Alipurduar Division | Water Supply Scheme for Mujnai Tea Garden Mouza. | SM/04770 | New | Supplying & laying of UPVC/DI/GI Distribution pipeline for Mujnai PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000103/2021-2022 | 902/ALD | 03/09/2021 | 03/10/2021 | DILIP MAHATO | 4.99 | 0 | 0 | 91
8 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Water Supply Scheme for Mujnai Tea Garden Mouza. | SM/04770 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at different PWSS under Birpara - Madarihat block in the dist. of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000521/2021-2022 | 1069/NMD-II | 10/09/2021 | 30/09/2021 | CHOWDHURY AND BASU ENTERPRISE | 4.72 | 0 | 0 | 0
9 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Water Supply Scheme for Mujnai Tea Garden Mouza. | SM/04770 | New | Supply, Delivery and fitting fixing of LED fixture instead of old damage LED at PHE compound of Dalmore TG & Mujnai TG W/S scheme in the dist. Alipurduar under, AMSD ,PHE Dte. |  |  | ORD/000781/2020-2021 | 765/AMSD | 28/12/2020 | 07/01/2021 | PRAGATI CONSTRUCTION COMPANY | 0.37 | 0.01 | 3.63 | 0
10 | ALIPURDUAR | Madarihat | Alipurduar Division | Water Supply Scheme for Mujnai Tea Garden Mouza. | SM/04770 | New | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Alipurduar - I Block,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 25/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 0 | 0 | 100
Total | [13 empty] | 583.83 | 9 | 1.54