## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Water Supply Scheme for Mujnai Tea Garden Mouza. | SM/04770 | New | Supply, delivery of Electro Mechanical components at MUJNAI TEA GARDEN Water Supply Scheme IN THE Dist OF ALIPURDUAR under NMD-II,PHE.Dte. |  |  | ORD/000570/2020-2021 | 1443/NMD-II | 29/01/2021 | 28/02/2021 | S.P ENTERPRISE (SLG) | 8.99 | 8.99 | 100 | 0
2 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Water Supply Scheme for Mujnai Tea Garden Mouza. | SM/04770 | New | Continuation for Operation & guarding of the pumping machinery at Pump House No. II under MUJNAI TG W/S Scheme, in the dist. Of Alipurduar P.H.E.,Dte. |  |  | ORD/000008/2021-2022 | 66/AMSD | 27/04/2021 | 27/07/2021 | M/S MATRI CONSTRUCTION | 0.72 | 0 | 0 | 0
3 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Water Supply Scheme for Mujnai Tea Garden Mouza. | SM/04770 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under MUJNAI TG W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000360/2021-2022 | 727/NMD-II | 08/07/2021 | 08/07/2022 | M/S P.P ELECTRICALS | 2.97 | 0 | 0 | 0
4 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Water Supply Scheme for Mujnai Tea Garden Mouza. | SM/04770 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under MUJNAI TG W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000341/2021-2022 | 708/NMD-II | 08/07/2021 | 08/07/2022 | M/S MATRI CONSTRUCTION | 2.97 | 0 | 0 | 0
5 | ALIPURDUAR | Madarihat | Alipurduar Division | Water Supply Scheme for Mujnai Tea Garden Mouza. | SM/04770 | New | Supplying & laying of UPVC/DI/GI Distribution pipeline for Mujnai PWSS under Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000103/2021-2022 | 902/ALD | 03/09/2021 | 03/10/2021 | DILIP MAHATO | 4.99 | 0 | 0 | 91
6 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Water Supply Scheme for Mujnai Tea Garden Mouza. | SM/04770 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at different PWSS under Birpara - Madarihat block in the dist. of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000521/2021-2022 | 1069/NMD-II | 10/09/2021 | 30/09/2021 | CHOWDHURY AND BASU ENTERPRISE | 4.72 | 0 | 0 | 0
7 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Water Supply Scheme for Mujnai Tea Garden Mouza. | SM/04770 | New | Supply, Delivery and fitting fixing of LED fixture instead of old damage LED at PHE compound of Dalmore TG & Mujnai TG W/S scheme in the dist. Alipurduar under, AMSD ,PHE Dte. |  |  | ORD/000781/2020-2021 | 765/AMSD | 28/12/2020 | 07/01/2021 | PRAGATI CONSTRUCTION COMPANY | 0.37 | 0 | 0 | 0
8 | ALIPURDUAR | Madarihat | Alipurduar Division | Water Supply Scheme for Mujnai Tea Garden Mouza. | SM/04770 | New | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Alipurduar - I Block,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 25/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 0 | 0 | 100
Total | [13 empty] | 528.31 | 8.99 | 1.7