## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Gargenda Tea Garden Piped Water Supply Scheme | SM/04790 | New | Supply, Delivery and fitting fixing of LED fixture instead of old damage LED at PHE compound of Gargenda Tea Garden W/S scheme, TW-I in the dist. Alipurduar under, AMSD ,PHE Dte. |  |  | ORD/000789/2020-2021 | 770/AMSD | 29/12/2020 | 08/01/2021 | SARKAR ELECTRIC | 0.74 | 0.07 | 10.04 | 0
2 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Gargenda Tea Garden Piped Water Supply Scheme | SM/04790 | New | Operation & guarding of the pumping machinery at Pump House No. III under GARGENDA TG W/S Scheme, in the dist. Of Alipurduar P.H.E.,Dte. |  |  | ORD/000790/2020-2021 | 525/AMSD | 18/09/2020 | 18/01/2021 | DEY ENTERPRISE (BALLY) | 0.98 | 0 | 0 | 0
3 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Gargenda Tea Garden Piped Water Supply Scheme | SM/04790 | New | Withdrawing & installation of 15 HP Submersible pump machinery along with supply and installation of electro mechanical accessories at P/H no. -I under Gargenda TG water supply scheme in the dist. Alipurduar. |  |  | ORD/000788/2020-2021 | 769/AMSD | 29/12/2020 | 08/01/2021 | SARKAR ELECTRIC | 0.79 | 0 | 0 | 0
4 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Gargenda Tea Garden Piped Water Supply Scheme | SM/04790 | New | Quotation of Garganda TG Phmp House No.- III (Application no.- 4002445036 |  |  | VCH/000591/2019-2020 | 97/19-20 | 06/01/2020 | 06/01/2020 | WBSEDCL | 0.9 | 0 | 0 | 0
5 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Gargenda Tea Garden Piped Water Supply Scheme | SM/04790 | New | Supply, delivery of Electro Mechanical components at GARGENDA TEA GARDEN Water Supply Scheme IN THE Dist OF ALIPURDUAR under NMD-II,PHE.Dte. |  |  | ORD/000569/2020-2021 | 1429/NMD-II | 28/01/2021 | 27/02/2021 | QUAZI NOZRUL ISLAM | 7.39 | 13.4 | 181.34 | 0
6 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Gargenda Tea Garden Piped Water Supply Scheme | SM/04790 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at different PWSS under Birpara - Madarihat block in the dist. of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000521/2021-2022 | 1069/NMD-II | 10/09/2021 | 30/09/2021 | CHOWDHURY AND BASU ENTERPRISE | 4.72 | 0 | 0 | 0
7 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Gargenda Tea Garden Piped Water Supply Scheme | SM/04790 | New | Continuation for Operation & guarding of the pumping machinery at Pump House No. III under GARGENDA TG W/S Scheme, in the dist. Of Alipurduar P.H.E.,Dte. |  |  | ORD/000624/2021-2022 | 136/AMSD | 24/05/2021 | 24/07/2021 | DEY ENTERPRISE (BALLY) | 0.48 | 0 | 0 | 0
8 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Gargenda Tea Garden Piped Water Supply Scheme | SM/04790 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under GARGENDA TG W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000416/2021-2022 | 749/NMD-II | 08/07/2021 | 08/07/2022 | SUBODH KUMAR BANIK | 2.97 | 0 | 0 | 0
9 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Gargenda Tea Garden Piped Water Supply Scheme | SM/04790 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under GARGENDA TG W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000417/2021-2022 | 750/NMD-II | 08/07/2021 | 08/07/2022 | SUBODH KUMAR BANIK | 2.97 | 0 | 0 | 0
10 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Gargenda Tea Garden Piped Water Supply Scheme | SM/04790 | New | Operation and Guarding of Pumping machinery at Pump House No. III , Under GARGENDA TG W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000551/2021-2022 | 766/NMD-II | 08/07/2021 | 08/07/2022 | DEY ENTERPRISE (BALLY) | 2.97 | 0 | 0 | 0
11 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Gargenda Tea Garden Piped Water Supply Scheme | SM/04790 | New | Continuation for Operation & guarding of the pumping machinery at Pump House No. III under GARGENDA TG W/S Scheme, in the dist. Of Alipurduar P.H.E.,Dte. |  |  | ORD/000862/2020-2021 | 852/AMSD | 27/01/2021 | 27/05/2021 | DEY ENTERPRISE (BALLY) | 0.95 | 0 | 0 | 0
12 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Gargenda Tea Garden Piped Water Supply Scheme | SM/04790 | New | Supply, delivery and installation of standby automatically controlled hydrualic diaphragm type Chlorinator for accurate dosing of Chlorine solution at P/H No.I of Lankapara T G ,Makrapar T.G Gargenda TG W/S scheme and P/H No.II of Uttar Kamakhyaguri in the district of Alipurduar under NMD-II ,P.H.E Dte. |  |  | ORD/000578/2021-2022 | 1026/NMD-II | 27/08/2021 | 16/09/2021 | DIAMOND ELECTRICAL WORKS | 3.5 | 0 | 0 | 0
13 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Gargenda Tea Garden Piped Water Supply Scheme | SM/04790 | New | Supply & delivery of standby automatically controlled hydrualic diaphragm type Chlorinator for accurate dosing of Chlorine solution at Dekhlapara T.G P/H No.-I , Birpara p/H No.I, Paschim Khairbari P/H No.II ,Gargenda P/h No.II, Dhumchipara P/HNo.I in the district of Alipurduar under NMD-II ,P.H.E Dte. |  |  | ORD/000522/2021-2022 | 1070/NMD-II | 10/09/2021 | 30/09/2021 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 3.76 | 0 | 0 | 0
14 | ALIPURDUAR | Madarihat | Alipurduar Division | Gargenda Tea Garden Piped Water Supply Scheme | SM/04790 | New | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Alipurduar - I Block,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 25/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 29.03 | 5.78 | 100
15 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Gargenda Tea Garden Piped Water Supply Scheme | SM/04790 | New | Supply, delivery,of Electro mechanical components at Gargenda T.G Water Supply Scheme in the dist of ALIPURDUAR under NMD-II,PHE.Dte,Alipurduar. |  |  | ORD/000858/2021-2022 | 298/ NMD-II | 10/03/2022 | 09/04/2022 | KASHI NATH DEY | 6.52 | 5.67 | 87.06 | 0
Total | [13 empty] | 542.21 | 48.18 | 8.89