## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar - I | Northern Mechanical | Paitkapara Tea Garden Piped Water Supply Scheme | SM/04810 | New | Consolidated Bill |  |  | VCH/000851/2018-2019 | 1082/W/18-19 | 21/02/2019 |  | B.B. CONCERNED | 3.3 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar - I | Northern Mechanical | Paitkapara Tea Garden Piped Water Supply Scheme | SM/04810 | New | Consolidated Supply Bills |  |  | VCH/001055/2018-2019 | 1230/W/18-19 | 18/03/2019 |  | M/S P.P. ELECTRICALS | 3.39 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar - I | Jalpaiguri Division | Paitkapara Tea Garden Piped Water Supply Scheme | SM/04810 | New | PATKAPARA T.G |  |  | VCH/001047/2018-2019 | 1023 | 01/02/2019 |  | EXECUTIVE ENGINEER ALIPURDUAR DIVISION P.H.E. DTE | 7.85 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar - I | Jalpaiguri Division | Paitkapara Tea Garden Piped Water Supply Scheme | SM/04810 | New | PATKAPARA T.G |  |  | VCH/001047/2018-2019 | 1023 | 01/02/2019 |  | EXECUTIVE ENGINEER ALIPURDUAR DIVISION P.H.E. DTE | 7.85 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | Paitkapara Tea Garden Piped Water Supply Scheme | SM/04810 | New | E-TENDER DOCUMENTS PROCESSING FOR BILL 4 |  |  | VCH/000315/2018-2019 | 407/18-19 | 25/03/2019 |  | PRIYANKA MANDAL | 0.07 | 0 | 0 | 0
6 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | Paitkapara Tea Garden Piped Water Supply Scheme | SM/04810 | New | E TENDER DOCUMENT PROCESSING BILL 2 |  |  | VCH/000318/2018-2019 | 406/18-19 | 25/03/2019 |  | PRIYANKA MANDAL | 0.05 | 0 | 0 | 0
7 | ALIPURDUAR | Alipurduar - I | Jalpaiguri Division | Paitkapara Tea Garden Piped Water Supply Scheme | SM/04810 | New | Bhangarhat |  |  | VCH/000038/2019-2020 | 43 | 16/05/2019 |  | PRADIP SAHA | 1.73 | 0 | 0 | 0
8 | ALIPURDUAR | Alipurduar - I | Northern Mechanical | Paitkapara Tea Garden Piped Water Supply Scheme | SM/04810 | New | Certified that, the marked schemes vide Sl. No. 1-4, 9-11, 14, 16, 22, 29-31, 33, 36, 38, 44, 45, 50, 53, 55, 56, 65, 71, 73, 80-86, 89-92, 94, 103, 107, 108, 110-112, 134, 135, 141-143, 152, 154, 156, 158, 159, 161-163, 167, 168, 174-187, 202-210, 214, 222-229, 243, 266, 267, 277, 278, 287, 294, 300, 305, 317-320, 331, 332, 335-337, 340-342, 348, 349, 352, 353 comes under the jurisdiction of Northern Mechanical Division-II, PHE Dte. and which accured to Rs 55,50,591.00/- (Rupees fifty five lakh fifty thousand five hundred ninety one only) out of total balance amount Rs 6,13,62,046.94/- (Rupees six crore thirteen lakh sixty two thousand forty six and ninety four paise only) to be transferred at the Deposit Account of Northern Mechanical Division-II, PHE Dte. (Operator ID - 71 under Alipurduar Treasury) from the Deposit Account of Northern Mechanical Division, PHE Dte. (Operator ID - 69 under Siliguri Treasury-I) through inter treasury transfer module of IFMS. |  |  | VCH/000387/2019-2020 | 94/W/19-20 | 12/06/2019 |  | NORTHERN MECHANICAL DIVISION II, P.H.E. DTE. | 55.51 | 0 | 0 | 0
9 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | Paitkapara Tea Garden Piped Water Supply Scheme | SM/04810 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under PAITKAPARA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000356/2021-2022 | 723/NMD-II | 08/07/2021 | 08/07/2022 | M/S P.P ELECTRICALS | 2.97 | 0 | 0 | 0
10 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | Paitkapara Tea Garden Piped Water Supply Scheme | SM/04810 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under PAITKAPARA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000338/2021-2022 | 705/NMD-II | 08/07/2021 | 08/07/2022 | B.B CONCERNED | 2.97 | 0 | 0 | 0
11 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | Paitkapara Tea Garden Piped Water Supply Scheme | SM/04810 | New | Supply, delivery of Electro mechanical components at Paitkapara T.G Water Supply Scheme and other adjacent scheme in the dist of ALIPURDUAR under NMD-II,PHE Dte Alipurduar. |  |  | ORD/000879/2021-2022 | 370/NMD-II | 16/03/2022 | 15/04/2022 | M/S P.P ELECTRICALS | 12.6 | 12.6 | 100 | 0
12 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | Paitkapara Tea Garden Piped Water Supply Scheme | SM/04810 | New | Quotation for new service connection at Paitkapara w/ss at Tw no III. Application no 4002956355 |  |  | VCH/000688/2022-2023 | null | 04/08/2022 |  | WBSEDCL | 0.87 | 0 | 0 | 0
13 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | Paitkapara Tea Garden Piped Water Supply Scheme | SM/04810 | New | Quotation for new service connection for PATKAPARA W/ss T/W no. III Application no. 4002956355 |  |  | VCH/001290/2022-2023 | BP-45/22-23 | 08/08/2022 |  | WBSEDCL | 0.87 | 0 | 0 | 0
14 | ALIPURDUAR | Alipurduar - I | Alipurduar Division | Paitkapara Tea Garden Piped Water Supply Scheme | SM/04810 | New | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of PAITKAPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar RWS | RWS Alipurduar - I Block | ORD/000296/2021-2022 | 1994/ALD | 27/12/2021 | 27/03/2022 | ANUP GUPTA | 20.99 | 0 | 0 | 70
15 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | Paitkapara Tea Garden Piped Water Supply Scheme | SM/04810 | New | Supply, delivery and installation of standby automatically controlled hydrualic diaphragm type Chlorinator for accurate dosing of Chlorine solution at differernt PWSS under Alipurduar-I Block in the district of Alipurduar under NMD-II ,P.H.E Dte. |  |  | ORD/000597/2021-2022 | 1042/NMD-II | 03/09/2021 | 23/09/2021 | MUSTAFI CONCERN | 3.5 | 0 | 0 | 0
16 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | Paitkapara Tea Garden Piped Water Supply Scheme | SM/04810 | New | Supply and Delivery of Calcium Hypochlorite[Ca(Ocl)2] granules at Different PWSS under Alipurduar-I & II Block in the Dist of Alipurduar under Northern Mechanical Division-II,PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000395/2021-2022 | 863/NMD-II | 28/07/2021 | 27/08/2021 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 3.58 | 0 | 0 | 0
17 | ALIPURDUAR | Alipurduar - I | Northern Mechanical Division II | Paitkapara Tea Garden Piped Water Supply Scheme | SM/04810 | New | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Paitkapara Tea Garden Water Supply Scheme TW No.-III under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000791/2022-2023 | 268/NMD-II | 16/02/2023 | 18/03/2023 | MADHAB SAHA | 8.27 | 8.27 | 100 | 100
Total | [13 empty] | 136.38 | 20.87 | 15.3