## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | Paitkapara Tea Garden Piped Water Supply Scheme | SM/04810 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under PAITKAPARA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000356/2021-2022 | 723/NMD-II | 08/07/2021 | 08/07/2022 | M/S P.P ELECTRICALS | 2.97 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | Paitkapara Tea Garden Piped Water Supply Scheme | SM/04810 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under PAITKAPARA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000338/2021-2022 | 705/NMD-II | 08/07/2021 | 08/07/2022 | B.B CONCERNED | 2.97 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | Paitkapara Tea Garden Piped Water Supply Scheme | SM/04810 | New | Supply, delivery of Electro mechanical components at Paitkapara T.G Water Supply Scheme and other adjacent scheme in the dist of ALIPURDUAR under NMD-II,PHE Dte Alipurduar. |  |  | ORD/000879/2021-2022 | 370/NMD-II | 16/03/2022 | 15/04/2022 | M/S P.P ELECTRICALS | 12.6 | 12.6 | 100 | 0
4 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | Paitkapara Tea Garden Piped Water Supply Scheme | SM/04810 | New | Quotation for new service connection at Paitkapara w/ss at Tw no III. Application no 4002956355 |  |  | VCH/000688/2022-2023 |  | 04/08/2022 | 04/08/2022 | WBSEDCL | 0.87 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | Paitkapara Tea Garden Piped Water Supply Scheme | SM/04810 | New | Quotation for new service connection for PATKAPARA W/ss T/W no. III Application no. 4002956355 |  |  | VCH/001290/2022-2023 | BP-45/22-23 | 08/08/2022 | 08/08/2022 | WBSEDCL | 0.87 | 0 | 0 | 0
6 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | Paitkapara Tea Garden Piped Water Supply Scheme | SM/04810 | New | Supply, delivery and installation of standby automatically controlled hydrualic diaphragm type Chlorinator for accurate dosing of Chlorine solution at differernt PWSS under Alipurduar-I Block in the district of Alipurduar under NMD-II ,P.H.E Dte. |  |  | ORD/000597/2021-2022 | 1042/NMD-II | 03/09/2021 | 23/09/2021 | MUSTAFI CONCERN | 3.5 | 0 | 0 | 0
7 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | Paitkapara Tea Garden Piped Water Supply Scheme | SM/04810 | New | Supply and Delivery of Calcium Hypochlorite[Ca(Ocl)2] granules at Different PWSS under Alipurduar-I & II Block in the Dist of Alipurduar under Northern Mechanical Division-II,PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000395/2021-2022 | 863/NMD-II | 28/07/2021 | 27/08/2021 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 3.58 | 0 | 0 | 0
8 | ALIPURDUAR | Alipurduar-I | Northern Mechanical Division II | Paitkapara Tea Garden Piped Water Supply Scheme | SM/04810 | New | Supply, delivery, installation, commissioning and Trial run of submersible pumping machinery including auto cum manual control panel and other related accessories of Paitkapara Tea Garden Water Supply Scheme TW No.-III under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000791/2022-2023 | 268/NMD-II | 16/02/2023 | 18/03/2023 | MADHAB SAHA | 8.27 | 8.27 | 100 | 100
9 | ALIPURDUAR | Alipurduar-I | Alipurduar Division | Paitkapara Tea Garden Piped Water Supply Scheme | SM/04810 | New | Construction of Pump House ,Boundary Wall , Tube well Boring ( ODEX-165 Method of drilling) and Rising Main for Additional T/W of PAITKAPARA Piped Water Supply Scheme Under Alipurduar Division PHE DTE. | Alipurduar RWS | RWS Alipurduar - I Block,RWS Madarihat - Birpara Block | ORD/000296/2021-2022 | 1994/ALD | 27/12/2021 | 27/03/2022 | ANUP GUPTA | 20.99 | 0 | 0 | 80
Total | [13 empty] | 56.62 | 20.87 | 36.86