## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Falakata | Northern Mechanical Division II | Chhota Salkumar Piped Water Supply Scheme | SM/04848 | New | Supply, delivery of Electro mechanical components at Chhota Shalkumar Water Supply Scheme and other adjacent moujas in the dist of ALIPURDUAR under NMD-II PHE Dte Alipurduar. |  |  | ORD/000880/2021-2022 | 371/NMD-II | 16/03/2022 | 15/04/2022 | SUNLIT | 6.29 | 6.29 | 100 | 0
2 | ALIPURDUAR | Falakata | Northern Mechanical Division II | Chhota Salkumar Piped Water Supply Scheme | SM/04848 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under CHHOTOSALKUMAR W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000334/2021-2022 | 701/NMD-II | 08/07/2021 | 08/07/2022 | CHOWDHURY AND BASU ENTERPRISE | 2.97 | 0 | 0 | 0
3 | ALIPURDUAR | Falakata | Alipurduar Division | Chhota Salkumar Piped Water Supply Scheme | SM/04848 | New | Construction of 300 m3 capacity RCC Over Head Reservoir For SALKUMARHAT PWSS under Alipurduar Division PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000080/2020-2021 | 632/ALD | 03/09/2020 | 02/12/2020 | HARIDAS GHOSH | 63.58 | 61.68 | 97.02 | 80
4 | ALIPURDUAR | Falakata | Northern Mechanical Division II | Chhota Salkumar Piped Water Supply Scheme | SM/04848 | New | -"Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at Bhutnirghat ,Choto salkumar, Dalimpur etc under Falakata block in the dist. of Alipurduar under NMD-II P.H E Dte¿ |  |  | ORD/000614/2021-2022 | 1114/NMD-II | 20/09/2021 | 20/10/2021 | M/S PARITOSH BHOWMICK & CO. | 2.15 | 0 | 0 | 0
5 | ALIPURDUAR | Falakata | Northern Mechanical Division II | Chhota Salkumar Piped Water Supply Scheme | SM/04848 | New | Supply, delivery and installation of standby automatically controlled hydrualic diaphragm type Chlorinator for accurate dosing of Chlorine solution at P/H No.I&II under Satkura and Salmara P/H No.I PWSS in the district of Coochbehar under NMD-II ,P.H.E Dte. |  |  | ORD/000569/2021-2022 | 1014/NMD-II | 27/08/2021 | 16/09/2021 | SUNLIT | 2.6 | 0.19 | 7.25 | 0
6 | ALIPURDUAR | Falakata | Northern Mechanical Division II | Chhota Salkumar Piped Water Supply Scheme | SM/04848 | New | Supply, delivery and installation of standby automatically controlled hydraulic diaphragm type Chlorinator for accurate dosing of Chlorine solution at P/H No.II of Chhoto Salkumar , Jogijhora Barabak, BhutnirghatW/S Scheme and P/H No.I of Jogendrapur W/S Scheme of Falakata Block etc in the district of Alipurduar under NMD-II P.H.E Dte. |  |  | ORD/000595/2021-2022 | 1041/NMD-II | 03/09/2021 | 23/09/2021 | SARKAR ELECTRIC | 3.39 | 0 | 0 | 0
7 | ALIPURDUAR | Falakata | Alipurduar Division | Chhota Salkumar Piped Water Supply Scheme | SM/04848 | New | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Alipurduar - I Block,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 25/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 26.25 | 5.22 | 100
8 | ALIPURDUAR | Falakata | Northern Mechanical Division II | Chhota Salkumar Piped Water Supply Scheme | SM/04848 | New | Quotation for new service connection at Chhota salkumar TW No III |  |  | BILL/00033/2022-2023 | BP-122/22-23 | 09/01/2023 | 09/01/2023 | WBSEDCL | 1.46 | 0 | 0 | 0
9 | ALIPURDUAR | Falakata | Northern Mechanical Division II | Chhota Salkumar Piped Water Supply Scheme | SM/04848 | New | "Hiring of Motor Cab (Non-air conditioned) for site visit of JJM Works under the Office of the EE/NMD-II P.H.E. Dte." |  |  | ORD/000097/2025-2026 | 191/AMSD | 21/04/2025 | 21/06/2025 | D.K AND SONS | 0.75 | 0 | 0 | 0
10 | ALIPURDUAR | Falakata | Northern Mechanical Division II | Chhota Salkumar Piped Water Supply Scheme | SM/04848 | New | "Hiring of Motor Cab (Non-air conditioned) for site visit of JJM Works under the Office of the EE/NMD-II P.H.E. Dte." |  |  | ORD/001450/2024-2025 | 97/AMSD | 27/02/2025 | 27/04/2025 | D.K AND SONS | 0.75 | 0 | 0 | 0
Total | [13 empty] | 586.52 | 94.42 | 16.1