## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Northern Mechanical | Construction of 43 nos. Rig Bored Tubewells fitted with India Mark-II hand pump in 5 nos. Tea Gardens | SM/04963 | New | Supply of Fuel & Other Consumable items |  |  | VCH/001894/2020-2021 |  | 04/03/2021 | 04/03/2021 | M/S MILLENNIUM FUEL CENTRE | 1.38 | 0 | 0 | 0
2 | ALIPURDUAR |  | Northern Mechanical | Construction of 43 nos. Rig Bored Tubewells fitted with India Mark-II hand pump in 5 nos. Tea Gardens | SM/04963 | New | Supply of Fuel & Other Consumable items |  |  | VCH/001891/2020-2021 |  | 04/03/2021 | 04/03/2021 | M/S MILLENNIUM FUEL CENTRE | 1.36 | 0 | 0 | 0
3 | ALIPURDUAR |  | Northern Mechanical | Construction of 43 nos. Rig Bored Tubewells fitted with India Mark-II hand pump in 5 nos. Tea Gardens | SM/04963 | New | Supply of Fuel & Other Consumable items |  |  | VCH/001893/2020-2021 |  | 04/03/2021 | 04/03/2021 | M/S MILLENNIUM FUEL CENTRE | 1.92 | 0 | 0 | 0
4 | ALIPURDUAR |  | Northern Mechanical | Construction of 43 nos. Rig Bored Tubewells fitted with India Mark-II hand pump in 5 nos. Tea Gardens | SM/04963 | New | Supply of Fuel & Other Consumable items |  |  | VCH/001892/2020-2021 |  | 04/03/2021 | 04/03/2021 | M/S MILLENNIUM FUEL CENTRE | 1.44 | 0 | 0 | 0
5 | ALIPURDUAR |  | Northern Mechanical | Construction of 43 nos. Rig Bored Tubewells fitted with India Mark-II hand pump in 5 nos. Tea Gardens | SM/04963 | New | Supply of Fuel & Other Consumable items |  |  | VCH/001890/2020-2021 |  | 04/03/2021 | 04/03/2021 | M/S MILLENNIUM FUEL CENTRE | 2.65 | 0 | 0 | 0
6 | ALIPURDUAR |  | Northern Mechanical | Construction of 43 nos. Rig Bored Tubewells fitted with India Mark-II hand pump in 5 nos. Tea Gardens | SM/04963 | New | Surrender unspent Jal Jeevan Mission Fund to Jal Jeevan Mission West Bengal ESCROW AC |  |  | VCH/001782/2021-2022 | 295/W/21-22 | 17/03/2022 | 17/03/2022 | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 90.18 | 0 | 0 | 0
Total | [13 empty] | 98.94 | 0 | 0