## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Renovation of the electrical installation of BAROVISA W/S scheme T/W No. - II under NMD-II , PHE, Dte. Alipuduar . |  |  | ORD/000787/2020-2021 | 864/AMSD | 29/01/2021 | 08/02/2021 | PRAGATI CONSTRUCTION COMPANY | 0.58 | 0 | 0 | 0
2 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Operation and Guarding of Pumping machinery at Pump House No. IV , Under BAROVISA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000563/2021-2022 | 650/NMD-II | 06/07/2021 | 06/07/2022 | SUDIP DUTTA | 4.88 | 0 | 0 | 0
3 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Operation and Guarding of Pumping machinery at Pump House No. I, ZONE - III under BAROVISA W/S Scheme. In the dist. Of ALIPURDUAR |  |  | ORD/000508/2021-2022 | 762/NMD-II | 08/07/2021 | 08/07/2022 | DIAMOND ELECTRICAL WORKS | 2.97 | 0 | 0 | 0
4 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Operation and Guarding of Pumping machinery at Pump House No. II , Under BAROVISA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000552/2021-2022 | 645/NMD-II | 06/07/2021 | 06/07/2022 | HARA PROSAD DAS | 4.88 | 0 | 0 | 0
5 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Operation and Guarding of Pumping machinery at Pump House No. I, Zone - II , Under BAROVISA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000352/2021-2022 | 719/NMD-II | 08/07/2021 | 08/07/2022 | GEETA CONSTRUCTION | 2.97 | 0 | 0 | 0
6 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Operation and Guarding of Pumping machinery at Pump House No. II, Zone - II , Under BAROVISA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000363/2021-2022 | 728/NMD-II | 08/07/2021 | 08/07/2022 | RIPON DAS | 2.97 | 0 | 0 | 0
7 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Withdrawing & installation of 7.5 HP Submersible pump machinery and repairing the same under BAROVISA WATER SUPPLY SCHEME,P/H No-IV under Northern Mechanical Division-II Phe. Dte. In the dist. Of Alipurduar. |  |  | ORD/000759/2021-2022 | 24/AMSD | 12/04/2021 | 22/04/2021 | M/S ANJALI ENTERPRISE | 0.28 | 0 | 0 | 0
8 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Supply, delivery,of Electro mechanical components at Barovisa Water Supply Scheme & adjoining mouzas in the dist of ALIPURDUAR under NMD-II,PHE.Dte,Alipurduar. |  |  | ORD/000848/2021-2022 | 627/AMSD | 03/03/2022 | 18/03/2022 | SARKAR ELECTRIC | 2.74 | 2.74 | 100 | 0
9 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Supply, delivery, of Electro mechanical components at Barovisa Water Supply Scheme(AUG) ,Zone-I TW No-I in the dist of ALIPURDUAR under NMD-II, PHE. Dte, Alipurduar. |  |  | ORD/000016/2022-2023 | 606/NMD-II | 06/05/2022 | 05/06/2022 | RIPON DAS | 7.55 | 7.55 | 100 | 0
10 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Supply, delivery of Electro mechanical components at Barovisa Water Supply Scheme(AUG) ,Zone-II TW No-II in the dist. of ALIPURDUAR under NMD-II, PHE. Dte, Alipurduar. |  |  | ORD/000012/2022-2023 | 580/NMD-II | 29/04/2022 | 29/05/2022 | SUMON ELECTRICAL | 7.99 | 7.99 | 100 | 0
11 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Quotation for burnt meter problem, Consumer ID: 423028936,Application no. 4003027556 |  |  | VCH/001469/2022-2023 | BP-92/22-23 | 22/11/2022 | 22/11/2022 | WBSEDCL | 0.09 | 0 | 0 | 0
12 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Supply and Delivery of 100 Amp,50 Hz ,415 Volt Kit Kat Rewireable Fuse for using breakdown purpose at Barovisa w/s scheme and adjoining mouzas in the dist. of Alipurduar under, Northern Mechanical Division-II ,PHE Dte. |  |  | ORD/000161/2022-2023 | 192/AMSD | 04/07/2022 | 14/07/2022 | SARKAR ELECTRIC | 0.91 | 0 | 0 | 0
13 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Supply, delivery and installation of 25 KVA servo motor operated Copper wound line voltage corrector at BAROVISA W/S Scheme,T/W NO- II under NMD-II, P.H.E. Dte.Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000046/2020-2021 | 1139/NMD-II | 15/10/2020 | 15/11/2020 | B.B CONCERNED | 3.12 | 0.28 | 8.94 | 0
14 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at different PWSS under Kumargram block in the dist. of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000520/2021-2022 | 1076/NMD-II | 10/09/2021 | 30/09/2021 | M/S P.P ELECTRICALS | 3.58 | 0 | 0 | 0
15 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at Barovisa, Radharani etc under Kumargram & Kalchini block in the dist. of Alipurduar¿ |  |  | ORD/000702/2021-2022 | 1313/NMD-II | 03/12/2021 | 18/12/2021 | DIPA CHHETRI | 1.29 | 0 | 0 | 0
16 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Supply and Delivery of Standby Submersible Pump for attending breakdown maintenance at Augmentation of Barovisa W/S Scheme, in the Dist of Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000976/2023-2024 | 143/AMSD | 05/07/2023 | 15/07/2023 | MUSTAFI CONCERN | 0.82 | 0.82 | 100 | 100
17 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for Rejuvenation of DIMA T.G water supply scheme, TW no III under NMD-II, PHE Dte 106. APD. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/001076/2023-2024 | 2766/NMD-II | 04/10/2023 | 02/08/2025 | ASHWIRBAD WOOD CRAFT | 10.68 | 0 | 0 | 90
Total | [13 empty] | 58.28 | 19.38 | 33.25