## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Northern Mechanical | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Bill for Advertisement |  |  | VCH/001259/2018-2019 | 1305/W/18-19 | 25/03/2019 |  | UTTARBANGA SAMBAD | 0.72 | 0 | 0 | 0
2 | ALIPURDUAR |  | Northern Mechanical | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Bill for Advertisement |  |  | VCH/001260/2018-2019 | 1305/W/18-19 | 25/03/2019 |  | GENESIS ADVERTISING PVT LTD | 2.62 | 0 | 0 | 0
3 | ALIPURDUAR |  | Jalpaiguri Division | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Barovisa |  |  | VCH/001051/2018-2019 | 1023 | 01/02/2019 |  | EXECUTIVE ENGINEER ALIPURDUAR DIVISION P.H.E. DTE | 11.78 | 0 | 0 | 0
4 | ALIPURDUAR |  | Northern Mechanical | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Certified that, the marked schemes vide Sl. No. 1-4, 9-11, 14, 16, 22, 29-31, 33, 36, 38, 44, 45, 50, 53, 55, 56, 65, 71, 73, 80-86, 89-92, 94, 103, 107, 108, 110-112, 134, 135, 141-143, 152, 154, 156, 158, 159, 161-163, 167, 168, 174-187, 202-210, 214, 222-229, 243, 266, 267, 277, 278, 287, 294, 300, 305, 317-320, 331, 332, 335-337, 340-342, 348, 349, 352, 353 comes under the jurisdiction of Northern Mechanical Division-II, PHE Dte. and which accured to Rs 55,50,591.00/- (Rupees fifty five lakh fifty thousand five hundred ninety one only) out of total balance amount Rs 6,13,62,046.94/- (Rupees six crore thirteen lakh sixty two thousand forty six and ninety four paise only) to be transferred at the Deposit Account of Northern Mechanical Division-II, PHE Dte. (Operator ID - 71 under Alipurduar Treasury) from the Deposit Account of Northern Mechanical Division, PHE Dte. (Operator ID - 69 under Siliguri Treasury-I) through inter treasury transfer module of IFMS. |  |  | VCH/000387/2019-2020 | 94/W/19-20 | 12/06/2019 |  | NORTHERN MECHANICAL DIVISION II, P.H.E. DTE. | 55.51 | 0 | 0 | 0
5 | ALIPURDUAR |  | Northern Mechanical | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Certified that, the marked schemes vide Sl. No. 1-4, 9-11, 14, 16, 22, 29-31, 33, 36, 38, 44, 45, 50, 53, 55, 56, 65, 71, 73, 80-86, 89-92, 94, 103, 107, 108, 110-112, 134, 135, 141-143, 152, 154, 156, 158, 159, 161-163, 167, 168, 174-187, 202-210, 214, 222-229, 243, 266, 267, 277, 278, 287, 294, 300, 305, 317-320, 331, 332, 335-337, 340-342, 348, 349, 352, 353 comes under the jurisdiction of Northern Mechanical Division-II, PHE Dte. and which accured to Rs 55,50,591.00/- (Rupees fifty five lakh fifty thousand five hundred ninety one only) out of total balance amount Rs 6,13,62,046.94/- (Rupees six crore thirteen lakh sixty two thousand forty six and ninety four paise only) to be transferred at the Deposit Account of Northern Mechanical Division-II, PHE Dte. (Operator ID - 71 under Alipurduar Treasury) from the Deposit Account of Northern Mechanical Division, PHE Dte. (Operator ID - 69 under Siliguri Treasury-I) through inter treasury transfer module of IFMS. |  |  | VCH/000387/2019-2020 | 94/W/19-20 | 12/06/2019 |  | NORTHERN MECHANICAL DIVISION II, P.H.E. DTE. | 55.51 | 0 | 0 | 0
6 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Renovation of the electrical installation of BAROVISA W/S scheme T/W No. - II under NMD-II , PHE, Dte. Alipuduar . |  |  | ORD/000787/2020-2021 | 864/AMSD | 29/01/2021 | 08/02/2021 | PRAGATI CONSTRUCTION COMPANY | 0.58 | 0 | 0 | 0
7 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Operation and Guarding of Pumping machinery at Pump House No. I, ZONE - III under BAROVISA W/S Scheme. In the dist. Of ALIPURDUAR |  |  | ORD/000508/2021-2022 | 762/NMD-II | 08/07/2021 | 08/07/2022 | DIAMOND ELECTRICAL WORKS | 2.97 | 0 | 0 | 0
8 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Operation and Guarding of Pumping machinery at Pump House No. II , Under BAROVISA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000552/2021-2022 | 645/NMD-II | 06/07/2021 | 06/07/2022 | HARA PROSAD DAS | 4.88 | 0 | 0 | 0
9 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Operation and Guarding of Pumping machinery at Pump House No. I, Zone - II , Under BAROVISA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000352/2021-2022 | 719/NMD-II | 08/07/2021 | 08/07/2022 | GEETA CONSTRUCTION | 2.97 | 0 | 0 | 0
10 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Operation and Guarding of Pumping machinery at Pump House No. II, Zone - II , Under BAROVISA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000363/2021-2022 | 728/NMD-II | 08/07/2021 | 08/07/2022 | RIPON DAS | 2.97 | 0 | 0 | 0
11 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Operation and Guarding of Pumping machinery at Pump House No. IV , Under BAROVISA W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000563/2021-2022 | 650/NMD-II | 06/07/2021 | 06/07/2022 | SUDIP DUTTA | 4.88 | 0 | 0 | 0
12 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Supply, delivery,of Electro mechanical components at Barovisa Water Supply Scheme & adjoining mouzas in the dist of ALIPURDUAR under NMD-II,PHE.Dte,Alipurduar. |  |  | ORD/000848/2021-2022 | 627/AMSD | 03/03/2022 | 18/03/2022 | SARKAR ELECTRIC | 2.74 | 2.74 | 100 | 0
13 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Withdrawing & installation of 7.5 HP Submersible pump machinery and repairing the same under BAROVISA WATER SUPPLY SCHEME,P/H No-IV under Northern Mechanical Division-II Phe. Dte. In the dist. Of Alipurduar. |  |  | ORD/000759/2021-2022 | 24/AMSD | 12/04/2021 | 22/04/2021 | M/S ANJALI ENTERPRISE | 0.28 | 0 | 0 | 0
14 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Supply, delivery of Electro mechanical components at Barovisa Water Supply Scheme(AUG) ,Zone-II TW No-II in the dist. of ALIPURDUAR under NMD-II, PHE. Dte, Alipurduar. |  |  | ORD/000012/2022-2023 | 580/NMD-II | 29/04/2022 | 29/05/2022 | SUMON ELECTRICAL | 7.99 | 7.99 | 100 | 0
15 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Supply, delivery, of Electro mechanical components at Barovisa Water Supply Scheme(AUG) ,Zone-I TW No-I in the dist of ALIPURDUAR under NMD-II, PHE. Dte, Alipurduar. |  |  | ORD/000016/2022-2023 | 606/NMD-II | 06/05/2022 | 05/06/2022 | RIPON DAS | 7.55 | 7.55 | 100 | 0
16 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Quotation for burnt meter problem, Consumer ID: 423028936,Application no. 4003027556 |  |  | VCH/001469/2022-2023 | BP-92/22-23 | 22/11/2022 |  | WBSEDCL | 0.09 | 0 | 0 | 0
17 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Supply, delivery and installation of 25 KVA servo motor operated Copper wound line voltage corrector at BAROVISA W/S Scheme,T/W NO- II under NMD-II, P.H.E. Dte.Alipurduar. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000046/2020-2021 | 1139/NMD-II | 15/10/2020 | 14/11/2020 | B.B CONCERNED | 3.12 | 0.28 | 8.94 | 0
18 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at different PWSS under Kumargram block in the dist. of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000520/2021-2022 | 1076/NMD-II | 10/09/2021 | 30/09/2021 | M/S P.P ELECTRICALS | 3.58 | 0 | 0 | 0
19 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at Barovisa, Radharani etc under Kumargram & Kalchini block in the dist. of Alipurduar¿ |  |  | ORD/000702/2021-2022 | 1313/NMD-II | 03/12/2021 | 18/12/2021 | DIPA CHHETRI | 1.29 | 0 | 0 | 0
20 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Supply and Delivery of 100 Amp,50 Hz ,415 Volt Kit Kat Rewireable Fuse for using breakdown purpose at Barovisa w/s scheme and adjoining mouzas in the dist. of Alipurduar under, Northern Mechanical Division-II ,PHE Dte. |  |  | ORD/000161/2022-2023 | 192/AMSD | 04/07/2022 | 14/07/2022 | SARKAR ELECTRIC | 0.91 | 0 | 0 | 0
21 | ALIPURDUAR |  | Alipurduar Division | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Continuation order of Supply of fuel for Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01.02.2023 to 30.04.2023) | HQ-A.E |  | ORD/000566/2022-2023 | 2952/ALD | 24/01/2023 | 24/04/2023 | NIRANJAN KIRTANIA | 0.7 | 0 | 0 | 0
22 | ALIPURDUAR |  | Alipurduar Division | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Continuation for the work of Hiring of Additional Diesel Vehicle Maxi Cab(At least 7 seater ) for inspection and monitoring of Jal Jeevan Mission (JJM) works under Alipurduar Division, P.H.E. Dte.(from 01/02/2023 to 30/04/2023) | HQ-A.E |  | ORD/000567/2022-2023 | 2953/ALD | 24/01/2023 | 24/04/2023 | NIRANJAN KIRTANIA | 0.5 | 0 | 0 | 0
23 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Supply, delivery, installation, commissioning and trial run of electro-mechanical components along with Cu wound line voltage corrector for Rejuvenation of DIMA T.G water supply scheme, TW no III under NMD-II, PHE Dte 106. APD. |  |  | ORD/001076/2023-2024 | 2766/NMD-II | 04/10/2023 | 03/11/2023 | ASHWIRBAD WOOD CRAFT | 10.68 | 0 | 0 | 0
24 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Barovisa Water Supply Scheme | SM/05155 | Augmentation | Supply and Delivery of Standby Submersible Pump for attending breakdown maintenance at Augmentation of Barovisa W/S Scheme, in the Dist of Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000976/2023-2024 | 143/AMSD | 05/07/2023 | 15/07/2023 | MUSTAFI CONCERN | 0.82 | 0 | 0 | 100
Total | [13 empty] | 185.62 | 18.56 | 10