## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | New | Supply, delivery of Standby Submersible pumping Machinery for Emergency Breakdown at Pump House No-II Under Jayanti TG Water Supply Scheme under NMD-II,PHE Dte,Dist-Alipurduar. |  |  | ORD/000857/2020-2021 | 691/AMSD | 03/12/2020 | 13/12/2020 | B.B CONCERNED | 0.5 | 0 | 0 | 0
2 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | New | Supply and Delivery of Calcium Hypochlorite[Ca(Ocl)2] granules at different PWSS under Kumargram Block in the District of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000533/2020-2021 | 1317/NMD-II | 29/12/2020 | 18/01/2021 | SARKAR ELECTRIC | 1.79 | 0 | 0 | 0
3 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | New | Supply and Delivery of Calcium Hypochlorite[Ca(Ocl)2] granules at different PWSS under Kumargram Block in the District of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000531/2020-2021 | 1316/NMD-II | 29/12/2020 | 18/01/2021 | SUMON ELECTRICAL | 1.79 | 0 | 0 | 0
4 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | New | Withdrawing 7.5 HP capacity submersible pumpset and lowering same set after necessary repairing and overhauling at T.W.No-II, under Jayanti TG W/S scheme ,in the dist. Alipurduar , AMSD ,PHE Dte. |  |  | ORD/000780/2020-2021 | 766/AMSD | 28/12/2020 | 07/01/2021 | PRAGATI CONSTRUCTION COMPANY | 0.4 | 0 | 0 | 0
5 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | New | quotation for New service Connection at Jayanti TG TW-iv, Application No.-4002557307 |  |  | VCH/001111/2020-2021 |  | 06/10/2020 | 06/10/2020 | WBSEDCL | 1.15 | 0 | 0 | 0
6 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | New | quotation for New service Connection at Jayanti TG TW-iii, Application No.-4002560908 |  |  | VCH/001110/2020-2021 |  | 06/10/2020 | 06/10/2020 | WBSEDCL | 1.15 | 0 | 0 | 0
7 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | New | Operation and Guarding of Pumping machinery at Pump House No. IV, Under JAYANTI T.G W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000695/2021-2022 | 1222/NMD-II | 28/10/2021 | 28/07/2022 | DEY ENTERPRISE (BALLY) | 2.22 | 0 | 0 | 0
8 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | New | Operation and Guarding of Pumping machinery at Pump House No. III , Under JAYANTI T.G W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000696/2021-2022 | 1223/NMD-II | 28/10/2021 | 28/07/2022 | INDRANI ENTERPRISE | 2.22 | 0 | 0 | 0
9 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at different PWSS under Kumargram block in the dist. of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000520/2021-2022 | 1076/NMD-II | 10/09/2021 | 30/09/2021 | M/S P.P ELECTRICALS | 3.58 | 0 | 0 | 0
10 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | New | Operation and Guarding of Pumping machinery at Pump House No. I under JAYANTI TG W/S Scheme. In the dist. Of ALIPURDUAR |  |  | ORD/000491/2021-2022 | 753/NMD-II | 08/07/2021 | 08/07/2022 | THE BANERJEE CONCERN | 2.97 | 0 | 0 | 0
11 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under JAYANTI TG W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000339/2021-2022 | 706/NMD-II | 08/07/2021 | 08/07/2022 | CHOWDHURY AND BASU ENTERPRISE | 2.97 | 0 | 0 | 0
12 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at Barovisa, Radharani etc under Kumargram & Kalchini block in the dist. of Alipurduar¿ |  |  | ORD/000702/2021-2022 | 1313/NMD-II | 03/12/2021 | 18/12/2021 | DIPA CHHETRI | 1.29 | 0 | 0 | 0
13 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | New | Electro Mechanical works at Jayanti piped w/s scheme in the dist. Alipurduar , under NMD-II ,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000054/2023-2024 | 100/AMSD | 12/06/2023 | 02/07/2023 | MUSTAFI CONCERN | 2.64 | 2.64 | 100 | 100
Total | [13 empty] | 24.68 | 2.64 | 10.71