## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | New | Operation and Guarding of Pumping machinery at Pump House No. IV, Under JAYANTI T.G W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000695/2021-2022 | 1222/NMD-II | 28/10/2021 | 28/07/2022 | DEY ENTERPRISE (BALLY) | 2.22 | 0 | 0 | 0
2 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | New | Operation and Guarding of Pumping machinery at Pump House No. III , Under JAYANTI T.G W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000696/2021-2022 | 1223/NMD-II | 28/10/2021 | 28/07/2022 | INDRANI ENTERPRISE | 2.22 | 0 | 0 | 0
3 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | New | Supply, delivery of Standby Submersible pumping Machinery for Emergency Breakdown at Pump House No-II Under Jayanti TG Water Supply Scheme under NMD-II,PHE Dte,Dist-Alipurduar. |  |  | ORD/000857/2020-2021 | 691/AMSD | 03/12/2020 | 13/12/2020 | B.B CONCERNED | 0.5 | 0 | 0 | 0
4 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | New | Supply and Delivery of Calcium Hypochlorite[Ca(Ocl)2] granules at different PWSS under Kumargram Block in the District of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000531/2020-2021 | 1316/NMD-II | 29/12/2020 | 18/01/2021 | SUMON ELECTRICAL | 1.79 | 0 | 0 | 0
5 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | New | Supply and Delivery of Calcium Hypochlorite[Ca(Ocl)2] granules at different PWSS under Kumargram Block in the District of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000533/2020-2021 | 1317/NMD-II | 29/12/2020 | 18/01/2021 | SARKAR ELECTRIC | 1.79 | 0 | 0 | 0
6 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | New | Withdrawing 7.5 HP capacity submersible pumpset and lowering same set after necessary repairing and overhauling at T.W.No-II, under Jayanti TG W/S scheme ,in the dist. Alipurduar , AMSD ,PHE Dte. |  |  | ORD/000780/2020-2021 | 766/AMSD | 28/12/2020 | 07/01/2021 | PRAGATI CONSTRUCTION COMPANY | 0.4 | 0 | 0 | 0
7 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at different PWSS under Kumargram block in the dist. of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000520/2021-2022 | 1076/NMD-II | 10/09/2021 | 30/09/2021 | M/S P.P ELECTRICALS | 3.58 | 0 | 0 | 0
8 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | New | Operation and Guarding of Pumping machinery at Pump House No. I under JAYANTI TG W/S Scheme. In the dist. Of ALIPURDUAR |  |  | ORD/000491/2021-2022 | 753/NMD-II | 08/07/2021 | 08/07/2022 | THE BANERJEE CONCERN | 2.97 | 0 | 0 | 0
9 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under JAYANTI TG W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000339/2021-2022 | 706/NMD-II | 08/07/2021 | 08/07/2022 | CHOWDHURY AND BASU ENTERPRISE | 2.97 | 0 | 0 | 0
10 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at Barovisa, Radharani etc under Kumargram & Kalchini block in the dist. of Alipurduar¿ |  |  | ORD/000702/2021-2022 | 1313/NMD-II | 03/12/2021 | 18/12/2021 | DIPA CHHETRI | 1.29 | 0 | 0 | 0
11 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | New | Electro Mechanical works at Jayanti piped w/s scheme in the dist. Alipurduar , under NMD-II ,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000054/2023-2024 | 100/AMSD | 12/06/2023 | 02/07/2023 | MUSTAFI CONCERN | 2.64 | 0 | 0 | 100
12 | ALIPURDUAR | Kumargram | Jalpaiguri Division | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | New | Jayanti TG |  |  | VCH/001052/2018-2019 | 1023 | 01/02/2019 |  | EXECUTIVE ENGINEER ALIPURDUAR DIVISION P.H.E. DTE | 17.37 | 0 | 0 | 0
13 | ALIPURDUAR | Kumargram | Northern Mechanical | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | New | Certified that, the marked schemes vide Sl. No. 1-4, 9-11, 14, 16, 22, 29-31, 33, 36, 38, 44, 45, 50, 53, 55, 56, 65, 71, 73, 80-86, 89-92, 94, 103, 107, 108, 110-112, 134, 135, 141-143, 152, 154, 156, 158, 159, 161-163, 167, 168, 174-187, 202-210, 214, 222-229, 243, 266, 267, 277, 278, 287, 294, 300, 305, 317-320, 331, 332, 335-337, 340-342, 348, 349, 352, 353 comes under the jurisdiction of Northern Mechanical Division-II, PHE Dte. and which accured to Rs 55,50,591.00/- (Rupees fifty five lakh fifty thousand five hundred ninety one only) out of total balance amount Rs 6,13,62,046.94/- (Rupees six crore thirteen lakh sixty two thousand forty six and ninety four paise only) to be transferred at the Deposit Account of Northern Mechanical Division-II, PHE Dte. (Operator ID - 71 under Alipurduar Treasury) from the Deposit Account of Northern Mechanical Division, PHE Dte. (Operator ID - 69 under Siliguri Treasury-I) through inter treasury transfer module of IFMS. |  |  | VCH/000387/2019-2020 | 94/W/19-20 | 12/06/2019 |  | NORTHERN MECHANICAL DIVISION II, P.H.E. DTE. | 55.51 | 0 | 0 | 0
14 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | New | quotation for New service Connection at Jayanti TG TW-iii, Application No.-4002560908 |  |  | VCH/001110/2020-2021 | null | 06/10/2020 |  | WBSEDCL | 1.15 | 0 | 0 | 0
15 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | New | quotation for New service Connection at Jayanti TG TW-iv, Application No.-4002557307 |  |  | VCH/001111/2020-2021 | null | 06/10/2020 |  | WBSEDCL | 1.15 | 0 | 0 | 0
16 | ALIPURDUAR | Kumargram | Northern Mechanical | Jayanti Tea Garden Piped Water Supply Scheme | SM/05187 | New | Consolidated Supply Bills |  |  | VCH/001044/2018-2019 | 1219/W/18-19 | 17/03/2019 |  | CHOWDHURY & BASU ENTERPRISE | 2.81 | 0 | 0 | 0
Total | [13 empty] | 100.37 | 0 | 0