## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Dima Tea Garden Piped Water Supply Scheme | SM/05189 | New | Supply, delivery of Electro Mechanical components at DIMA TEA GARDEN Water Supply Scheme IN THE Dist OF Alipurduar under NMD-II,PHE.Dte. |  |  | ORD/000576/2020-2021 | 1458/NMD-II | 02/02/2021 | 04/03/2021 | TALUKDAR ENTERPRISE | 8.42 | 0 | 0 | 0
2 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Dima Tea Garden Piped Water Supply Scheme | SM/05189 | New | Operation and Guarding of Pumping machinery at Pump House No. I under DIMA TG W/S Scheme. In the dist. Of ALIPURDUAR |  |  | ORD/000507/2021-2022 | 761/NMD-II | 08/07/2021 | 08/07/2022 | SUBODH KUMAR BANIK | 2.97 | 0 | 0 | 0
3 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Dima Tea Garden Piped Water Supply Scheme | SM/05189 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at different PWSS under Kalchini block in the dist. of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000518/2021-2022 | 1071/NMD-II | 10/09/2021 | 30/09/2021 | R.K ENTERPRISE | 1.85 | 0 | 0 | 0
4 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Dima Tea Garden Piped Water Supply Scheme | SM/05189 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under DIMA TG W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000325/2021-2022 | 692/NMD-II | 07/07/2021 | 07/07/2022 | BONANZA ENTERPRISE | 2.97 | 0 | 0 | 0
5 | ALIPURDUAR | Kalchini | Alipurduar Division | Dima Tea Garden Piped Water Supply Scheme | SM/05189 | New | Construction of approach road & car parking area with paver block & chequered tiles at Jainty WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division | Alipurduar Sub Division,RWS Alipurduar - I Block | ORD/000331/2021-2022 | 2107/ALD | 05/01/2022 | 04/02/2022 | DAS ENTERPRISE | 5.02 | 0 | 0 | 77
6 | ALIPURDUAR | Kalchini | Jalpaiguri Division | Dima Tea Garden Piped Water Supply Scheme | SM/05189 | New | DIMA |  |  | VCH/000470/2018-2019 | 543 | 19/11/2018 |  | M/S.ARATI CONSTRUCTION | 1.05 | 0 | 0 | 0
7 | ALIPURDUAR | Kalchini | Northern Mechanical | Dima Tea Garden Piped Water Supply Scheme | SM/05189 | New | Consolidated Supply & delivery Bills |  |  | VCH/001057/2018-2019 | 1241/W/18-19 | 19/03/2019 |  | ALPHA ENTERPRISE | 3.41 | 0 | 0 | 0
8 | ALIPURDUAR | Kalchini | Jalpaiguri Division | Dima Tea Garden Piped Water Supply Scheme | SM/05189 | New | jainty wss |  |  | VCH/000877/2018-2019 | 993 | 01/02/2019 |  | TAPASH KUMAR BHOWMICK | 0.93 | 0 | 0 | 0
9 | ALIPURDUAR | Kalchini | Jalpaiguri Division | Dima Tea Garden Piped Water Supply Scheme | SM/05189 | New | dima |  |  | VCH/001053/2018-2019 | 1023 | 01/02/2019 |  | EXECUTIVE ENGINEER ALIPURDUAR DIVISION P.H.E. DTE | 18.23 | 0 | 0 | 0
10 | ALIPURDUAR | Kalchini | Jalpaiguri Division | Dima Tea Garden Piped Water Supply Scheme | SM/05189 | New | dima |  |  | VCH/001053/2018-2019 | 1023 | 01/02/2019 |  | EXECUTIVE ENGINEER ALIPURDUAR DIVISION P.H.E. DTE | 18.23 | 0 | 0 | 0
11 | ALIPURDUAR | Kalchini | Northern Mechanical | Dima Tea Garden Piped Water Supply Scheme | SM/05189 | New | Certified that, the marked schemes vide Sl. No. 1-4, 9-11, 14, 16, 22, 29-31, 33, 36, 38, 44, 45, 50, 53, 55, 56, 65, 71, 73, 80-86, 89-92, 94, 103, 107, 108, 110-112, 134, 135, 141-143, 152, 154, 156, 158, 159, 161-163, 167, 168, 174-187, 202-210, 214, 222-229, 243, 266, 267, 277, 278, 287, 294, 300, 305, 317-320, 331, 332, 335-337, 340-342, 348, 349, 352, 353 comes under the jurisdiction of Northern Mechanical Division-II, PHE Dte. and which accured to Rs 55,50,591.00/- (Rupees fifty five lakh fifty thousand five hundred ninety one only) out of total balance amount Rs 6,13,62,046.94/- (Rupees six crore thirteen lakh sixty two thousand forty six and ninety four paise only) to be transferred at the Deposit Account of Northern Mechanical Division-II, PHE Dte. (Operator ID - 71 under Alipurduar Treasury) from the Deposit Account of Northern Mechanical Division, PHE Dte. (Operator ID - 69 under Siliguri Treasury-I) through inter treasury transfer module of IFMS. |  |  | VCH/000387/2019-2020 | 94/W/19-20 | 12/06/2019 |  | NORTHERN MECHANICAL DIVISION II, P.H.E. DTE. | 55.51 | 0 | 0 | 0
12 | ALIPURDUAR | Kalchini | Alipurduar Division | Dima Tea Garden Piped Water Supply Scheme | SM/05189 | New | Laying of DI Pipe line and others misc. works at Jateswar PWSS under Alipurduar Division , PHE Dte. |  |  | VCH/000741/2020-2021 | 395/20-21 | 11/02/2021 |  | SREE MAA CONSTRUCTION & CO. | 3.5 | 0 | 0 | 0
Total | [13 empty] | 122.08 | 0 | 0