## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Dima Tea Garden Piped Water Supply Scheme | SM/05189 | New | Supply, delivery of Electro Mechanical components at DIMA TEA GARDEN Water Supply Scheme IN THE Dist OF Alipurduar under NMD-II,PHE.Dte. |  |  | ORD/000576/2020-2021 | 1458/NMD-II | 02/02/2021 | 04/03/2021 | TALUKDAR ENTERPRISE | 8.42 | 0 | 0 | 0
2 | ALIPURDUAR | Kalchini | Alipurduar Division | Dima Tea Garden Piped Water Supply Scheme | SM/05189 | New | Laying of DI Pipe line and others misc. works at Jateswar PWSS under Alipurduar Division , PHE Dte. |  |  | VCH/000741/2020-2021 | 395/20-21 | 11/02/2021 | 11/02/2021 | SREE MAA CONSTRUCTION & CO. | 3.5 | 0 | 0 | 0
3 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Dima Tea Garden Piped Water Supply Scheme | SM/05189 | New | Operation and Guarding of Pumping machinery at Pump House No. I under DIMA TG W/S Scheme. In the dist. Of ALIPURDUAR |  |  | ORD/000507/2021-2022 | 761/NMD-II | 08/07/2021 | 08/07/2022 | SUBODH KUMAR BANIK | 2.97 | 0 | 0 | 0
4 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Dima Tea Garden Piped Water Supply Scheme | SM/05189 | New | Operation and Guarding of Pumping machinery at Pump House No. II , Under DIMA TG W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000325/2021-2022 | 692/NMD-II | 07/07/2021 | 07/07/2022 | BONANZA ENTERPRISE | 2.97 | 0 | 0 | 0
5 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Dima Tea Garden Piped Water Supply Scheme | SM/05189 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at different PWSS under Kalchini block in the dist. of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000518/2021-2022 | 1071/NMD-II | 10/09/2021 | 30/09/2021 | R.K ENTERPRISE | 1.85 | 0 | 0 | 0
6 | ALIPURDUAR | Kalchini | Alipurduar Division | Dima Tea Garden Piped Water Supply Scheme | SM/05189 | New | Construction of approach road & car parking area with paver block & chequered tiles at Jainty WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division | Alipurduar Sub Division,RWS Alipurduar - I Block | ORD/000331/2021-2022 | 2107/ALD | 05/01/2022 | 04/02/2022 | DAS ENTERPRISE | 5.02 | 1.5 | 29.9 | 77
7 | ALIPURDUAR | Kalchini | Alipurduar Division | Dima Tea Garden Piped Water Supply Scheme | SM/05189 | New | Repairing of UPVC pipeline, ferrule and other allied works for Dima TG under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kumargram Block | ORD/000168/2025-2026 | 1776/ALD | 18/08/2025 | 02/10/2025 | TAPASH DAS | 5.08 | 0 | 0 | 0
Total | [13 empty] | 29.8 | 1.5 | 5.03