## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Dhaolajhora Tea Garden Piped Water Supply Scheme | SM/05197 | New | Supply and Delivery of Calcium Hypochlorite[Ca(Ocl)2] granules at Different PWSS under Alipurduar-I & II Block in the Dist of Alipurduar under Northern Mechanical Division-II,PHE Dte. | Assistant Engineer, Cooch-Behar Mechanical Sub-Division | Junior Engineer 4, Cooch-Behar Mechanical Sub-Division, | ORD/000395/2021-2022 | 863/NMD-II | 28/07/2021 | 27/08/2021 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 3.58 | 0 | 0 | 0
2 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Dhaolajhora Tea Garden Piped Water Supply Scheme | SM/05197 | New | Operation and Guarding of Pumping machinery at Pump House No. I , Under DHAOLAJHORA TG W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000354/2021-2022 | 721/NMD-II | 08/07/2021 | 08/07/2022 | S.P ENTERPRISE (SLG) | 2.97 | 0 | 0 | 0
3 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Dhaolajhora Tea Garden Piped Water Supply Scheme | SM/05197 | New | Supply, delivery and installation of standby automatically controlled hydrualic diaphragm type Chlorinator for accurate dosing of Chlorine solution at differernt PWSS under Alipurduar-I Block in the district of Alipurduar under NMD-II ,P.H.E Dte. |  |  | ORD/000597/2021-2022 | 1042/NMD-II | 03/09/2021 | 23/09/2021 | MUSTAFI CONCERN | 3.5 | 0 | 0 | 0
4 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Dhaolajhora Tea Garden Piped Water Supply Scheme | SM/05197 | New | Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at Samuktala,Dholajhora T.G, Purba Chepani etc under Alipurduar block in the dist. of Alipurduar under NMD-II P.H E Dte |  |  | ORD/000615/2021-2022 | 1111/NMD-II | 20/09/2021 | 20/10/2021 | COMBINE ENTERPRISES | 3.01 | 0 | 0 | 0
5 | ALIPURDUAR | Alipurduar-II | Alipurduar Division | Dhaolajhora Tea Garden Piped Water Supply Scheme | SM/05197 | New | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Alipurduar - I Block,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 25/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 8.65 | 1.72 | 100
6 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Dhaolajhora Tea Garden Piped Water Supply Scheme | SM/05197 | New | Supply, delivery and installation of standby automatically controlled hydrualic diaphragm type Chlorinator for accurate dosing of Chlorine solution at P/H No.I&II under Satkura and Salmara P/H No.I PWSS in the district of Coochbehar under NMD-II ,P.H.E Dte. |  |  | ORD/000569/2021-2022 | 1014/NMD-II | 27/08/2021 | 16/09/2021 | SUNLIT | 2.6 | 0.02 | 0.64 | 0
7 | ALIPURDUAR | Alipurduar-II | Northern Mechanical Division II | Dhaolajhora Tea Garden Piped Water Supply Scheme | SM/05197 | New | Supply, delivery of Electro mechanical components at Dholajhora T.G Water Supply Scheme, in the dist of ALIPURDUAR under NMD-II, PHE Dte. Alipurduar. |  |  | ORD/000737/2021-2022 | 60/NMD-II | 21/01/2022 | 20/02/2022 | SUMON ELECTRICAL | 8.67 | 8.67 | 100 | 0
Total | [13 empty] | 526.9 | 17.34 | 3.29