## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Alipurduar Division | Improvement of Dakshin Sonapur Water Supply Scheme by construction of Over Head Reservoir. | SM/05243 | Augmentation | River crossing for laying DI pipe line, Extension and replacement of damaged pipeline and providing FHTC at Sonapur and surrounding area of Sonapur PWSS. Alipurduar-I Block under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000357/2021-2022 | 2236/ALD | 14/01/2022 | 15/03/2022 | M/S SIBU DEY AND CO | 38.07 | 0 | 0 | 91
2 | ALIPURDUAR |  | Alipurduar Division | Improvement of Dakshin Sonapur Water Supply Scheme by construction of Over Head Reservoir. | SM/05243 | Augmentation | Extension and replacement of damaged pipeline and providing FHTC at Uttar Kashigram area under Sonapur PWSS under Alipurduar Division, Division, PHE Dte. | Alipurduar RWS | JUNIOR ENGINEER | ORD/000367/2021-2022 | 2295/ALD | 24/01/2022 | 04/03/2026 | NARENDRA BHADANI. | 45.29 | 0 | 0 | 18
3 | ALIPURDUAR |  | Alipurduar Division | Improvement of Dakshin Sonapur Water Supply Scheme by construction of Over Head Reservoir. | SM/05243 | Augmentation | Extension and replacement of damaged pipeline and providing FHTC at Dakshin Kashigram area under Sonapur PWSS under Alipurduar Division, Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000366/2021-2022 | 2294/ALD | 24/01/2022 | 25/03/2022 | SASANKA ROY | 50.15 | 0 | 0 | 18
Total | [13 empty] | 133.52 | 0 | 0