## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply delivery and Installation of 40 KVA Servo Motor Operated Copper wound line voltage corrector for Additional Tubewell No-II under Zone I Proposed for Alternative Source under Piped Water Supply Scheme for Jaygaon Development Area under NMD-II,PHE Dte,Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000055/2020-2021 | 1186/NMD-II | 18/11/2020 | 18/12/2020 | RMD TRADING | 4.71 | 3.68 | 78.1 | 0
2 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply delivery and Installation of 40 KVA Servo Motor Operated Copper wound line voltage corrector for Additional Tubewell No-II under Zone II Proposed for Alternative Source under Piped Water Supply Scheme for Jaygaon Development Area under NMD-II,PHE Dte,Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000057/2020-2021 | 1202/NMD-II | 24/11/2020 | 24/12/2020 | MITRA ENTERPRISE | 4.69 | 3.67 | 78.14 | 0
3 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply, Installation & commissioning of Gaseous Chlorination arrangement of capacity 0 - 1 kg/hr for piped water supply scheme for Jaigaon Development Area (JDA) based on Sub Surface Water source of River Torsa, Dist. Alipurduar. (Zone-II OHR site) | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000028/2020-2021 | 1086/NMD-II | 05/10/2020 | 03/01/2021 | ALPHA ENTERPRISE | 23.49 | 18.15 | 77.25 | 0
4 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply, Installation & commissioning of Gaseous Chlorination arrangement of capacity 0 - 1 kg/hr for piped water supply scheme for Jaigaon Development Area (JDA) based on Sub Surface Water source of River Torsa, Dist. Alipurduar. (Zone-I OHR site) | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000029/2020-2021 | 1087/NMD-II | 05/10/2020 | 03/01/2021 | CHOWDHURY AND BASU ENTERPRISE | 23.5 | 18.15 | 77.26 | 0
5 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply, Installation & commissioning of Gaseous Chlorination arrangement of capacity 0 - 1 kg/hr for piped water supply scheme for Jaigaon Development Area (JDA) based on Sub Surface Water source of River Torsa, Dist. Alipurduar. (Zone-IV OHR site) | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000031/2020-2021 | 1090/NMD-II | 05/10/2020 | 03/01/2021 | BOSE & CHATTERJEE INDUSTRIES | 23.5 | 7.88 | 33.54 | 0
6 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply delivery and Installation of 40 KVA Servo Motor Operated Copper wound line voltage corrector for Additional Tubewell No-I under Zone I Proposed for Alternative Source under Piped Water Supply Scheme for Jaygaon Development Area under NMD-II,PHE Dte, Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000054/2020-2021 | 1184/NMD-II | 18/11/2020 | 18/12/2020 | B.B CONCERNED | 4.7 | 4.19 | 89.21 | 0
7 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply delivery and Installation of 40 KVA Servo Motor Operated Copper wound line voltage corrector for Additional Tubewell No-I under Zone II Proposed for Alternative Source under Piped Water Supply Scheme for Jaygaon Development Area under NMD-II,PHE Dte, Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000056/2020-2021 | 1196/NMD-II | 23/11/2020 | 23/12/2020 | SARKAR ELECTRIC | 4.7 | 3.67 | 78.06 | 0
8 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Paper advertising bill. Invoice no. GA/08/0078/19-20 Date: 08/08/2019 |  |  | VCH/001689/2019-2020 | 143/19-20 | 19/02/2020 | 19/02/2020 | GENESIS ADVERTISING PVT.LTD. | 0.32 | 0 | 0 | 0
9 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Publication of advertisement in newspaper (Invoice no. GA/08/1037/19-20 ) |  |  | VCH/001679/2019-2020 | 143/19-20 | 19/02/2020 | 19/02/2020 | GENESIS ADVERTISING PVT.LTD. | 0.03 | 0 | 0 | 0
10 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Jaigaon P.H.C Gopimohan Hospital Compound (Application Id: 4002445132) |  |  | VCH/000616/2019-2020 | 97/19-20 | 06/01/2020 | 06/01/2020 | WBSEDCL | 1.35 | 0 | 0 | 0
11 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Paper advertising bill. Invoice no. K02P0521 |  |  | VCH/001683/2019-2020 | 143/19-20 | 19/02/2020 | 19/02/2020 | CRAYONS ADVERTISING PVT. LTD. | 0.01 | 0 | 0 | 0
12 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Paper advertising bill. Invoice no. GA/10/0350/19-20 |  |  | VCH/001682/2019-2020 | 143/19-20 | 19/02/2020 | 19/02/2020 | GENESIS ADVERTISING PVT.LTD. | 0.04 | 0 | 0 | 0
13 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Paper advertising bill. Invoice no. GA/06/0849/19-20 Date: 20/06/2019 |  |  | VCH/001686/2019-2020 | 143/19-20 | 19/02/2020 | 19/02/2020 | GENESIS ADVERTISING PVT.LTD. | 0.04 | 0 | 0 | 0
14 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | HIRING OF VEHICLE FOR TH MONTH APRIL'18 TO JUNE'18. |  |  | VCH/000620/2019-2020 | 264/19-20 | 17/03/2020 | 17/03/2020 | PRASENJIT DEY SARKAR | 0.65 | 0 | 0 | 0
15 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Shifting of LTOH pole with allied works at Toribari IRO. |  |  | VCH/000201/2020-2021 | 47/20-21 | 15/06/2020 | 15/06/2020 | WBSEDCL | 0.23 | 0 | 0 | 0
16 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | paper advertising bill. Invoice no. GA/08/0558/19-20 Date.25/11/2019 |  |  | VCH/001680/2019-2020 | 143/19-20 | 19/02/2020 | 19/02/2020 | GENESIS ADVERTISING PVT.LTD. | 0.04 | 0 | 0 | 0
17 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Paper advertising bill. Invoice no. K06P0092 Date: 13/06/2019 |  |  | VCH/001684/2019-2020 | 143/19-20 | 19/02/2020 | 19/02/2020 | CRAYONS ADVERTISING PVT. LTD. | 0.01 | 0 | 0 | 0
18 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Paper advertising bill. Invoice no. GA/07/0028/19-20 Date: 1/07/2019 |  |  | VCH/001688/2019-2020 | 143/19-20 | 19/02/2020 | 19/02/2020 | GENESIS ADVERTISING PVT.LTD. | 0.09 | 0 | 0 | 0
19 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Publication of advertisement in newspaper (Invoice no. GA/11/10557/19-20 ) |  |  | VCH/001681/2019-2020 | 143/19-20 | 19/02/2020 | 19/02/2020 | GENESIS ADVERTISING PVT.LTD. | 0.1 | 0 | 0 | 0
20 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Paper advertising bill. Invoice no. K01P0391 Date: 28/02/2019 |  |  | VCH/001685/2019-2020 | 143/19-20 | 19/02/2020 | 19/02/2020 | CRAYONS ADVERTISING PVT. LTD. | 0.01 | 0 | 0 | 0
21 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Paper advertising bill. Invoice no. GA/JAN/0949/18-19 Date: 30/01/2019 |  |  | VCH/001687/2019-2020 | 143/19-20 | 19/02/2020 | 19/02/2020 | GENESIS ADVERTISING PVT.LTD. | 0.04 | 0 | 0 | 0
22 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Construction of gasious chlorine room for Zone-II of JDA water supply scheme Alipurduar Division PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000278/2020-2021 | 1328/ALD | 11/01/2021 | 11/04/2021 | TAPASH DAS | 5 | 0 | 0 | 0
23 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply and Delivery of Al. armoured cable at JDA Piped water supply scheme in the dist. Alipurduar under, AMSD,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000600/2020-2021 | 883/AMSD | 08/02/2021 | 18/02/2021 | B.B CONCERNED | 0.74 | 0.74 | 100 | 0
24 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Quotation for earnest money of JDA |  |  | VCH/001461/2021-2022 | BP-2021-22-17 | 28/10/2021 | 28/10/2021 | WBSEDCL | 0.05 | 0 | 0 | 0
25 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Quotation for Earnest money deposition for bulk power supply for yours proposed premises at JDA piped water supply scheme , JAIGAON for an ultimate contract demand of 630 KVA. |  |  | VCH/000576/2021-2022 |  | 12/08/2021 | 12/08/2021 | WBSEDCL | 0.05 | 0 | 0 | 0
26 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | New connection of WBSEDCL of JAIGAON TARIBARI -I, Application ID. 4002657896, Rf. 402584079 |  |  | VCH/001459/2021-2022 | BP-2021-22-15 | 28/10/2021 | 28/10/2021 | WBSEDCL | 1.63 | 0 | 0 | 0
27 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Quotation for new service connection at Khokla basty, new reservoir, jaigaon Z-III(A) T.W No. I . Application No. 4002614695 |  |  | VCH/001252/2020-2021 | 196/20-21 | 22/12/2020 | 22/12/2020 | WBSEDCL | 1.29 | 0 | 0 | 0
28 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | quotation for New service Connection at Jayanti TG TW-iii, Application No.-4002560908 |  |  | VCH/002075/2020-2021 | 171/20-21 | 27/11/2020 | 27/11/2020 | WBSEDCL | 1.15 | 0 | 0 | 0
29 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Quotation for new service connection at Dalsingpara T.G jaigaon Z-VA T.W No. III . Application No. 400260347 |  |  | VCH/001253/2020-2021 | 196/20-21 | 22/12/2020 | 22/12/2020 | WBSEDCL | 1.35 | 0 | 0 | 0
30 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | New connection of JAIGAON TARIBARI- II, Application no. 4002657902, |  |  | VCH/001460/2021-2022 | BP-2021-22-16 | 28/10/2021 | 28/10/2021 | WBSEDCL | 1.63 | 0 | 0 | 0
31 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Quotation for new service connection at jda Z-II,TW NO. II application no. 4002657902 |  |  | VCH/001008/2021-2022 |  | 07/10/2021 | 07/10/2021 | WBSEDCL | 1.63 | 0 | 0 | 0
32 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Paper advertise bill. Bill no.182 Date: 07/03/2020 |  |  | VCH/001680/2020-2021 | 189/20-21 | 16/12/2020 | 16/12/2020 | RAMEN DEY | 0.16 | 0 | 0 | 0
33 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Quotation for new service connection at JDA, Z-I, TW-I |  |  | VCH/001390/2021-2022 |  | 23/11/2021 | 23/11/2021 | WBSEDCL | 1.49 | 0 | 0 | 0
34 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | New Service connection at Z-I, TW-I JDA (WBSEDCL) |  |  | VCH/001548/2021-2022 |  | 22/12/2021 | 22/12/2021 | WBSEDCL | 1.49 | 0 | 0 | 0
35 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply of HSD for different vehicle under Alipurduar Division |  |  | VCH/000369/2021-2022 | 174/21-22 | 02/08/2021 | 02/08/2021 | SHIVAM SERVICE STATION | 0.63 | 0 | 0 | 0
36 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Paper advertise bill. Bill no.188 Date: 10/03/2020 |  |  | VCH/001679/2020-2021 | 189/20-21 | 16/12/2020 | 16/12/2020 | RAMEN DEY | 0.17 | 0 | 0 | 0
37 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | quotation for New service Connection at Jayanti TG TW-iii, Application No.-4002557307 |  |  | VCH/002076/2020-2021 | 171/20-21 | 27/11/2020 | 27/11/2020 | WBSEDCL | 1.15 | 0 | 0 | 0
38 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Quotation for new service connection jda Tw No.I Z-I |  |  | VCH/001009/2021-2022 |  | 07/10/2021 | 07/10/2021 | WBSEDCL | 1.63 | 0 | 0 | 0
39 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Laying of Distribution Line (by using metal Pipes) of Zone-II for JDA (Jaigaon Development Authority) Area Water Supply Scheme under Alipurduar District. | HQ-A.E | RWS Kalchini Block | ORD/000119/2020-2021 | 790/ALD | 01/10/2020 | 28/02/2021 | DILIP MAHATO | 198.88 | 193.05 | 97.07 | 0
40 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Laying of CI/DI/MS Pipe for delivery line, cons. of RCC Pillar with ISMB and balance part of boundary wall of CWR Project Area and earth filling at River Bed site of JDA (JAIGAON DEVELOPMENT AUTHORITY) Area Water Supply Scheme under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000013/2021-2022 | 405/ALD | 17/06/2021 | 17/07/2021 | DILIP MAHATO | 49.78 | 40.26 | 80.89 | 67
41 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Installation of 125mm X 80mm X 90 mtr. Deep TW (Mark-II TW) for fresh drinking water sources by ODEX-115 method of Drilling at different places (03 Different Locations) under JAIGAON PS under Alipurduar Division, PHE Dte. PART-1 | HQ-A.E | RWS Kalchini Block | ORD/000206/2021-2022 | 20/ALD | 05/04/2021 | 20/04/2021 | MAHENDRA CHHETRI | 4.81 | 0 | 0 | 0
42 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Operation and Guarding of Pumping machinery at Pump House No. I, Zone - VA, Under JDA Piped W/S Scheme (Near Football Ground) , in the dist. Of Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000549/2021-2022 | 810/NMD-II | 13/07/2021 | 13/07/2022 | M/S SAJAHAN CHOWDHURY | 2.97 | 0 | 0 | 0
43 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Installation of 125mm X 80mm X 90 mtr. Deep TW (Mark-II TW) for fresh drinking water sources by ODEX-115 method of Drilling at different places (03 Different Locations) under JAIGAON PS under Alipurduar Division, PHE Dte. PART-3 | HQ-A.E | RWS Kalchini Block | ORD/000208/2021-2022 | 22/ALD | 05/04/2021 | 20/04/2021 | MAHENDRA CHHETRI | 4.81 | 0 | 0 | 0
44 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply and delivery at site of 80 mm dia x 3 mtr. Long HDPE Jacketed/SS Strainer, India Mark-II hand pump set,128 mm ID/139 mm OD MSERW fin cut pipe for Jaigaon PS under Alipurduar Division, PHE Dte. (Part-1 | HQ-A.E | RWS Kalchini Block | ORD/000213/2021-2022 | 27/ALD | 05/04/2021 | 20/04/2021 | MAHENDRA CHHETRI | 3.74 | 0 | 0 | 0
45 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply and delivery at site of 80 mm dia x 3 mtr. Long HDPE Jacketed/SS Strainer, India Mark-II hand pump set,128 mm ID/139 mm OD MSERW fin cut pipe for Jaigaon PS under Alipurduar Division, PHE Dte. (Part-2 | HQ-A.E | RWS Kalchini Block | ORD/000214/2021-2022 | 28/ALD | 05/04/2021 | 20/04/2021 | MAHENDRA CHHETRI | 3.74 | 0 | 0 | 0
46 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply and delivery at site of 80 mm dia x 3 mtr. Long HDPE Jacketed/SS Strainer, India Mark-II hand pump set,128 mm ID/139 mm OD MSERW fin cut pipe for Jaigaon PS under Alipurduar Division, PHE Dte. (Part-4 | HQ-A.E | RWS Kalchini Block | ORD/000216/2021-2022 | 30/ALD | 05/04/2021 | 20/04/2021 | MAHENDRA CHHETRI | 3.74 | 0 | 0 | 0
47 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply and delivery at site of 80 mm dia x 3 mtr. Long HDPE Jacketed/SS Strainer, India Mark-II hand pump set,128 mm ID/139 mm OD MSERW fin cut pipe for Jaigaon PS under Alipurduar Division, PHE Dte. (Part-3 | HQ-A.E | RWS Kalchini Block | ORD/000215/2021-2022 | 29/ALD | 05/04/2021 | 20/04/2021 | MAHENDRA CHHETRI | 3.74 | 0 | 0 | 0
48 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Installation of 125mm X 80mm X 90 mtr. Deep TW (Mark-II TW) for fresh drinking water sources by ODEX-115 method of Drilling at different places (03 Different Locations) under JAIGAON PS under Alipurduar Division, PHE Dte. PART-4 | HQ-A.E | RWS Kalchini Block | ORD/000209/2021-2022 | 23/ALD | 05/04/2021 | 20/04/2021 | MAHENDRA CHHETRI | 4.81 | 0 | 0 | 0
49 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Installation of 125mm X 80mm X 90 mtr. Deep TW (Mark-II TW) for fresh drinking water sources by ODEX-115 method of Drilling at different places (03 Different Locations) under JAIGAON PS under Alipurduar Division, PHE Dte. PART-2 | HQ-A.E | RWS Kalchini Block | ORD/000207/2021-2022 | 21/ALD | 05/04/2021 | 20/04/2021 | MAHENDRA CHHETRI | 4.83 | 0 | 0 | 0
50 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Laying of HDPE pipeline and providing FHTC at JDA PWSS Zone-II under JDA PWSS,Kalchini Block under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000324/2021-2022 | 2204/ALD | 11/01/2022 | 12/03/2022 | DILIP MAHATO | 64.64 | 0 | 0 | 0
51 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply & delivery of Fuse unit for JDA piped water supply scheme in the dist. Alipurduar under NMD-II ,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000933/2020-2021 | 813/AMSD | 14/01/2021 | 24/01/2021 | SARKAR ELECTRIC | 0.84 | 0 | 0 | 0
52 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply & delivery of C.I.D.F Bend for JDA piped water supply scheme in the dist. Alipurduar under NMD-II ,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000934/2020-2021 | 821/AMSD | 15/01/2021 | 25/01/2021 | M/S ANJALI ENTERPRISE | 0.64 | 0 | 0 | 0
53 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply and delivery of Standby Submersible pump for JDA piped water supply scheme , Z-IV under NMD-II , Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000847/2021-2022 | 626/AMSD | 03/03/2022 | 18/03/2022 | NUPUR CHANDRA HALDER | 1.09 | 0 | 0 | 0
54 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply and delivery of Standby Submersible pump for JDA piped water supply scheme , Z-II under NMD-II , Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000849/2021-2022 | 628/AMSD | 03/03/2022 | 18/03/2022 | WILFUL UNEMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 1.09 | 0 | 0 | 0
55 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply & delivery of Desktop CPU-AMD Ryzen5 2400, H320 Gigabyte Mother Board, 8GB DDR4 Ram, ATX Cabinet, SMPS 450 Watt,240 GB SSD,1 TB HDD & Epson printer L-1100 for the use at Estimating Section, under Alipurduar Division, P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000244/2022-2023 | 1154/ALD | 02/08/2022 | 09/08/2022 | CYBER NET | 0.99 | 0 | 0 | 0
56 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply & delivery of Desktop CPU-AMD Ryzen5 2400, H320 Gigabyte Mother Board, 8GB DDR4 Ram, ATX Cabinet, SMPS 450 Watt,240 GB SSD,1 TB HDD & Epson printer L-1100 for the use at Birpara Sub-Division under Alipurduar Division, P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000245/2022-2023 | 1155/ALD | 02/08/2022 | 09/08/2022 | CYBER NET | 0.99 | 0 | 0 | 0
57 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Laying of CI/DI pipeline and gap filling of pipeline at JDA PWSS Zone-I under JDA PWSS,Kalchini Block under Alipurduar Division, PHE Dte. (PART-B) | HQ-A.E | RWS Kalchini Block | ORD/000222/2022-2023 | 1112/ALD | 29/07/2022 | 28/08/2022 | M/S SSB CONSTRUCTION CO. | 4.09 | 0 | 0 | 0
58 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Carriage and Arrangement of different dia DI/CI pipe and specials from Jalpaiguri Stackyard to JDA Area WSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000217/2022-2023 | 1107/ALD | 29/07/2022 | 28/08/2022 | DILIP MAHATO | 1.51 | 0 | 0 | 0
59 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Laying of CI/DI pipeline and gap filling of pipeline at JDA PWSS Zone-I under JDA PWSS,Kalchini Block under Alipurduar Division, PHE Dte. (PART-A) | HQ-A.E | RWS Kalchini Block | ORD/000221/2022-2023 | 1111/ALD | 29/07/2022 | 28/08/2022 | M/S SSB CONSTRUCTION CO. | 4.7 | 0 | 0 | 0
60 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Quotation for meter shifting at JAigaon TW No-III Application No- 4002965631 |  |  | VCH/000700/2022-2023 |  | 10/08/2022 | 10/08/2022 | WBSEDCL | 0.09 | 0 | 0 | 0
61 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | WBSEDCL new connection for Jaigaon Gopimohan, Application No. 4002801671 |  |  | VCH/002606/2021-2022 | BP-19/21-22 | 07/02/2022 | 07/02/2022 | WBSEDCL | 1.49 | 0 | 0 | 0
62 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Quotation for meter shifting at P/H no. II under JAIGAON W/SS Application no. 4002965617 |  |  | VCH/001291/2022-2023 | BP-46/22-23 | 12/08/2022 | 12/08/2022 | WBSEDCL | 0.05 | 0 | 0 | 0
63 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Quotation for meter shifting at P/H no. III under JAIGAON W/SS Application no. 4002965631 |  |  | VCH/001292/2022-2023 | BP-47/22-23 | 12/08/2022 | 12/08/2022 | WBSEDCL | 0.09 | 0 | 0 | 0
64 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Providing House connection for DALSINGPARA, JAIGAON DEVLOPMENT AREA ZONE-5A under Alipurduar Division, P.H.E. Dte. |  |  | VCH/000627/2021-2022 |  | 01/10/2021 | 01/10/2021 | AQUEDUCT PLASTICS PVT. LTD. | 40.17 | 0 | 0 | 0
65 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Quotation for new service connection at JDA, Z-I, TW-I |  |  | VCH/001787/2021-2022 |  | 06/01/2022 | 06/01/2022 | WBSEDCL | 1.49 | 0 | 0 | 0
66 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Quotation for meter shifting at JAigaon TW No-II Application No- 4002965617 |  |  | VCH/000702/2022-2023 |  | 10/08/2022 | 10/08/2022 | WBSEDCL | 0.05 | 0 | 0 | 0
67 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply delivery & installation of 40 KVA Servo Motor operated copper wound line voltage corrector at P/H no. IV,Zone IV under JAYGAON DEVELOPMENT PROGRAM. |  |  | ORD/000698/2019-2020 | 1375/NMD-II | 06/03/2020 | 06/03/2020 | M/S P.P ELECTRICALS | 4.71 | 7.36 | 156.25 | 0
68 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Laying of Distribution Line (by using metal Pipes) of Zone-I for JDA (Jaigaon Development Authority) Area Water Supply Scheme under Alipurduar District. | HQ-A.E | RWS Kalchini Block | ORD/000118/2020-2021 | 789/ALD | 01/10/2020 | 28/02/2021 | M/S SSB CONSTRUCTION CO. | 185.6 | 123.55 | 66.57 | 65
69 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Providing House connection for FALAKATA AUG. piped water supply scheme (Falakata-Birpara Road) under Alipuduar Division, P.H.E. Dte. Part-3 | HQ-A.E | RWS Kalchini Block | ORD/000266/2020-2021 | 1257/ALD | 28/12/2020 | 26/02/2021 | BILTU DAS | 43.41 | 0 | 0 | 70
70 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Providing House connection for MADARI ROAD/ PARANGERPAR, FALAKATA AUG. PWSS ZONE-I under Alipuduar Division, P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000365/2020-2021 | 1758/ALD | 19/02/2021 | 20/04/2021 | ALIPURDUAR CO-OPERATIVE LABOUR CONTRUCT & CONSTRUCTION SOCIETY LTD. | 39.97 | 0 | 0 | 63
71 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Providing Functional Household Tap connection (FHTC) in connection with Jaldhara Jal Sapno for Jogendrapur PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000301/2020-2021 | 1381/ALD | 19/01/2021 | 05/03/2021 | ASSOCIATE CONSTRUCTION COMPANY | 15.78 | 0 | 0 | 67
72 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply, Delivery and laying of Al. armoured cable at JDA Piped water supply scheme in the dist. Alipurduar under,AMSD,PHE Dte. |  |  | ORD/000711/2021-2022 | .411/AMSD | 05/10/2021 | 20/10/2021 | B.B CONCERNED | 0.73 | 0 | 0 | 0
73 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna ( for public/Govt. organisations etc. ) at JDA WSS (Zone-II) under Alipurduar Division, PHE Dte. Part-3 | HQ-A.E | RWS Kalchini Block | ORD/000344/2021-2022 | 2137/ALD | 06/01/2022 | 05/02/2022 | D. K. & SONS | 5.02 | 0 | 0 | 65
74 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Laying of different dia. Of HDPE pipeline inclu. Providing FHTC and other works at JDA PWSS Zone-IV under JDA PWSS, Kalchini Block under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000373/2021-2022 | 2373/ALD | 31/01/2022 | 01/04/2022 | AQUEDUCT PLASTICS PVT. LTD. | 55.55 | 0 | 0 | 71
75 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Additional works in connection with supply ,installation and commissioning and trial operation of electromechanical accessories at Jaigaon Development Area water supply scheme in the dist. of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000785/2021-2022 | 0468/AMSD | 23/11/2021 | 03/12/2021 | WEST BENGAL ENGINEERING CO. | 0.56 | 0 | 0 | 0
76 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply and delivery of Standby Submersible pump for JDA piped water supply scheme , Z-III under NMD-II , Alipurduar. |  |  | ORD/000869/2021-2022 | 633/AMSD | 03/03/2022 | 18/03/2022 | DILIP MAHATO | 1.09 | 0 | 0 | 0
77 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply and delivery of Standby Submersible pump for JDA piped water supply scheme , Z- V under NMD-II , Alipurduar. |  |  | ORD/000851/2021-2022 | 630/AMSD | 03/03/2022 | 18/03/2022 | S.P ENTERPRISE (SLG) | 1.09 | 0 | 0 | 0
78 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Preparation of general arrangement drawing with reinforcement details along with design document for construction of Internal Road, Drain, Sub-Station, Chemical House, Guard Room, Laboratory, Pressure Filter and Clear Water Reservoir at Head Work Site under Jaigaon Development Area including its Office Building and Stores under Alipurduar Division P.H.E. Dte. | Alipurduar RWS |  | ORD/000476/2022-2023 | 3239ALD | 28/02/2023 | 30/03/2023 | RRG AND MREPL JV | 6.5 | 0 | 0 | 0
79 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | CONTINUATION ORDER FOR Supply, installation, commissioning and trial operation of Electro Mechanical components for Additional Tube wells of Zone I (2 nos TW) proposed for Alternative source of River Torsa,in the dist of Alipurduar. |  |  | ORD/000796/2022-2023 | 1667/NMD-II | 26/09/2022 | 25/12/2022 | M/S P.P ELECTRICALS | 0.85 | 0 | 0 | 0
80 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Extension of HDPE pipeline (90mm Dia) and providing 80 nos FHTC at Chhetri Line under Dalsingpara within Kalchini Block, Alipurduar Division, PHE Dte. | HQ-A.E |  | ORD/000568/2022-2023 | 3622/ALD | 30/03/2023 | 29/05/2023 | D. K. & SONS | 5.72 | 0 | 0 | 0
81 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply and delivery of Standby Submersible flat cable for JDA piped water supply scheme under NMD-II , Alipurduar. |  |  | ORD/000850/2021-2022 | 0629/AMSD | 03/03/2022 | 18/03/2022 | M/S CHANDRANATH MUKHERJEE | 2.02 | 0 | 0 | 0
82 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna ( for public/Govt. organisations etc. ) at JDA WSS (Zone-II) under Alipurduar Division, PHE Dte. Part-2 | HQ-A.E | RWS Kalchini Block | ORD/000343/2021-2022 | 2136/ALD | 06/01/2022 | 05/02/2022 | D. K. & SONS | 5.02 | 0 | 0 | 67
83 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Providing Power Supply Arrangement at WTP to feed safe drinking water at Zone I & II of Jaigaon Development Area (JDA) water supply scheme under Northern Mechanical Division II,PHE Dte in the district of Alipurduar. |  |  | ORD/001118/2023-2024 | 2864/NMD-II | 17/10/2023 | 14/02/2024 | R.N.S. TRADING | 203.22 | 0 | 0 | 0
84 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply, Installation & commissioning of Gaseous Chlorination arrangement of capacity 0 - 1 kg/hr for piped water supply scheme for Jaigaon Development Area (JDA) based on Sub Surface Water source of River Torsa, Dist. Alipurduar. (Zone-V, Part-A OHR site) | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000030/2020-2021 | 1089/NMD-II | 05/10/2020 | 03/01/2021 | S.P ENTERPRISE (SLG) | 23.5 | 18.15 | 77.24 | 0
85 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply delivery & installation of 40 KVA Servo Motor operated copper wound line voltage corrector at P/H no. III,Zone III under JAYGAON DEVELOPMENT PROGRAM. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000694/2019-2020 | 1374/NMD-II | 06/03/2020 | 06/03/2020 | WEST BENGAL ENGINEERING CO. | 4.71 | 7.35 | 156.24 | 0
86 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply,Installation,Commissioning and trial operation of Electro Mechanical Components for additional Tube well of Zone-III( 6 Nos. T.W) propossed for alternative source under piped water supply scheme for JAIGAON DEVELOPMENT AREA(JDA) based on Sub-Serface water source of River Torsa in the district of Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000784/2019-2020 | 04/NMD | 02/01/2020 | 02/01/2020 | WEST BENGAL ENGINEERING CO. | 39.82 | 39.82 | 100 | 0
87 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Sinking of Big Dia T/Well P/House B/Wall & Rising Main of 3rd T/Well Site at FALAKATA Aug. PWSS under Alipurduar Division PHED. | HQ-A.E | RWS Kalchini Block | ORD/000083/2020-2021 | 655/ALD | 08/09/2020 | 06/01/2021 | BILTU DAS | 22.65 | 0 | 0 | 82
88 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Loop Connention between West Falakata & Barodoba area via Mujnai River Bridge incl interconnection with the existing BHUTNIRGHAT PWSS under FALAKATA Aug. PWSS under Alipurduar Division PHED. | HQ-A.E | RWS Kalchini Block | ORD/000072/2020-2021 | 626/ALD | 03/09/2020 | 01/01/2021 | GOUTAM KUMAR DAS | 26.08 | 0 | 0 | 83
89 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Construction of gasious chlorine room for Zone-VB of JDA water supply scheme Alipurduar Division PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000285/2020-2021 | 1333/ALD | 11/01/2021 | 11/04/2021 | MAHENDRA CHHETRI | 5 | 0 | 0 | 65
90 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Construction of gasious chlorine room for Zone-IV of JDA water supply scheme Alipurduar Division PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000281/2020-2021 | 1331/ALD | 11/01/2021 | 11/04/2021 | MAHENDRA CHHETRI | 5 | 4.03 | 80.55 | 60
91 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Providing House connection for CHOTO SALKUMAR water supply scheme at Falakata Block under Alipuduar Division, P.H.E. Dte. Part-III | Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Kalchini Block | ORD/000218/2020-2021 | 1169/ALD | 15/12/2020 | 13/02/2021 | SASANKA ROY | 29.9 | 0 | 0 | 70
92 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Construction of gasious chlorine room for Zone-IIIB of JDA water supply scheme Alipurduar Division PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000280/2020-2021 | 1330/ALD | 11/01/2021 | 11/04/2021 | MAHENDRA CHHETRI | 5 | 4.03 | 80.69 | 67
93 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Laying of CI/DI/MS Pipe for Rising and delivery line, cons. Of valve chamber and other allied works for Zone-II and III at JDA (Jaigaon Development Authority) Area Water Supply Scheme under Alipurduar District. | HQ-A.E | RWS Kalchini Block | ORD/000229/2021-2022 | 1572/ALD | 22/11/2021 | 21/01/2022 | DILIP MAHATO | 26.46 | 0 | 0 | 66
94 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Laying of HDPE pipeline and providing FHTC at JDA PWSS Zone-I under JDA PWSS, Kalchini Block under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000323/2021-2022 | 2203/ALD | 11/01/2022 | 12/03/2022 | MAHENDRA CHHETRI | 53.59 | 0 | 0 | 0
95 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Repairing of drainage system & painting of office cum Godown building at Head Work site of Falakata WSS (OLD) under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000267/2021-2022 | 1832/ALD | 10/12/2021 | 08/02/2022 | NARENDRA BHADANI. | 4.47 | 0 | 0 | 63
96 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna ( for AWC and school & others) at JDA WSS (Zone-1) under Alipurduar Division, PHE Dte. Part-2 | HQ-A.E | RWS Kalchini Block | ORD/000371/2021-2022 | 2153/ALD | 06/01/2022 | 05/02/2022 | MAHENDRA CHHETRI | 5.02 | 0 | 0 | 66
97 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna ( for AWC, school & public/Govt. organisations etc. ) at JDA WSS (Existing) under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000372/2021-2022 | 2154/ALD | 06/01/2022 | 05/02/2022 | MAHENDRA CHHETRI | 5.02 | 0 | 0 | 62
98 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jaldhara Jal Swapna ( for public/Govt. organisations etc. ) at JDA WSS (Zone-1) under Alipurduar Division, PHE Dte. Part-3 | HQ-A.E | RWS Kalchini Block | ORD/000353/2021-2022 | 2152/ALD | 06/01/2022 | 05/02/2022 | D. K. & SONS | 5.02 | 0 | 0 | 61
99 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply of various materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | Alipurduar RWS,Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Birpara Sub Division,RWS Alipurduar - I Block,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000432/2021-2022 | 846/ALD | 26/08/2021 | 25/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 502.58 | 0 | 0 | 100
100 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Laying of CI/ DI, HDPE pipe including valve chamber and other misc. works at JDA PWSS ZONE-II under JDA PWSS, Kalchini Block under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000500/2021-2022 | 3005/ALD | 15/03/2022 | 14/04/2022 | DILIP MAHATO | 30.59 | 0 | 0 | 60
101 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Installation of 125mm X 80mm X 90 mtr. Deep Tube Well (Mark-II TW) for fresh drinking water sources(with provision of lowering of sub-merssible pump) by ODEX-115 method of Drilling at Truck Stand of Jaigaon PS (West side) within Alipurduar District under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000566/2021-2022 | 3140/ALD | 25/03/2022 | 14/04/2022 | D. K. & SONS | 3.32 | 0 | 0 | 61
102 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Construction of pathway with paver block and repairing of old H/W site's Guest House of Jaigaon WSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000570/2021-2022 | 3143/ALD | 25/03/2022 | 24/04/2022 | D. K. & SONS | 4.86 | 0 | 0 | 67
103 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Gap filling and culvert crossing along the main road at Zone-II and Zone-I by MS, DI Pipe and other allied works at JDA WSS under Alipurduar Division, PHE Dte | HQ-A.E | RWS Kalchini Block | ORD/000064/2022-2023 | 341/ALD | 02/05/2022 | 16/06/2022 | DILIP MAHATO | 10.82 | 0 | 0 | 63
104 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Construction of Boundary wall 2nd TW site of Jaigaon PWSS (near Hanuman Mandir) under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000571/2021-2022 | 3144/ALD | 25/03/2022 | 09/05/2022 | D. K. & SONS | 4.75 | 0 | 0 | 62
105 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Laying of HDPE pipeline including Providing FHTC at Jaigaon Development Area Zone-II from Krishna Pradhan house to Geeta Chhetri house within Kalchini Block under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000196/2022-2023 | 1222/ALD | 10/08/2022 | 09/10/2022 | MAHENDRA CHHETRI | 36.35 | 0 | 0 | 67
106 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Installation of 125mm X 80mm X 90 mtr. Deep Tube Well (Mark-II TW) for fresh drinking water sources(with provision of lowering of sub-merssible pump) by ODEX-115 method of Drilling at Truck Stand of Jaigaon PS (East side) within Alipurduar District under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000565/2021-2022 | 3139/ALD | 25/03/2022 | 14/04/2022 | MAHENDRA CHHETRI | 3.32 | 0 | 0 | 67
107 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply delivery & installation of 40 KVA Servo Motor operated copper wound line voltage corrector at P/H no. II,Zone III under JAYGAON DEVELOPMENT PROGRAM. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 2,Alipurduar Mechanical sub-division,PH | ORD/000693/2019-2020 | 1372/NMD-II | 06/03/2020 | 06/03/2020 | ORIENTAL ENGINEERING CO. | 4.67 | 7.29 | 156.21 | 0
108 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply of different materials at Alipurduar Divisional Stack Yard under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000727/2020-2021 | 1933/ALD | 23/02/2021 | 25/03/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 1000 | 0 | 0 | 0
109 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Quotation for new service connection at jaigaon TW No- II |  |  | BILL/00038/2022-2023 | BP-124/22-23 | 13/01/2023 | 13/01/2023 | WBSEDCL | 0.69 | 0 | 0 | 0
110 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | QUOTATION FOR EARNEST MONEY DEPOSITION FOR BULK POWER SUPPLY AT JAIGAON CLEAR WATER PUMPING STATION. |  |  | BILL/02072/2023-2024 | BP-2023-24-469 | 07/12/2023 | 07/12/2023 | WBSEDCL | 0.05 | 0 | 0 | 0
111 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Providing FHTC from existing distribution system as per specification for JAIGAON PWSS (Part-1) under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000378/2023-2024 | 169/ALD | 15/01/2024 | 15/03/2024 | DAS CONSTRUCTION | 48.23 | 0 | 0 | 0
112 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Providing FHTC from existing distribution system as per specification for JAIGAON PWSS (Part-2) under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000379/2023-2024 | 170/ALD | 15/01/2024 | 14/04/2024 | AMBITIOUS ENTERPRISE | 53.92 | 0 | 0 | 0
113 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | 16 nos Tubewell fencing work at Torsha river bed by boulder apron with RBT and other allied works at JDA Zone-I PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000406/2024-2025 | 4541/ALD | 26/12/2024 | 24/02/2025 | D.K & SONS | 24.66 | 0 | 0 | 0
114 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Repairing work of existing boundary wall, land development, and pathway of Jaigaon 2nd pump house area near matamandir at Jaigaon WSS under Alipurduar Division, PHE Dte.(SM/05647) | HQ-A.E | RWS Kalchini Block | ORD/000470/2023-2024 | 676/ALD | 06/03/2024 | 05/05/2024 | TAPASH DAS | 9.5 | 0 | 0 | 0
115 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply, Installation & commissioning of Gaseous Chlorination arrangement of capacity 0 - 1 kg/hr for piped water supply scheme for Jaigaon Development Area (JDA) based on Sub Surface Water source of River Torsa, Dist. Alipurduar. (Zone-III,PART-A OHR site) | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000027/2020-2021 | 1082/NMD-II | 05/10/2020 | 03/01/2021 | M/S DILIP MITRA | 23.51 | 18.15 | 77.24 | 100
116 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply, Installation & commissioning of Gaseous Chlorination arrangement of capacity 0 - 1 kg/hr for piped water supply scheme for Jaigaon Development Area (JDA) , Dist. Alipurduar. under Zone-V,PART-B OHR site under NMD-II,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000524/2020-2021 | 1307/NMD-II | 24/12/2020 | 23/01/2021 | M/S SAJAHAN CHOWDHURY | 21.67 | 16.95 | 78.2 | 100
117 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Material Requisition To Resource Division |  |  | RTOR000031/2024-2025 | 4262/ALD | 11/12/2024 | 11/12/2024 | Resource Division | 23.46 | 0 | 0 | 0
118 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Provisional quotation for Bulk Power supply for your proposed premises at Executive Engineer, NMD-II,PHE Dte, Jaigaon Clear water pumping station near Jaigaon Auditorium Ground,Alipurduar. |  |  | BILL/02381/2023-2024 | BP-2023-24-512 | 05/01/2024 | 05/01/2024 | WBSEDCL | 27.61 | 0 | 0 | 0
119 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | New service connection charge for LT Bulk at Jaigaon W/S/S |  |  | BILL/02423/2023-2024 | BP-2023-24-521 | 09/01/2024 | 09/01/2024 | WBSEDCL | 6.56 | 0 | 0 | 0
120 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply, Installation & commissioning of Gaseous Chlorination arrangement of capacity 0 - 1 kg/hr for piped water supply scheme for Jaigaon Development Area (JDA) , Dist. Alipurduar. under Zone-III,PART-B OHR site under NMD-II,PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000525/2020-2021 | 1311/NMD-II | 28/12/2020 | 27/01/2021 | M/S P.P ELECTRICALS | 23.47 | 18.14 | 77.26 | 100
121 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Providing House connection for JAIGAON piped water supply scheme (Old scheme Area) under Alipuduar Division, P.H.E. Dte. Part-2 | HQ-A.E | RWS Kalchini Block | ORD/000318/2020-2021 | 1451/ALD | 25/01/2021 | 11/03/2021 | AQUEDUCT PLASTICS PVT. LTD. | 43.86 | 0 | 0 | 90
122 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Providing House connection for TORSA TG AREA, JAIGAON DEVLOPMENT AREA ZONE-3B under Alipuduar Division, P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000726/2020-2021 | 1764/ALD | 19/02/2021 | 20/04/2021 | AQUEDUCT PLASTICS PVT. LTD. | 40.17 | 0 | 0 | 67
123 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Laying of different dia. Of HDPE pipeline inclu. Providing FHTC and other works at JDA PWSS Zone-5A and 5B under JDA PWSS, Kalchini Block under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000374/2021-2022 | 2374/ALD | 31/01/2022 | 01/04/2022 | AQUEDUCT PLASTICS PVT. LTD. | 52.63 | 0 | 0 | 80
124 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Construction of CWR, High lift Pump House, laying of raising main of Zone-I, Pressure filter, Sub-station (2X500 KW) and other allied works at Head Work Site under Jaigaon Development Area under Alipurduar Division P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000262/2021-2022 | 21-22/1420/ALD | 01/11/2021 | 26/06/2025 | AQUEDUCT PLASTICS PVT. LTD. | 234.63 | 0 | 0 | 38
125 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Construction of Internal Road, Drain, Sub-station (2X500 KW), internal road, chemical house, guard room, Laboratorys and Pressure filter at Head Work Site under Jaigaon Development Area under Alipurduar Division P.H.E. Dte. | HQ-A.E | RWS Kalchini Block | ORD/000486/2021-2022 | 2910/ALD | 08/03/2022 | 20/06/2025 | MAHENDRA CHHETRI | 157.79 | 0 | 0 | 30
126 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Laying of Rising Main (by using metal Pipes) and installation of pressure filters of Zone-II for JDA (Jaigaon Development Authority) Area Water Supply Scheme under Alipurduar District. | HQ-A.E | RWS Kalchini Block | ORD/000001/2022-2023 | 11/ALD | 01/04/2022 | 29/08/2022 | DILIP MAHATO | 206.76 | 0 | 0 | 10
127 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply, Installation & commissioning of Gaseous Chlorination arrangement of capacity 0 - 1 kg/hr for piped water supply scheme for Jaigaon Development Area (JDA) based on Sub Surface Water source of River Torsa, Dist. Alipurduar. (Zone-V, Part-A OHR site) |  |  | ORD/000829/2022-2023 | 1825/NMD-II | 07/11/2022 | 07/07/2023 | S.P ENTERPRISE (SLG) | 2.66 | 0 | 0 | 0
128 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Construction of LT Panel House (16m x 5m) for JDA PWSS under Alipurduar Division PHE Dte | HQ-A.E | RWS Kalchini Block,RWS Kumargram Block | ORD/000007/2023-2024 | 91/ALD | 18/04/2023 | 09/10/2024 | D. K. & SONS | 10.44 | 0 | 0 | 0
129 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Providing Mechanical / Electrical Equipment¿s with all ancillaries and auxiliaries along with disinfection arrangement for Clear Water Pumping Station for Jaigaon, (Zone- I & II ) in the district of Alipurduar under Northern Mechanical Division-II, PHE Dte | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000950/2023-2024 | 2557/NMD-II | 18/08/2023 | 02/01/2026 | WEST BENGAL ENGINEERING CO. | 367.85 | 0 | 0 | 15
130 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply, delivery, installation low lift Submersible Pumping machinery at river bed tubewells in the river Torsa under Jaigaon Development Authority water Supply Scheme in the district of Aliupurduar under Northern Mechanical Division-II,PHE.Dte in the Dist of Alipurduar. |  |  | ORD/001132/2023-2024 | 2898/NMD-II | 18/10/2023 | 15/02/2024 | ORIENTAL ENGINEERING CO. | 240.42 | 0 | 0 | 0
131 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Providing FHTC from existing distribution system as per specification for JAIGAON PWSS (Part-3) under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000380/2023-2024 | 171/ALD | 15/01/2024 | 29/06/2025 | TAPASH DAS | 46.99 | 0 | 0 | 25
132 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supplying & Laying of MS & CIDI pipe's for Raw Water Rising and clear Water Rising main at JDA PWSS under Alipurduar Division, PHE Dte. under North Bengal Circle-I, PHE Dte. | HQ-A.E | RWS Kalchini Block | ORD/000359/2024-2025 | 3560/ALD | 22/10/2024 | 18/08/2025 | MAMATA USHA ENTERPRISE | 862.23 | 0 | 0 | 25
133 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Construction of 2 no pump house, 2no boundary wall, 2 nos TW boring ODEX-165 and laying of HDPE pipeline, FTHC and platform & allied works for Chota Jaigaon under JDA PWSS under Alipurduar Division, PHE Dte. | HQ-A.E | RWS Kalchini Block,RWS Kumargram Block | ORD/000490/2023-2024 | 746/ALD | 12/03/2024 | 02/11/2025 | MAHENDRA CHHETRI | 87.11 | 0 | 0 | 40
134 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Gap filling of HDPE pipeline along with construction of platform at Jaigaon Zone-II under Alipurduar Division PHE Dte. | HQ-A.E | RWS Kalchini Block,RWS Kumargram Block | ORD/000539/2023-2024 | 896/ALD | 15/03/2024 | 05/11/2025 | MAHENDRA CHHETRI | 99.44 | 0 | 0 | 60
135 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Reparing of Pump House at 4th site of Jaigaon PWSS Under Alipurduar Division PHE DTE. |  |  | ORD/000600/2024-2025 | 5430/ALD | 19/03/2025 | 18/05/2025 | D.K & SONS | 0.99 | 0 | 0 | 0
136 | ALIPURDUAR | Kalchini | Alipurduar Division | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Reparing of Pump House at 2nd site of Jaigaon PWSS Under Alipurduar Division PHE DTE |  |  | ORD/000599/2024-2025 | 5429/ALD | 19/03/2025 | 18/05/2025 | TAPASH DAS | 0.84 | 0 | 0 | 0
137 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Modification Work in Connection with Supply, delivery, installation low lift Submersible Pumping machinery at river bed tubewells in the river Torsa under Jaigaon Development Authority water Supply Scheme in the district of Aliupurduar under Northern Mechanical Division-II,PHE.Dte in the Dist of Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P |  | ORD/000054/2025-2026 | 1135/NMD-II | 15/05/2025 | 14/06/2025 | ORIENTAL ENGINEERING CO. | 84 | 0 | 0 | 0
138 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Piped Water Supply Scheme for Jaigaon Development Area (JDA) Based on Sub-Surface Water Source of River Torsa | SM/05647 | New | Supply, delivery, installation, commissioning and Trial run of electro mechanical component along with Cu wound line voltage corrector for Joygaon Water Supply Scheme(JDA) TW No.-V and VI (Add ) chhota joygaon under NMD-II,PHE.Dte,Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000052/2025-2026 | 1120/NMD-II | 08/05/2025 | 08/12/2025 | D.K AND SONS | 20.71 | 0 | 0 | 80
Total | [13 empty] | 5785.58 | 558.26 | 9.65