## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Hantupara Tea Garden Area Piped Water Supply Scheme | SM/05896 | New | Supply, delivery of Electro Mechanical components at HANTAPARA TEA GARDEN Water Supply Scheme IN THE Dist OF ALIPURDUAR under NMD-II,PHE.Dte. |  |  | ORD/000568/2020-2021 | 1426/NMD-II | 28/01/2021 | 27/02/2021 | MUSTAFI CONCERN | 10.22 | 10.22 | 100 | 0
2 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Hantupara Tea Garden Area Piped Water Supply Scheme | SM/05896 | New | Operation and Guarding of Pumping machinery at Pump House No. II under HANTUPARA TG W/S Scheme. In the dist. Of ALIPURDUAR |  |  | ORD/000497/2021-2022 | 759/NMD-II | 08/07/2021 | 08/07/2022 | DIAMOND ELECTRICAL WORKS | 2.97 | 0 | 0 | 0
3 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Hantupara Tea Garden Area Piped Water Supply Scheme | SM/05896 | New | Operation and Guarding of Pumping machinery at Pump House No.I , Under HANTAPARA TG W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000348/2021-2022 | 715/NMD-II | 08/07/2021 | 08/07/2022 | GEETA CONSTRUCTION | 2.97 | 0 | 0 | 0
4 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Hantupara Tea Garden Area Piped Water Supply Scheme | SM/05896 | New | Supply, delivery,of Electro mechanical components at Hantapara T.G Water Supply Scheme & adjoining mouzas in the dist of ALIPURDUAR under NMD-II PHE.Dte Alipurduar. |  |  | ORD/000886/2021-2022 | 418/NMD-II | 23/03/2022 | 22/04/2022 | GOENKA ENTERPRISE | 8.3 | 0 | 0 | 0
5 | ALIPURDUAR | Madarihat | Alipurduar Division | Hantupara Tea Garden Area Piped Water Supply Scheme | SM/05896 | New | Supply & delivery of Desktop CPU-AMD Ryzen5 2400, H320 Gigabyte Mother Board, 8GB DDR4 Ram, ATX Cabinet, SMPS 450 Watt,240 GB SSD,1 TB HDD & Epson printer L-1100 for the use at office of the Assistant Engineer, Alipurduar Sadar Sub-Division, P.H.E. Dte. | HQ-A.E |  | ORD/000240/2022-2023 | 1150/ALD | 02/08/2022 | 09/08/2022 | CYBER NET | 0.99 | 0 | 0 | 0
6 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Hantupara Tea Garden Area Piped Water Supply Scheme | SM/05896 | New | Quotation for Burnt meter at HANTAPARA T.G, T/W no. II , Consumer ID: 402250022,Application no. 4002972224 |  |  | VCH/001294/2022-2023 | BP-49/22-23 | 25/08/2022 | 25/08/2022 | WBSEDCL | 0.09 | 0 | 0 | 0
7 | ALIPURDUAR | Madarihat | Alipurduar Division | Hantupara Tea Garden Area Piped Water Supply Scheme | SM/05896 | New | Laying of DI/MS/HDPE pipeline for the Hantapara WSS (Jamtala Area) under Alipurduar Division, PHE Dte. | Alipurduar RWS,Birpara A.E | Birpara Sub Division,RWS Madarihat - Birpara Block | ORD/000323/2020-2021 | 1455/ALD | 25/01/2021 | 11/03/2021 | M/S SURAJIT DEY & CO | 8.92 | 0 | 0 | 98
8 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Hantupara Tea Garden Area Piped Water Supply Scheme | SM/05896 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at different PWSS under Birpara - Madarihat block in the dist. of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000521/2021-2022 | 1069/NMD-II | 10/09/2021 | 30/09/2021 | CHOWDHURY AND BASU ENTERPRISE | 4.72 | 0 | 0 | 0
9 | ALIPURDUAR | Madarihat | Alipurduar Division | Hantupara Tea Garden Area Piped Water Supply Scheme | SM/05896 | New | Laying of HDPE pipeline for Hantapara Topline under Hatapara WSS within Alipurduar Division, PHE Dte. | Birpara A.E | Birpara Sub Division | ORD/000429/2021-2022 | 2627/ALD | 18/02/2022 | 19/04/2022 | DILIP MAHATO | 16.19 | 0 | 0 | 69
10 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Hantupara Tea Garden Area Piped Water Supply Scheme | SM/05896 | New | Supply, Delivery and fitting fixing of LED fixture inplace of old damage LED at PHE compound of Hantapara TG W/S scheme in the dist. Alipurduar under, NMD-II ,PHE Dte. |  |  | ORD/000445/2022-2023 | 187/AMSD | 04/07/2022 | 14/07/2022 | GEETA CONSTRUCTION | 0.49 | 0 | 0 | 0
11 | ALIPURDUAR | Madarihat | Alipurduar Division | Hantupara Tea Garden Area Piped Water Supply Scheme | SM/05896 | New | Construction of pathway & land development 1no TW (HWS) of Purba Kanthalbari WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000102/2021-2022 | 901/ALD | 03/09/2021 | 03/10/2021 | PINTU SAHA | 4.11 | 0 | 0 | 0
12 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Hantupara Tea Garden Area Piped Water Supply Scheme | SM/05896 | New | Supply, delivery & installation of 15KVA Servo Motor operated Copper wound line voltage corrector for Hantapara TG W/S Scheme at T/W No. III in the dist. of Alipurduar under Northern Mechanical Division-II P.H.E Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000962/2023-2024 | 314/AMSD | 21/08/2023 | 10/09/2023 | M/S A.D. ENTERPRISE | 2.27 | 0 | 0 | 100
Total | [13 empty] | 62.23 | 10.22 | 16.42