## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Madhu Tea Garden Area Piped Water Supply Scheme | SM/05897 | New | Supply, delivery of Electro Mechanical components at Madhu Tea Garden Water Supply Scheme IN THE Dist OF Alipurduar under NMD-II,PHE.Dte. |  |  | ORD/000593/2020-2021 | 1517/NMD-II | 12/02/2021 | 14/03/2021 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 9.47 | 7.87 | 83.06 | 0
2 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Madhu Tea Garden Area Piped Water Supply Scheme | SM/05897 | New | Supply, delivery of Electro Mechanical components at Madhu Tea Garden Water Supply Scheme,T/W No-II IN THE Dist OF Alipurduar under NMD-II,PHE.Dte. |  |  | ORD/000594/2020-2021 | 1518/NMD-II | 12/02/2021 | 14/03/2021 | WEST BENGAL ENGINEERING CO. | 8.88 | 8.85 | 99.66 | 0
3 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Madhu Tea Garden Area Piped Water Supply Scheme | SM/05897 | New | Operation and Guarding of Pumping machinery at Pump House No. II Under MADHU T.G W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000358/2021-2022 | 725/NMD-II | 08/07/2021 | 08/07/2022 | M/S CHANDRANATH MUKHERJEE | 2.97 | 0 | 0 | 0
4 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Madhu Tea Garden Area Piped Water Supply Scheme | SM/05897 | New | Supply, delivery and installation of standby automatically controlled hydrualic diaphragm type Chlorinator for accurate dosing of Chlorine solution at P/H No.I of Shishubari ,BaraHauda , Madhu T.G W/S schemeand P/H No.II of Birpara Madarihat Block in the district of Alipurduar. |  |  | ORD/000546/2021-2022 | 1018/NMD-II | 27/08/2021 | 16/09/2021 | TAPAN BISWAS | 3.5 | 0 | 0 | 0
5 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Madhu Tea Garden Area Piped Water Supply Scheme | SM/05897 | New | Operation and Guarding of Pumping machinery at Pump House No. I Under MADHU T.G W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000439/2021-2022 | 752/NMD-II | 08/07/2021 | 08/07/2022 | MITRA ENTERPRISE | 2.97 | 0 | 0 | 0
6 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Madhu Tea Garden Area Piped Water Supply Scheme | SM/05897 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at different PWSS under Kalchini block in the dist. of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000518/2021-2022 | 1071/NMD-II | 10/09/2021 | 30/09/2021 | R.K ENTERPRISE | 1.85 | 0 | 0 | 0
7 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Madhu Tea Garden Area Piped Water Supply Scheme | SM/05897 | New | Supply, delivery of Electro mechanical components at Madhu T.G Water Supply Scheme & other adjcent mouzas in the dist of ALIPURDUAR under NMD-II, PHE. Dte, Alipurduar. |  |  | ORD/000864/2021-2022 | 306/NMD-II | 10/03/2022 | 09/04/2022 | MUSTAFI CONCERN | 7.55 | 7.55 | 100 | 0
8 | ALIPURDUAR | Kalchini | Northern Mechanical | Madhu Tea Garden Area Piped Water Supply Scheme | SM/05897 | New | New Service Connection Charge |  |  | VCH/000970/2018-2019 | 1140/W/ 18-19 | 01/03/2019 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 10.68 | 0 | 0 | 0
9 | ALIPURDUAR | Kalchini | Northern Mechanical Division II | Madhu Tea Garden Area Piped Water Supply Scheme | SM/05897 | New | Quotation for new service connection at Madhu T.G, P/H no. III, Application no. 4003018858 |  |  | VCH/001471/2022-2023 | BP-94/22-23 | 25/11/2022 |  | WBSEDCL | 0.98 | 0 | 0 | 0
Total | [13 empty] | 48.86 | 24.27 | 49.69