## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Rahimabad Tea Garden Area Piped Water Supply Scheme | SM/05898 | New | Supply, delivery of Electro Mechanical components at RAHIMABAD TEA GARDEN Water Supply Scheme IN THE Dist OF Alipurduar under NMD-II,PHE.Dte. |  |  | ORD/000583/2020-2021 | 1495/NMD-II | 10/02/2021 | 12/03/2021 | RMD TRADING | 8.87 | 17.75 | 200 | 0
2 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Rahimabad Tea Garden Area Piped Water Supply Scheme | SM/05898 | New | Supply, delivery of Electro Mechanical components at Rahimabad TEA Garden Water Supply Scheme and adjoing mouzas in the Dist of Alipurduar under NMD-II,PHE.Dte. |  |  | ORD/000544/2020-2021 | 1325/NMD-II | 30/12/2020 | 29/01/2021 | CHOWDHURY AND BASU ENTERPRISE | 4.32 | 8.64 | 200 | 0
3 | ALIPURDUAR | Kumargram | Alipurduar Division | Rahimabad Tea Garden Area Piped Water Supply Scheme | SM/05898 | New | SUPPLY OF DIFFERENT MATERIALS FOR OFFICE USE UNDER ALIPURDUAR DIVISION PHED |  |  | VCH/000781/2021-2022 | 260/21-22 | 07/10/2021 | 07/10/2021 | PROBHAT CHOWDHURY | 0.26 | 0 | 0 | 0
4 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Rahimabad Tea Garden Area Piped Water Supply Scheme | SM/05898 | New | Yard lighting arrangement at pump House No.-I under Rahimabad Tea Garden Water supply scheme Under Northern Mechanical Division-II P.H.E Dte. |  |  | ORD/000646/2021-2022 | 1101/NMD-II | 20/09/2021 | 20/10/2021 | MUSTAFI CONCERN | 3.17 | 3.17 | 100 | 0
5 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Rahimabad Tea Garden Area Piped Water Supply Scheme | SM/05898 | New | Supply, delivery of Electro mechanical components at Rahimabad T.G Water Supply Scheme & adjoining mouzas in the dist of ALIPURDUAR under NMD-II PHE Dte Alipurduar. |  |  | ORD/000866/2021-2022 | 329/NMD-II | 14/03/2022 | 13/04/2022 | THE BANERJEE CONCERN | 6.77 | 6.77 | 100 | 0
6 | ALIPURDUAR | Kumargram | Alipurduar Division | Rahimabad Tea Garden Area Piped Water Supply Scheme | SM/05898 | New | Supply & delivery of Desktop CPU-AMD Ryzen5 2400, H320 Gigabyte Mother Board, 8GB DDR4 Ram, ATX Cabinet, SMPS 450 Watt,240 GB SSD,1 TB HDD & Epson printer L-1100 for the use at office of the Assistant Engineer,Headquater, Alipurduar Division, P.H.E. Dte. | HQ-A.E |  | ORD/000241/2022-2023 | 1151/ALD | 02/08/2022 | 09/08/2022 | CYBER NET | 0.99 | 0.99 | 100 | 0
7 | ALIPURDUAR | Kumargram | Alipurduar Division | Rahimabad Tea Garden Area Piped Water Supply Scheme | SM/05898 | New | Supply & delivery of Desktop CPU-AMD Ryzen5 2400, H320 Gigabyte Mother Board, 8GB DDR4 Ram, ATX Cabinet, SMPS 450 Watt,240 GB SSD,1 TB HDD & Epson printer L-1100 for the use at Divisional Accounts Section under Alipurduar Division, P.H.E. Dte. | HQ-A.E |  | ORD/000243/2022-2023 | 1153/ALD | 02/08/2022 | 09/08/2022 | CYBER NET | 0.99 | 0.99 | 100 | 0
8 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Rahimabad Tea Garden Area Piped Water Supply Scheme | SM/05898 | New | Supply and delivery of Standby Submersible pump for Rahimabad water supply scheme , P/H-I under Alipurduar Mechanical sub-division in the dist. alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000769/2022-2023 | 607/AMSD | 07/02/2023 | 27/02/2023 | SUNLIT | 4.28 | 4.28 | 100 | 100
9 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Rahimabad Tea Garden Area Piped Water Supply Scheme | SM/05898 | New | Supply and Delivery of Calcium Hypochlorite[Ca(Ocl)2] granules at different PWSS under Kumargram Block in the District of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000533/2020-2021 | 1317/NMD-II | 29/12/2020 | 18/01/2021 | SARKAR ELECTRIC | 1.79 | 0 | 0 | 0
10 | ALIPURDUAR | Kumargram | Alipurduar Division | Rahimabad Tea Garden Area Piped Water Supply Scheme | SM/05898 | New | LAYING DISTRIBUTION LINE FOR RETROFITTING OF FHTC AT KHASRU LINE UNDER RAHIMABAD TG PWSS UNDER ALIPURDUAR DIVISION, PHE DTE. | Alipurduar Sadar Sub Division | Alipurduar Sub Division | ORD/000032/2021-2022 | 580/ALD | 15/07/2021 | 14/08/2021 | M/S BHOWMICK CONSTRUCTION | 12.75 | 20.73 | 162.6 | 71
11 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Rahimabad Tea Garden Area Piped Water Supply Scheme | SM/05898 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at different PWSS under Kumargram block in the dist. of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000520/2021-2022 | 1076/NMD-II | 10/09/2021 | 30/09/2021 | M/S P.P ELECTRICALS | 3.58 | 0 | 0 | 0
12 | ALIPURDUAR | Kumargram | Alipurduar Division | Rahimabad Tea Garden Area Piped Water Supply Scheme | SM/05898 | New | Construction of pathway & land development 1no TW (HWS) of Purba Kanthalbari WSS under Alipurduar Division, PHE Dte. | Alipurduar RWS | Birpara Sub Division | ORD/000102/2021-2022 | 901/ALD | 03/09/2021 | 03/10/2021 | PINTU SAHA | 4.11 | 2.16 | 52.64 | 0
13 | ALIPURDUAR | Kumargram | Alipurduar Division | Rahimabad Tea Garden Area Piped Water Supply Scheme | SM/05898 | New | Supply of different materials for Alipurduar divisional stackyard under Alipurduar Division, PHE Dte. | Alipurduar Sadar Sub Division,Birpara A.E,HQ-A.E | Alipurduar Sub Division,Birpara Sub Division,RWS Alipurduar - II Block,RWS Kalchini Block | ORD/000556/2021-2022 | 855/ALD | 31/08/2021 | 30/09/2021 | EXECUTIVE ENGINEER, RESOURCE DIVISION | 2590.66 | 5 | 0.19 | 0
14 | ALIPURDUAR | Kumargram | Alipurduar Division | Rahimabad Tea Garden Area Piped Water Supply Scheme | SM/05898 | New | Entry of data for house Connection (JJM) of PWSS in website under Alipurduar division, PHE Dte. (for the financial year 2022-2023 from 01/04/2022 onwards) | HQ-A.E |  | ORD/000579/2021-2022 | 3224/ALD | 31/03/2022 | 31/03/2023 | DILIP MAHATO | 4.25 | 4.25 | 100 | 0
15 | ALIPURDUAR | Kumargram | Northern Mechanical Division II | Rahimabad Tea Garden Area Piped Water Supply Scheme | SM/05898 | New | Hiring of Motor Cab (Non-air conditioned) for site visit of JJM Works under the Office of the EE/NMD-II and AE/AMSD, PHE Dte. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/001071/2023-2024 | 329/AMSD | 31/08/2023 | 31/10/2023 | MUSTAFI CONCERN | 0.69 | 0 | 0 | 100
16 | ALIPURDUAR | Kumargram | Alipurduar Division | Rahimabad Tea Garden Area Piped Water Supply Scheme | SM/05898 | New | New Service Connection Charges For ROHIMABAD TG Pump House NO-3 |  |  | BILL/00491/2024-2025 |  | 28/10/2024 | 28/10/2024 | WBSEDCL | 7.4 | 0 | 0 | 0
Total | [13 empty] | 2654.89 | 74.73 | 2.81