## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Northern Mechanical | Augmentation of Dalmore Tea Garden Piped Water Supply | SM/05899 | Augmentation | New Service Connection Charge for TEA GARDENS |  |  | VCH/000605/2018-2019 | 806/W/18-19 | 01/01/2019 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.66 | 0 | 0 | 0
2 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Dalmore Tea Garden Piped Water Supply | SM/05899 | Augmentation | Addle quotation for the Dalmore water supply scheme T/W No. III, under NMD-II, PHE Dte. |  |  | VCH/000813/2019-2020 | 101/19-20 | 17/01/2020 |  | WBSEDCL | 2.98 | 0 | 0 | 0
3 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Dalmore Tea Garden Piped Water Supply | SM/05899 | Augmentation | Supply, delivery of Electro Mechanical components at DOLMORE TEA GARDEN Water Supply Scheme (AUG) IN THE Dist OF Alipurduar under NMD-II,PHE.Dte. |  |  | ORD/000575/2020-2021 | 1456/NMD-II | 02/02/2021 | 04/03/2021 | M/S CHANDRANATH MUKHERJEE | 9.1 | 9.07 | 99.67 | 0
4 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Dalmore Tea Garden Piped Water Supply | SM/05899 | Augmentation | Supply, delivery of Electro Mechanical components at Dolmore Water Supply Scheme,T/W NO-IV IN THE Dist OF Alipurduar under NMD-II,PHE.Dte. |  |  | ORD/000596/2020-2021 | 1512/NMD-II | 12/02/2021 | 14/03/2021 | M/S SAJAHAN CHOWDHURY | 9.1 | 9.07 | 99.67 | 0
5 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Dalmore Tea Garden Piped Water Supply | SM/05899 | Augmentation | Continuation for Operation & guarding of the pumping machinery at Pump House No. III under DALMORE(AUG.) W/S Scheme, in the dist. Of Alipurduar P.H.E.,Dte. |  |  | ORD/000749/2020-2021 | 992/AMSD | 26/03/2021 | 24/06/2021 | M/S P.P ELECTRICALS | 0.72 | 0 | 0 | 0
6 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Dalmore Tea Garden Piped Water Supply | SM/05899 | Augmentation | Operation & guarding of the pumping machinery at Pump House No. III under DALMORE(AUG.) W/S Scheme, in the dist. Of Alipurduar P.H.E.,Dte. |  |  | ORD/000748/2020-2021 | 649/AMSD | 12/11/2020 | 26/02/2021 | M/S P.P ELECTRICALS | 0.8 | 0 | 0 | 0
7 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Dalmore Tea Garden Piped Water Supply | SM/05899 | Augmentation | Continuation for Operation & guarding of the pumping machinery at Pump House No. III under DALMORE(AUG.) W/S Scheme, in the dist. Of Alipurduar P.H.E.,DTE. |  |  | ORD/000623/2021-2022 | 207/AMSD | 25/06/2021 | 25/07/2021 | M/S P.P ELECTRICALS | 0.24 | 0 | 0 | 0
8 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Dalmore Tea Garden Piped Water Supply | SM/05899 | Augmentation | Operation and Guarding of Pumping machinery at Pump House No. III , Under DALMORE TG (AUG)W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000357/2021-2022 | 724/NMD-II | 08/07/2021 | 08/07/2022 | M/S P.P ELECTRICALS | 2.97 | 0 | 0 | 0
9 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Dalmore Tea Garden Piped Water Supply | SM/05899 | Augmentation | Operation and Guarding of Pumping machinery at Pump House No. I , Under DALMORE TG (AUG)W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000418/2021-2022 | 751/NMD-II | 08/07/2021 | 08/07/2022 | SUBODH KUMAR BANIK | 2.97 | 0 | 0 | 0
10 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Dalmore Tea Garden Piped Water Supply | SM/05899 | Augmentation | Operation and Guarding of Pumping machinery at Pump House No. II , Under DALMORE TG (AUG)W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000329/2021-2022 | 696/NMD-II | 08/07/2021 | 08/07/2022 | CHOWDHURY AND BASU ENTERPRISE | 2.97 | 0 | 0 | 0
11 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Dalmore Tea Garden Piped Water Supply | SM/05899 | Augmentation | Supply and delivery of Standby Submersible pump and other allied items for Dalmore and Ramjhora T.G water supply scheme in the dist. Alipurduar under NMD-II. |  |  | ORD/000742/2021-2022 | 61/NMD-II | 21/01/2022 | 20/02/2022 | ASHOKE ADHIKARY | 5.99 | 5.99 | 100 | 0
12 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Dalmore Tea Garden Piped Water Supply | SM/05899 | Augmentation | Supply, delivery of Electro mechanical components at Dalmore T.G Water Supply Scheme and other adjcent moujas, in the dist. of ALIPURDUAR under NMD-II, PHE. Dte, Alipurduar. |  |  | ORD/000863/2021-2022 | 305/NMD-II | 10/03/2022 | 09/04/2022 | GEETA CONSTRUCTION | 10.83 | 10.83 | 100 | 0
13 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Dalmore Tea Garden Piped Water Supply | SM/05899 | Augmentation | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at different PWSS under Birpara - Madarihat block in the dist. of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000521/2021-2022 | 1069/NMD-II | 10/09/2021 | 30/09/2021 | CHOWDHURY AND BASU ENTERPRISE | 4.72 | 0 | 0 | 0
14 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Dalmore Tea Garden Piped Water Supply | SM/05899 | Augmentation | Supply, Delivery and fitting fixing of LED fixture instead of old damage LED at PHE compound of Dalmore TG & Mujnai TG W/S scheme in the dist. Alipurduar under, AMSD ,PHE Dte. |  |  | ORD/000781/2020-2021 | 765/AMSD | 28/12/2020 | 07/01/2021 | PRAGATI CONSTRUCTION COMPANY | 0.37 | 0 | 0 | 0
15 | ALIPURDUAR |  | Northern Mechanical Division II | Augmentation of Dalmore Tea Garden Piped Water Supply | SM/05899 | Augmentation | Supply, delivery and installation of 30 KVA servo motor operated Copper wound line voltage corrector at DALMORE T.G W/S Scheme TW NO- I under NMD-II, P.H.E. Dte.Alipurduar. |  |  | ORD/000040/2020-2021 | 1112/NMD-II | 08/10/2020 | 07/11/2020 | B.B CONCERNED | 3.93 | 3.93 | 100 | 0
Total | [13 empty] | 70.34 | 38.9 | 55.3