## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR | Madarihat | Northern Mechanical | Dekhlapara Tea Garden Area Piped Water Supply Scheme | SM/05912 | New | New Service Connection Charge for TEA GARDENS |  |  | VCH/000605/2018-2019 | 806/W/18-19 | 01/01/2019 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 12.66 | 0 | 0 | 0
2 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dekhlapara Tea Garden Area Piped Water Supply Scheme | SM/05912 | New | Publication of advertisement in newspaper (Invoice no. GA/07/0028/19-20 ) |  |  | VCH/000594/2019-2020 | null | 04/12/2019 |  | GENESIS ADVERTISING PVT.LTD. | 0.09 | 0 | 0 | 0
3 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dekhlapara Tea Garden Area Piped Water Supply Scheme | SM/05912 | New | Publication of advertisement in newspaper (Invoice no. GA/07/0614/19-20 ) |  |  | VCH/000723/2019-2020 | null | 11/12/2019 |  | GENESIS ADVERTISING PVT.LTD. | 0.32 | 0 | 0 | 0
4 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dekhlapara Tea Garden Area Piped Water Supply Scheme | SM/05912 | New | Publication of advertisement in newspaper (Invoice no. GA/08/1037/19-20 ) |  |  | VCH/000728/2019-2020 | null | 11/12/2019 |  | GENESIS ADVERTISING PVT.LTD. | 0.03 | 0 | 0 | 0
5 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dekhlapara Tea Garden Area Piped Water Supply Scheme | SM/05912 | New | Publication of advertisement in newspaper (Invoice no. GA/08/0812/19-20 ) |  |  | VCH/000727/2019-2020 | 143/19-20 | 19/02/2020 |  | GENESIS ADVERTISING PVT.LTD. | 0.18 | 0 | 0 | 0
6 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dekhlapara Tea Garden Area Piped Water Supply Scheme | SM/05912 | New | Quotation for New service connection , Dekhlapara, T/W No. III. Application No. 4002574447 |  |  | VCH/001108/2020-2021 | 171/20-21 | 27/11/2020 |  | WBSEDCL | 0.85 | 0 | 0 | 0
7 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dekhlapara Tea Garden Area Piped Water Supply Scheme | SM/05912 | New | Operation & guarding of the pumping machinery at Pump House No. III under DEKHLAPARA TG W/S Scheme, in the dist. Of Alipurduar P.H.E.,Dte. |  |  | ORD/000448/2021-2022 | 74/AMSD | 28/04/2021 | 27/07/2021 | DEY ENTERPRISE (MALDA) | 0.75 | 0 | 0 | 0
8 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dekhlapara Tea Garden Area Piped Water Supply Scheme | SM/05912 | New | Operation and Guarding of Pumping machinery at Pump House No. II ,Under DEKHLAPARA TG W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000372/2021-2022 | 735/NMD-II | 08/07/2021 | 08/07/2022 | M/S UTPAL CHAKRABORTY & CO. | 2.97 | 0 | 0 | 0
9 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dekhlapara Tea Garden Area Piped Water Supply Scheme | SM/05912 | New | Operation and Guarding of Pumping machinery at Pump House No. III , Under DEKHLAPARA TG W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000350/2021-2022 | 717/NMD-II | 08/07/2021 | 08/07/2022 | DEY ENTERPRISE (MALDA) | 2.97 | 0 | 0 | 0
10 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dekhlapara Tea Garden Area Piped Water Supply Scheme | SM/05912 | New | Operation and Guarding of Pumping machinery at Pump House No. I, Under DEKHLAPARA TG W/S Scheme, in the dist. Of Alipurduar. |  |  | ORD/000351/2021-2022 | 718/NMD-II | 08/07/2021 | 08/07/2022 | QUAZI NOZRUL ISLAM | 2.97 | 0 | 0 | 0
11 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dekhlapara Tea Garden Area Piped Water Supply Scheme | SM/05912 | New | Withdrawing & installation of 12.5 HP Submersible pump machinery and repairing the same under DEKHLAPARA TG WATER SUPPLY SCHEME,P/H No-I under Northern Mechanical Division-II Phe. Dte. In the dist. Of Alipurduar. |  |  | ORD/000842/2021-2022 | 235/AMSD | 09/07/2021 | 19/07/2021 | PRAGATI CONSTRUCTION COMPANY | 0.43 | 0 | 0 | 0
12 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dekhlapara Tea Garden Area Piped Water Supply Scheme | SM/05912 | New | "Supply and delivery of Calcium Hypochlorite [Ca(Ocl)₂] granules at different PWSS under Birpara - Madarihat block in the dist. of Alipurduar under Northern Mechanical Division-II,PHE Dte. |  |  | ORD/000521/2021-2022 | 1069/NMD-II | 10/09/2021 | 30/09/2021 | CHOWDHURY AND BASU ENTERPRISE | 4.72 | 0 | 0 | 0
13 | ALIPURDUAR | Madarihat | Northern Mechanical Division II | Dekhlapara Tea Garden Area Piped Water Supply Scheme | SM/05912 | New | Supply & delivery of standby automatically controlled hydrualic diaphragm type Chlorinator for accurate dosing of Chlorine solution at Dekhlapara T.G P/H No.-I , Birpara p/H No.I, Paschim Khairbari P/H No.II ,Gargenda P/h No.II, Dhumchipara P/HNo.I in the district of Alipurduar under NMD-II ,P.H.E Dte. |  |  | ORD/000522/2021-2022 | 1070/NMD-II | 10/09/2021 | 30/09/2021 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 3.76 | 0 | 0 | 0
Total | [13 empty] | 32.69 | 0 | 0