## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Northern Mechanical | Construction of RBTW with India Mark-II hand pump under NRDWP 2016-17 [141 Nos.] | SM/05988 | New | Supply of Fuel & Other Consumable items |  |  | VCH/000084/2020-2021 | 39/W/20-21 | 03/04/2020 |  | M/S MILLENNIUM FUEL CENTRE | 9.72 | 0 | 0 | 0
2 | ALIPURDUAR |  | Northern Mechanical | Construction of RBTW with India Mark-II hand pump under NRDWP 2016-17 [141 Nos.] | SM/05988 | New | Construction of platform and installation of IM-II hand pump / extra deep tube well in the district of Darjeeling (plains) /Jalpaiguri / Alipurduar under Northern Mechanical Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000198/2021-2022 | 50/DSD | 10/06/2021 | 25/06/2021 | M/S UTPAL CHAKRABORTY & CO. | 0.95 | 0 | 0 | 0
3 | ALIPURDUAR |  | Northern Mechanical | Construction of RBTW with India Mark-II hand pump under NRDWP 2016-17 [141 Nos.] | SM/05988 | New | Construction of Platform and Installation of IM-II Hand Pump / Extra Deep Tube well in the dist. Of Darjeeling / Jalpaiguri / Alipurduar in the different RBTW (Spot Source) under Northern Mechanical Sub-Division (Drilling), PHE, Dte. | Driller-in-Charge | Junior Engineer | ORD/000717/2020-2021 | 682/DSD | 12/02/2021 | 27/02/2021 | M/S UTPAL CHAKRABORTY & CO. | 0.96 | 0 | 0 | 0
4 | ALIPURDUAR |  | Northern Mechanical | Construction of RBTW with India Mark-II hand pump under NRDWP 2016-17 [141 Nos.] | SM/05988 | New | Fabricating of 128mm ID M.S Top of Cashing Shoe (Bit Tube) at Banarhat for construction of spot sources tube well under Northern Mechanical Sub-Division (D), P.H.E, Dte. | Driller-in-Charge | Junior Engineer | ORD/000450/2021-2022 | 84/DSD | 28/07/2021 | 04/08/2021 | R.K.ENTERPRISES | 0.6 | 0 | 0 | 0
5 | ALIPURDUAR |  | Northern Mechanical | Construction of RBTW with India Mark-II hand pump under NRDWP 2016-17 [141 Nos.] | SM/05988 | New | Surrender unspent Jal Jeevan Mission Fund to Jal Jeevan Mission West Bengal ESCROW AC |  |  | VCH/001782/2021-2022 | 295/W/21-22 | 17/03/2022 |  | JAL JEEVAN MISSION WEST BENGAL ESCROW AC | 90.18 | 0 | 0 | 0
Total | [13 empty] | 102.41 | 0 | 0