## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | ALIPURDUAR |  | Northern Mechanical Division II | Construction of Office Building for Northern Mechanical Division-II, PHE Dte. at Alipurduar | SM/06172 | New | Soil investigation work inconnection of construction of office building for the Northern Mechanical Division-II, PHE, Dte. Alipurduar |  |  | VCH/000752/2019-2020 | 121/19-20 | 05/02/2020 | 05/02/2020 | SUBIR CHANDRA CHOWDHURY | 1.03 | 0 | 0 | 0
2 | ALIPURDUAR |  | Northern Mechanical Division II | Construction of Office Building for Northern Mechanical Division-II, PHE Dte. at Alipurduar | SM/06172 | New | Supply and Delivery of Furniture in the office of the Assistant Engineer in the dist of Coochbehar under CMSD PHE Dte. |  |  | ORD/000573/2020-2021 | 1042/CMSD | 20/01/2021 | 04/02/2021 | MUSTAFI CONCERN | 0.3 | 0 | 0 | 0
3 | ALIPURDUAR |  | Alipurduar Division | Construction of Office Building for Northern Mechanical Division-II, PHE Dte. at Alipurduar | SM/06172 | New | Sinking of ODEX-165 T/well & Construction of Northern Mechl. Division Office - II cum Laboratory cum Water Collection Center under Alipurduar Division PHED. |  |  | ORD/000067/2020-2021 | 640/ALD | 04/09/2020 | 01/02/2021 | UJJWAL ROY | 162.62 | 0 | 0 | 0
4 | ALIPURDUAR |  | Northern Mechanical Division II | Construction of Office Building for Northern Mechanical Division-II, PHE Dte. at Alipurduar | SM/06172 | New | Internal wiring arrangement and Others allied works at newly constructed Office building for Office of the Executive Engineer ,NMD-II ,PHE Dte, Alipurduar. |  |  | ORD/000719/2021-2022 | 1380/NMD-II | 22/12/2021 | 21/01/2022 | ALPHA ENTERPRISE | 4.84 | 4.79 | 98.94 | 0
5 | ALIPURDUAR |  | Northern Mechanical Division II | Construction of Office Building for Northern Mechanical Division-II, PHE Dte. at Alipurduar | SM/06172 | New | Sinking of ODEX-165, T/Well and construction of Northern Mech. Division-II cum Laboratory cum water collection center under Alipurduar Division PHED. |  |  | VCH/001312/2022-2023 |  | 29/09/2022 | 29/09/2022 | UJJWAL ROY | 58.93 | 0 | 0 | 0
6 | ALIPURDUAR |  | Northern Mechanical Division II | Construction of Office Building for Northern Mechanical Division-II, PHE Dte. at Alipurduar | SM/06172 | New | " Drawing of distribution wiring including earthing arrangement and Others allied works at Ground floor at newly constructed Office building for Office of the Executive Engineer , NMD-II , PHE. Dte, Alipurduar." |  |  | ORD/000309/2022-2023 | 636/NMD-II | 20/05/2022 | 19/06/2022 | ALPHA ENTERPRISE | 4.22 | 4.22 | 100 | 0
7 | ALIPURDUAR |  | Northern Mechanical Division II | Construction of Office Building for Northern Mechanical Division-II, PHE Dte. at Alipurduar | SM/06172 | New | Drawing of distribution wiring at 1st Floor and 2 nd floor and Others allied works at newly constructed Office building for Office of the Executive Engineer ,NMD-II ,PHE. Dte, Alipurduar. |  |  | ORD/000024/2022-2023 | 628/NMD-II | 13/05/2022 | 12/06/2022 | ALPHA ENTERPRISE | 2.89 | 2.89 | 100 | 0
8 | ALIPURDUAR |  | Northern Mechanical Division II | Construction of Office Building for Northern Mechanical Division-II, PHE Dte. at Alipurduar | SM/06172 | New | Drawing of Unsheathed Single core stranded Copper Wire at 1st Floor and Others allied works at newly constructed Office building for Office of the Executive Engineer ,NMD-II ,PHE. Dte, Alipurduar. |  |  | ORD/000025/2022-2023 | 623/NMD-II | 13/05/2022 | 12/06/2022 | ALPHA ENTERPRISE | 2.69 | 2.66 | 99 | 0
9 | ALIPURDUAR |  | Northern Mechanical Division II | Construction of Office Building for Northern Mechanical Division-II, PHE Dte. at Alipurduar | SM/06172 | New | Internal wiring including Supply and fixing of TPN and SPN DB with allied works at 3rd floor of newly constructed Office building for Office of the Assistant Engineer ,AMSD, PHE.Dte,Alipurduar. |  |  | ORD/000022/2022-2023 | 113/AMSD | 27/05/2022 | 11/06/2022 | ALPHA ENTERPRISE | 1.17 | 1.14 | 97.55 | 0
10 | ALIPURDUAR |  | Northern Mechanical Division II | Construction of Office Building for Northern Mechanical Division-II, PHE Dte. at Alipurduar | SM/06172 | New | Internal illumination system for New Office building of the Executive Engineer, NMD-II, PHE. Dte and Office of the Assistant Engineer, AMSD,PHE Dte Dist-Alipurduar. | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Cooch-Behar Mechanical Sub-Division, | ORD/000697/2022-2023 | 1984/NMD-II | 07/12/2022 | 27/12/2022 | ALPHA ENTERPRISE | 6.39 | 6.39 | 100 | 0
11 | ALIPURDUAR |  | Northern Mechanical Division II | Construction of Office Building for Northern Mechanical Division-II, PHE Dte. at Alipurduar | SM/06172 | New | Construction of Boundary Wall for the office premises of Northern Mechanical Division-II, PHE Dte | Assistant Engineer,Alipurduar Mechanical Sub-Division,P | Junior Engineer 1, Northern Mechanical Division-II,PHE | ORD/000955/2023-2024 | 2555/NMD-II | 17/08/2023 | 16/10/2023 | WILFUL UNEMPLOYED ENGINEERS CO OPERATIVE SOCIETY LIMITED | 11.9 | 0 | 0 | 100
Total | [13 empty] | 256.99 | 22.1 | 8.6